**STEPS FOR NET METERING (Solar/ Wind Generation) APPLICATION PROCESS**

* **Distributed Generator Facility**
* **Solar/Wind energy resource for generation of electricity from 1KW to 1MW**
* **Eligible Distributed Generator**
* **3 Phase 400V or 11 KV Consumers with proper sanctioned Load as per Solar Generation i.e. Domestic, Commercial, Agricultural or Industrial, who owns operates Distributed Generated Facility**
* **Eligible DG submits application along with required documents in MEPCO Office (Schedule I-VII of Regulations) in Concerned MEPCO office XEN/SE/Chief Engineer.**
* **MEPCO office (XEN/SE/Chief Engineer) provides acknowledgement whether application is complete or Not.**
* **If application is complete MEPCO office (XEN/SE/Chief Engineer) performs an initial review to see whether it qualifies for interconnection facility Or Not.**
* **If application is incomplete, applicant will provide documents within 7 days.**
* **If application is complete MEPCO office (XEN/SE/Chief Engineer) performs an initial review to see whether it qualifies for interconnection facility.**
* **MEPCO office (SDO/XEN/SE/Chief Engineer) performs technical feasibility verification within 20 days.**
* **In case proposed facility is not technically feasible MEPCO office (SDO/XEN/SE/Chief Engineer) informs about reasons of rejection within 3 working days after completion of initial review.**
* **If facility is technically feasible MEPCO office (SDO/XEN/SE/Chief Engineer) approves installation of SRTPV+ & enters into an agreement within 10 days (Schedule-I- VII of Regulations). Completed file will be sent to SDO Net Metering Cell MEPCO H/Q Multan.**
* **MEPCO Net Metering Cell sends copy of agreement to NEPRA within 7 working days of its signing. MEPCO shall forward the application for grant of License (Schedule-II of Regulations).**
* **Net Metering shall commence in upon grant of license to DG in accordance with in Regulation IV of these regulations.**
* **MEPCO will issue connection charge estimate within 7 working days of agreement signing after License issued by NEPRA or issue a NOC for self purchase of meters if meters are not available within MEPCO. (Consumer must apply for self purchase in SE or XEN or Chief Engineer office).**
* **Applicant shall make payment of estimate within 20 days or provide self purchased two bidirectional meters within a week after getting a NOC from concerned MEPCO office (XEN/SE/Chief Engineer) .**
* **MEPCO shall install/Commission the DG facility within 30 days of payment of Demand Notices or after provision of self purchased bidirectional meters and tested by MEPCO M&T Department within a week.**
* **The file is sent from concerned SDO office to RO office for Billing( feeding of CP-136/137 Change with application # starting with "N" and feeding of MCO CP138 with net meters readings/parameters.**