## abstract
Progress of Net Metering (Dated: 07-06-2018)
Description | Detail | Capacity (KW) | Remarks
No. of Applications Received | 17 | 722.08 | -
Genereation licences applied to NEPRA | 17 | 722.08 | -
Genereation licences issued by NEPRA | 17 | 722.08 | -
Genereation licences pending at NEPRA | 0 | 0 | -
No. of Connections Installed | 15 | 693.12 | Billing of 12 Connections is Started. Billing of 3 Connections is under process.
Applications Under Process | 2 | 28.96 | Demand Notice of bidirectional meters issued to consumers

## circle wise abstract
MEPCO Circlewise Progress of Net Metering (Dated:07-06-2018) on Roshan Pakistan App
Circles Names | Circles Codes | Total Sanctioned/ Connected Load (KW) | Total required load for Net Metering (KW) | Generation (KW) | Total Applications | Billing Started | Applied to NEPRA | Total connections |  | Remarks
[8 empty] | Installed | Remaining
Multan | 15100 | 1307 | 271.46 | 242.5 | 10 | 7 | 0 | 8 | 2 | 2#DN ISSUED FOR BIDIRECTIONAL NET METERS. 1#Billing under Process.
Bahawalpur | 15400 | 16 | 8 | 8 | 2 | 1 | 0 | 2 | 0 | 1#Billing under Process.
Sahiwal | 15500 | 12 | 7.62 | 7.62 | 2 | 1 | 0 | 2 | 0 | 1#Billing under Process.
Khanewal | 15900 | 5508 | 435 | 435 | 3 | 3 | 0 | 3 | 0 | -
Total |  | 6843 | 722.08 | 693.12 | 17 | 12 | 0 | 15 | 2 | Net Connections in Progress=2

## tariff wise abstract
Progress of Net Metering Tariff wise Abstract (Dated: 07-06-2018)
Sr. No. | Type | Tariff | No. Of Connections | Meters Installed | Under Process
1 | Domestic | A-1a(01) | 1 | 0 | 1 connection DN issued.
|  | A-1b(03)T | 8 | 8 | Connection Installed. Billing under process.
2 | Commercial | A-2a(04) | 1 | 1 | Connection Installed. Billing started.
|  | A-2c(06)T | 4 | 4 | 4 meters installed (Billing of 2 connections started and 2 connection billing under process).
3 | Industrial | B2b(12)T | 1 | 0 | 1 connection Demand Notice issued.
|  | B3(14)T | 2 | 2 | Connection Installed. Billing started.
|  | Total | 17 | 15

## Net-Metering-Info
NET METERING APPLICATION(S) INFORMATION/STATUS
COMPANY NAME: MEPCO | [16 empty] | Dated:07-06-2018
Application No. | Name of Applicant | Sub Division Code | Tariff | Application Date | Reference No. | Sanctioned Load | Required Load for Net Metering | Name of Installer | Applied To NEPRA (Yes or No) | Generation Licence | Feeder | Installation Status (Installed or Uninstalled) | Installation Date | Billing Started (Yes or No) | Billing Start Date | Generation (KW) | Remarks | Current Position (What is Present Status i.e. either with installer or SDO or NEPRA etc.)
1 | OFFICE BUILDING TEHSILDAR LODHRAN NEAR MARKET COMMITTEE OFFICE LODHRAN | 15421 | A-1b(03)T | 2016-06-18 | 03154210167800 | 11 | 3 | M/S Creative Electronics | Yes | DGL/75/2017 | City Lodhran | Installed | 2018-01-06 | Yes | 2018-01-10 | 3 | Connection Installed. Billing Started | -
2 | XEN CIVIL MEPCO | 15173 | A-1b(03)T | 2016-07-12 | 13151734972100 | 12 | 3 | Reap | Yes | DGL/48/2017 | Wapda Colony | Installed | 2016-07-28 | Yes | 2016-08-23 | 3 | Connection Installed. Billing Started | -
3 | KHALID NAZEER CMISSIONER SAHIWAL | 15512 | A-1b(03)T | 2016-08-12 | 12155121038000 | 7 | 3 | M/S Creative Electronics | Yes | DGL/74/2017 | Civil Line | Installed | 2018-05-10 | NO | Billing will start this month billing cycle | 3 | Billing will start this month billing cycle | Billing Under Process
4 | MALIK NOOR ASGHAR BUCHA S/O MLK NOOR MUHAMMAD BUCHA THE GRAND COMMERCIAL BUILDING BUCH VILLAS H/S BOSAN ROAD MTN | 15175 | A-2c(06)T | 2016-09-12 | 27151758887001 | 857 | 25.5 | Orient Energies (Pvt) Ltd. | Yes | DGL/83/2017 | Buch Villas | Installed | 2018-01-17 | Yes | 2018-03-01 | 25.5 | Connection Installed. Billing Started | -
5 | Asif Iqbal SM Bashir Agencies | 15514 | A-2a(04) | 2016-12-15 | 03155140275502- old 28155140275502 | 5 | 4.62 | Royal Energy Sultan Electronics | Yes | DGL/80/2017 | College Road | Installed | 2018-01-18 | Yes | 2018-02-12 | 4.62 | Connection Installed. Billing Started | -
6 | MUHAMMAD ARSHAD NADEEM S-O MHAMMAD ASHIQ ST NO 1 MADINA ABAD CLY MTN MULTAN | 15132 | A-1b(03)T | 2017-01-06 | 13151322030405 | 5 | 10 | Solar Tech. | Yes | DGL/117/2017 | Timber Market | Installed | 2017-12-17 | Yes | 2017-12-21 | 10 | Connection Installed. Billing Started | -
7 | SAJIDA KHALID W/O CH.KHALID LATIF PUNJAB SMALL INDUSTRIES MTN | 15175 | A-1b(03)T | 2017-01-26 | 17151753136101 | 5 | 10 | Pak Friends Enterprises | Yes | DGL/107/2017 | Peer Akbar Shah | Installed | 2017-12-19 | Yes | 2017-12-20 | 10 | Connection Installed. Billing Started | -
8 | UNILEVER PAKISTAN LIMITED TEA FACTORY CHAK NO.88-A10R KHANEWAL | 15913 | B3(14)T | 2017-02-08 | 27159132372500 | 503 | 110 | Reon | Yes | DGL/106/2017 | UNILEVER TEA FACTORY | Installed | 2018-01-16 | Yes | 2018-02-03 | 110 | Connection Installed. Billing Started | -
9 | KHAWAJA MUHAMMAD YOUNIS S-O KHAWAJA MUHAMMAD MASOOD FATIMA MODEL SCHOOL MULTAN ROAD K.WALA | 15921 | A-1b(03)T | 2017-03-03 | 28159210647407 | 6 | 5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/76/2017 | Masood Spinning-2 | Installed | 2017-12-21 | Yes | 2018-02-13 | 5 | Connection Installed. Billing Started | -
10 | KH MUHAMMAD YOUNIS S-O MUHAMMAD MASOOD 13 B OFFICER CLY MULTAN | 15172 | A-1b(03)T | 2017-03-03 | 18151723474200 | 12 | 32 | Preimer Energy (Pvt) Ltd. | Yes | DGL/78/2017 | Eid Gah | Installed | 2017-12-19 | Yes | 2017-12-27 | 32 | Connection Installed. Billing Started | -
11 | MEHMOOD TEXTILE MILLS LTD MULTAN LOHARI GATE MULTAN CITY | 15113 | A-2c(06)T | 2017-03-03 | 27151130721400 | 200 | 64 | Preimer Energy (Pvt) Ltd. | Yes | DGL/77/2017 | Abdali Road | Installed | 2018-01-29 | Yes | 2018-02-03 | 64 | Connection Installed. Billing Started | -
12 | Kh M YOUNAS M/S MASOOD SPINNING MILLS UNIT NO.02 04-KM MULTAN ROAD KABIR WALA | 15921 | B3(14)T | 2017-03-03 | 30159212533901 | 4999 | 320 | Preimer Energy (Pvt) Ltd. | Yes | DGL/79/2017 | Masood Spinning-2 | Installed | 2018-01-31 | Yes | 2018-02-03 | 320 | Connection Installed. Billing Started | -
13 | NAIMAT ULLAH S.O ALLAH BACHAYA QURESHI 259-N WAPDA TOWN-11 MTN | 15175 | A-1b(03)T | - | 17151753132415 | 5 | 10 | - | Yes | DGL/128/2017 | Wapda Town | Installed | 2017-12-19 | YES | 2017-12-20 | 10 | Connection Installed. Billing Started | -
14 | NASEEM AHMAD/ FAZAL CLOTH MILLS 59/3 ABDALI ROAD MULTAN | 15117 | A-2c(06)T | 2018-02-19 | 27151170144100 | 145 | 88 | Preimer Energy (Pvt) Ltd. | Yes | DGL/349/2018 | Hassan Perwana | Installed | 2018-05-15 | - | Billing will start this month billing cycle | 88 | Billing will start this month billing cycle | Billing Under Process
15 | ALLIED ENGINEERING & SERVICES HAMID PUR KANORA SHER SHAH BY PASS MTN | 15138 | B2b (12)T | 2018-03-09 | 27151380994405 | 60 | 23.76 | AYK (Pvt) Ltd. | Yes | DGL/343/20178 | Basti Balail | Un Installed | - | - | - | - | Demand Notice issued to consumer for bidirectional Meter | NEPRA Issued the licence on 16-04-2018
16 | AMIR AWAIS GHAURI BX-586/1 SADIQ COLONY BAHAWAL PUR | 15441 | A-2c(06)T | 2018-03-12 | 17154410396400 | 5 | 5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/348/2018 | N. Mahal (Cantt) | Installed | 2018-05-15 | NO | Billing will start this month billing cycle | 5 | Billing will start this month billing cycle | Billing Under Process
17 | HAMEED RAZA S/O AMEER UD DIN AT HOUSE #2 HAMZA STREET BOSAN ROAD MULTAN | 15171 | A-1a(01) | 2018-04-03 | 13151717096201 | 2 | 5.2 | Preimer Energy (Pvt) Ltd. | Yes | DGL/358/2018 | Sabzazar | Un Installed | - | - | - | - | Demand Notice issued to consumer for bidirectional Meter | NEPRA Issued the licence on 24-04-2018
|  |  | Applicant total (KW)= |  |  | 722.08 | [5 empty] | Generation total (KW)= |  |  | 693.12