## abstract
Progress of Net Metering (Dated: 10-10-2018)
Description | Detail | Capacity (KW) | Remarks | Formulas
No. of Applications Received | 25 | 1291.26 | - | 1291.26
Genereation licences applied to NEPRA | 25 | 1291.26 | -
Genereation licences issued by NEPRA | 23 | 1268.26 | - | 1268.26
Genereation licences pending at NEPRA | 2 | 23 | Applied To NEPRA 15-08-2018 & 01-10-2018 | 23
No. of Connections Installed | 18 | 902.32 | Billing of 16 Connections Started. 2# Connections billing will start in 10/2018
Applications Under Process | 5 | 365.94 | 2 #Connections DN for bidirectional meters Issued to Consumer. 03# connections 357.76 KW, permission granted to consumers on 12/09/2018 for purchase of meters. Meters will be installed after provision of meters by consumers. | 357.76

## circle wise abstract
MEPCO Circlewise Progress of Net Metering on Roshan Pakistan App (Dated:10-10-2018)
Circles Names | Circles Codes | Total Sanctioned/ Connected Load (KW) | Total required load for Net Metering (KW) | Generation (KW) | Total Applications | Billing Started | Applied to NEPRA | Total connections |  | Remarks
[8 empty] | Installed | Remaining
Multan | 15100 | 1315 | 277.52 | 247.7 | 12 | 9 | 1 | 9 | 2 | 1# Applied To NEPRA For DG License On 15-08-2018. 1# Connection DN Issued To Consumer. FOR 1 #CONNECTION Permission granted to consumer on 12/09/2018 for purchase of meter. Meters will be installed after provision of meters by consumer.
Vehari | 15300 | 200 | 192 | 192 | 1 | 0 | 0 | 1 | 0 | Meter installed on 08/10/2018. Billing will start in 10/2018
Bahawalpur | 15400 | 29 | 28 | 8 | 3 | 2 | 1 | 2 | 1 | 1# connection applied to NEPRA on 01/10/2018
Sahiwal | 15500 | 12 | 7.62 | 7.62 | 2 | 2 | 0 | 2 | 0 | -
Rahim Yar Khan | 15600 | 12 | 12 | 12 | 1 | 0 | 0 | 1 | 0 | Meter installed on 14/09/2018. Billing will start in 10/2018
Bahawal Nagar | 15800 | 642 | 334 | 0 | 2 | 0 | 0 | 0 | 2 | Permission granted to consumers on 12/09/2018 for purchase of meter. Meters will be installed after provision of meters by consumers.
Khanewal | 15900 | 5512 | 440 | 435 | 4 | 3 | 0 | 3 | 1 | 1 connection in progress. Demand of meter sent to Manager MM.
Total |  | 7722 | 1291.14 | 902.32 | 25 | 16 | 2 | 18 | 6 | 2# connections billing will start in 10/2018.

## tariff wise abstract
Progress of Net Metering Tariff wise Abstract (Dated: 10-10-2018)
Sr. No. | Type | Tariff | No. Of Connections | Meters Installed | Under Process
1 | Domestic | A-1a(01) | 3 | 2 | 1 Connection Applied To NEPRA For DG License On 15-08-2018.
|  | A-1b(03)T | 10 | 8 | DN for bidirectional meters issued to Consumer. 1 connection applied to NEPRA on 01/10/2018
2 | Commercial | A-2a(04) | 2 | 1 | Connection Installed. Billing started. 1 Connection under process.
|  | A-2c(06)T | 6 | 5 | 5 meters installed (Billing of 4 connections started). 1# connections under process. 1# billing will start in 10/2018
3 | Industrial | B2b(12)T | 2 | 0 | 1 connection DN Paid and Demand sent to Manager (MM). Permission granted to consumers on 12/09/2018 for purchase of meter. Meters will be installed after provision of meters by consumers.
|  | B3(14)T | 2 | 2 | Connection Installed. Billing started.
|  | Total | 25 | 18

## year wise abstract
NET METERING APPLICATION(S) INFORMATION/STATUS
COMPANY NAME: MEPCO | [7 empty] | Dated:10-10-2018
Description | 2016 |  | 2017 |  | 2018 |  | TOTAL Connections | TOTAL Load | Pending connections 2018 | Pending Load 2018 | REMARKS
| Connections | Load For Net Metering (KW) | Connections | Load For Net Metering (KW) | Connections | Load For Net Metering (KW)
Number of Connections applied to MEPCO | 5 | 39.12 | 10 | 868 | 10 | 384.14 | 25 | 1291.26 | - | - | 25 applications received
Number of Generation Licenses applied to NEPRA | 0 | 0 | 13 | 600.12 | 12 | 691.14 | 25 | 1291.26 | - | - | 25 applications applied to NEPRA
Number of Generation Licenses issued by NEPRA | 0 | 0 | 13 | 600.12 | 10 | 668.14 | 23 | 1268.26 | 2 | 23 | Applied to NEPRA in 08/2018 and 10/2018 | 344.96
Number of Connections Installed | 1 | 3 | 5 | 67 | 12 | 832.32 | 18 | 902.32 | 4 | 365.94 | Three connections 536.96 KW meters not installed due to non-availability of meters within Manager (MM) MEPCO. Permission granted to consumers on 12/09/2018 and 01/10/2018 for purchase of meters. Meter will be installed after provision of meter by consumers. | 192 | 902.32
Number of Connection Where Billing Started | 1 | 3 | 4 | 62 | 11 | 633.2 | 16 | 698.2 | 2 | 204.12 | 2 connections billing will start in 10/2018 | 536.96 | 192
710.32

## dg licences sheet
NEPRA Generation Licences for MEPCO Net Metering Consumers Till Dated:10-10-2018
Sr.# | Date | Expiry Date | Generation Licence No. And Application No. And Name
1 | 2017-02-02 | 2020-02-01 | Generation Licence No. DGL/48/2017 - Licence Application No. LAN-48 - MEPCO Head Quarters, Khanewal Road, Multan
2 | 2017-03-28 | 2020-03-27 | Generation Licence No. DGL/76/2017 - Licence Application No. LAN-76 - Mr. Khawaja M. Younus, Multan
3 | 2017-04-04 | 2020-04-03 | Generation Licence No. DGL/83/2017 - Licence Application No. LAN-83 Mr. Malik Noor Asghar Bucha, Multan
4 | 2017-04-04 | 2020-04-03 | Generation Licence No. DGL/79/2017 - Licence Application No. LAN-79 - Mr. Khawaja M. Ilyas, Masood Spinning Mills, Kabirwala
5 | 2017-04-04 | 2020-04-03 | Generation Licence No. DGL/77/2017 - Licence Application No. LAN-77 - Mr. Khawaja M. Younus, Mahmood Textile Mills, Multan
6 | 2017-04-04 | 2020-04-03 | Generation Licence No. DGL/80/2017 - Licence Application No. LAN-80 - Mr. Asif Iqbal, Sahiwal
7 | 2017-04-13 | 2020-04-12 | Generation Licence No. DGL/78/2017 - Licence Application No. LAN-78 - Mr. Khawaja Muhammad Younus, Multan
8 | 2017-05-17 | 2020-05-16 | Generation Licence No. DGL/74/2017 - Licence Application No. LAN-74 - Zila Council, Iqbal Road, Sahiwal
9 | 2017-05-22 | 2020-05-21 | Generation Licence No. DGL/75/2017 - Licence Application No. LAN-75 - Office of the Deputy Commissioner, Lodhran
10 | 2017-06-13 | 2020-06-12 | Generation Licence No. DGL/107/2017 - Licence Application No. LAN-107 - Mrs. Sajida Khalid, Multan
11 | 2017-07-10 | 2020-07-09 | Generation Licence No. DGL/106/2017 Licence Application No. LAN-106 Unilever Khanewal Tea Factory, Khanewal
12 | 2017-07-12 | 2020-07-11 | Generation Licence No. DGL/128/2017 Licence Application No. LAN-128 Mr. Naimat Ullah Qureshi, Multan
13 | 2017-07-12 | 2020-07-11 | Generation Licence No. DGL/117/2017 Licence Application No. LAN-117 Mr. Muhammad Arshad Nadeem, Multan
14 | 2018-04-16 | 2025-04-15 | Generation Licence No. DGL/343/2018 Licence Application No. LAN-343 Allied Engineering & Services, Multan
15 | 2018-04-16 | 2025-04-15 | Generation Licence No. DGL/348/2018 Licence Application No. LAN-348 Mr. Amir Owais Ghauri, Bahawalpur
16 | 2018-04-20 | 2025-04-19 | Generation Licence No. DGL/349/2018 Licence Application No. LAN-349 Fazal Cloth Mills Limited, Multan
17 | 2018-04-24 | 2025-04-23 | Generation Licence No. DGL/358/2018 Licence Application No. LAN-358 Mr. Hameed Raza, Multan
18 | 2018-07-06 | 2025-07-05 | Generation Licence No. DGL/463/2018 Licence Application No. LAN-463 Mr. Mushtaq Ahmad Laghari Village Rahimabad Tehsil Sadiqabad
19 | 2018-07-12 | 2025-07-11 | Generation Licence No. DGL/478/2018 - Licence Application No. LAN-478 - Mr. Shabbir Ahmad, Eastern Products (Private) Limited, MEPCO
20 | 2018-08-16 | 2025-08-15 | Generation Licence No. DGL/526/2018 - Licence Application No. LAN-526 - Ms. Fatima Jafar, MEPCO
21 | 2018-09-03 | 2025-09-02 | Generation Licence No. DGL/561/2018 - Licence Application No. LAN-561 -Mr. Muhammad Hussain Tahir, MEPCO
22 | 2018-09-25 | 2025-09-24 | Generation Licence No. DGL/608/2018 - Licence Application No. LAN-608 - Ms. Sobia Akram, MEPCO
23 | 2018-09-25 | 2025-09-24 | Generation Licence No. DGL/620/2018 - Licence Application No. LAN-620 - Mr. Muhammad Sarwar, MEPCO