## abstract
Progress of Net Metering (Dated: 15-08-2018)
Description | Detail | Capacity (KW) | Remarks | Formulas
No. of Applications Received | 22 | 1074.14 | - | 1074.14
Genereation licences applied to NEPRA | 22 | 1074.14 | -
Genereation licences issued by NEPRA | 19 | 1038.08 | - | 1038.08
Genereation licences pending at NEPRA | 3 | 36.06 | Applied To NEPRA on 19-07-2018 & 09-08-2018 | 36.06
No. of Connections Installed | 15 | 693.12 | Billing of 15 Connections is Started.
Applications Under Process | 4 | 344.96 | Demand Notice of bidirectional meters of 4 connections are issued to consumers | 344.96

## circle wise abstract
MEPCO Circlewise Progress of Net Metering (Dated:15-08-2018) on Roshan Pakistan App
Circles Names | Circles Codes | Total Sanctioned/ Connected Load (KW) | Total required load for Net Metering (KW) | Generation (KW) | Total Applications | Billing Started | Applied to NEPRA | Total connections |  | Remarks
[8 empty] | Installed | Remaining
Multan | 15100 | 1315 | 277.52 | 242.5 | 12 | 8 | 2 | 8 | 4 | 2#DN ISSUED FOR BIDIRECTIONAL NET METERS. 2# applied to NEPRA on 19-07-2018 & 15-08-2018.
Bahawalpur | 15400 | 16 | 8 | 8 | 2 | 2 | 0 | 2 | 0 | -
Sahiwal | 15500 | 12 | 7.62 | 7.62 | 2 | 2 | 0 | 2 | 0 | -
Rahim Yar Khan | 15600 | 12 | 12 | 0 | 1 | 0 | 0 | 0 | 1 | DN for Net Meter Issued to Consumer.
Bahawal Nagar | 15800 | 642 | 334 | 0 | 2 | 0 | 1 | 0 | 2 | 1# Connection is under Process. 2nd Connection applied to NEPRA on 09-08-2018
Khanewal | 15900 | 5508 | 435 | 435 | 3 | 3 | 0 | 3 | 0 | -
Total |  | 7505 | 1074.14 | 693.12 | 22 | 15 | 3 | 15 | 7 | Net Connections in Progress=7

## tariff wise abstract
Progress of Net Metering Tariff wise Abstract (Dated: 15-08-2018)
Sr. No. | Type | Tariff | No. Of Connections | Meters Installed | Under Process
1 | Domestic | A-1a(01) | 3 | 0 | 2 connection DN issued. 1 Connection applied to NEPRA for DG License on 15-08-2018.
|  | A-1b(03)T | 9 | 8 | 8 Connections Installed & Billing started. 1 Connection applied to NEPRA for DG License on 19-07-2018.
2 | Commercial | A-2a(04) | 1 | 1 | Connection Installed. Billing started.
|  | A-2c(06)T | 5 | 4 | 4 meters installed (Billing of 4 connections started). 1# connection applied to NEPRA for DG License on 09-08-2018
3 | Industrial | B2b(12)T | 2 | 0 | 1 connection Demand Notice issued. 2nd connection DG License issued on 12/07/2018 & under Process.
|  | B3(14)T | 2 | 2 | Connection Installed. Billing started.
|  | Total | 22 | 15