## pitc file
NET METERING APPLICATION(S) INFORMATION/STATUS
| COMPANY NAME: MEPCO | [16 empty] | As on 10-01-2020
Sr. No | Application No. | Name of Applicant | Sub Division Code | Tariff | Application Date | Reference No. | Sanctioned Load | Required Load for Net Metering | Name of Installer | Applied To NEPRA (Yes or No) | Generation Licence | Feeder | Installation Status (Installed or Uninstalled) | Installation Date | Billing Started (Yes or No) | Billing Start Date | Generation (KW) | Remarks | Current Position (What is Present Status i.e. either with installer or SDO or NEPRA etc.)
1 | 1 | OFFICE BUILDING TEHSILDAR LODHRAN NEAR MARKET COMMITTEE OFFICE LODHRAN COMMISSIONER LODHRAN | 15421 | A-1b(03)T | 2016-06-18 | New 15154210167800 Old 03154210167800 | 11 | 3 | M/S Creative Electronics | Yes | DGL/75/2017 | CITY LODHRAN | Installed | 2018-01-06 | YES | 2018-01-10 | 3 | Connection Installed. Billing Started | -
2 | 2 | XEN CIVIL MEPCO | 15173 | A-3(66) | 2016-07-12 | 13151734972100 | 12 | 3 | Reap | Yes | DGL/48/2017 | WAPDA COLONY | Installed | 2016-07-28 | YES | 2016-08-23 | 3 | Connection Installed. Billing Started | -
3 | 3 | KHALID NAZEER CMISSIONER SAHIWAL ZILA COUNCIL SAIWAL. Director Local Government and Community Development, Commissioner Office, Sahiwal. Ph # 0300-6956755 | 15512 | A-3(66) | 2016-08-12 | 12155121038000 | 7 | 3 | M/S Creative Electronics | Yes | DGL/74/2017 | CIVIL LINES | Installed | 2018-05-10 | YES | 2018-06-20 | 3 | Connection Installed. Billing Started | -
4 | 5 | Asif Iqbal SM Bashir Agencies | 15514 | A-2c(06)T | 2016-12-15 | New 28155140275502 and old 03155140275502 | 5 | 4.62 | Royal Energy Sultan Electronics | Yes | DGL/80/2017 | COLLEGE ROAD | Installed | 2018-01-18 | YES | 2018-02-12 | 4.62 | Connection Installed. Billing Started | -
5 | 6 | MUHAMMAD ARSHAD NADEEM S-O MHAMMAD ASHIQ ST NO 1 MADINA ABAD CLY MTN MULTAN | 15132 | A-1b(03)T | 2017-01-06 | 13151322030405 | 5 | 10 | Solar Tech. | Yes | DGL/117/2017 | TIMBER MARKT | Installed | 2017-12-17 | YES | 2017-12-21 | 10 | Connection Installed. Billing Started | -
6 | 7 | SAJIDA KHALID W/O CH.KHALID LATIF PUNJAB SMALL INDUSTRIES MTN (Jahanzaib) | 15175 | A-1b(03)T | 2017-01-26 | 17151753136101 | 5 | 10 | Pak Friends Enterprises | Yes | DGL/107/2017 | DARBAR PEER AKBAR SHAH | Installed | 2017-12-19 | YES | 2017-12-20 | 10 | Connection Installed. Billing Started | -
7 | 8 | UNILEVER PAKISTAN LIMITED TEA FACTORY CHAK NO.88-A10R KHANEWAL. Mr. Danish Mukhtar The Works Manager. | 15913 | B3(14)T | 2017-02-08 | New 30159132372500 Old 27159132372500 | 503 | 110 | Reon | Yes | DGL/106/2017 | UNILEVER TEA FACTORY | Installed | 2018-01-16 | YES | 2018-01-16 | 110 | Connection Installed. Billing Started | Export stopped due to main panel burnt. System will be restored soon.
9 | 10 | KH MUHAMMAD YOUNIS S-O MUHAMMAD MASOOD 13 B OFFICER CLY MULTAN | 15172 | A-1b(03)T | 2017-03-03 | 18151723474200 | 12 | 32 | Preimer Energy (Pvt) Ltd. | Yes | DGL/78/2017 | EID GAH ROAD | Installed | 2017-12-19 | YES | 2017-12-27 | 32 | Connection Installed. Billing Started | -
10 | 11 | MEHMOOD TEXTILE MILLS LTD MULTAN LOHARI GATE MULTAN CITY | 15113 | A-2c(06)T | 2017-03-03 | 27151130721400 | 200 | 64 | Preimer Energy (Pvt) Ltd. | Yes | DGL/77/2017 | ABDALI ROAD | Installed | 2018-01-29 | YES | 2018-02-03 | 64 | Connection Installed. Billing Started | -
11 | 12 | Kh. M. Ilyas M/S MASOOD SPINNING MILLS UNIT NO.02 04-KM MULTAN ROAD KABIR WALA | 15921 | B3(14)T | 2017-03-03 | 30159212533901 | 4999 | 320 | Preimer Energy (Pvt) Ltd. | Yes | DGL/79/2017 | MASOOD SPINNING UNIT-2 | Installed | 2018-02-01 | YES | 2018-02-03 | 320 | Connection Installed. Billing Started | -
12 | 13 | SHABBIR AHMAD S-O MIRAJ DIN EASTREN PRODUCTS-VITAL TEA LTD QAZI WALA HAROON ABAD (Haseeb) | 15821 | B2b(12)T | 2017-12-26 | 27158210966702 | 482 | 304 | REON | Yes | DGL/478/2018 | KHATAN | Installed | 2018-10-26 | YES | 2019-01-03 | 304 | Connection Installed. Billing Started | M&T checked thenstalled creative meter on 04/09/2019 and found date and Time upset and meter running 33% slow and detection was charged from the consumer. Meter was replaced with Micro tech meter. .
13 | 14 | NAIMAT ULLAH S.O ALLAH BACHAYA QURESHI 259-N WAPDA TOWN-11 MTN | 15175 | A-1b(03)T | 2017-06-01 | 17151753132415 | 5 | 10 | SOLAR MASTER | Yes | DGL/128/2017 | WAPDA TOWN | Installed | 2017-12-19 | YES | 2017-12-20 | 10 | Connection Installed. Billing Started | -
14 | 15 | NASEEM AHMAD/ FAZAL CLOTH MILLS 59/3 ABDALI ROAD MULTAN | 15117 | A-2c(06)T | 2018-02-19 | 27151170144100 | 145 | 88 | Preimer Energy (Pvt) Ltd. | Yes | DGL/349/2018 | HASSAN PARWANA | Installed | 2018-05-15 | YES | 2018-06-01 | 88 | Connection Installed. Billing Started | -
15 | 16 | ALLIED ENGINEERING & SERVICES HAMID PUR KANORA SHER SHAH BY PASS MTN | 15138 | B2b(12)T | 2018-03-09 | 27151380994405 | 60 | 23.76 | AYK (Pvt) Ltd. | Yes | DGL/343/2018 | BASTI BALAIL | Installed | 2018-10-18 | YES | 2019-01-03 | 23.76 | Connection Installed. Billing Started | -
16 | 17 | AMIR AWAIS GHAURI BX-586/1 SADIQ COLONY BAHAWAL PUR | 15441 | A-2c(06)T | 2018-03-12 | 17154410396400 | 5 | 5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/348/2018 | N.MAHAL(CANTT) | Installed | 2018-05-15 | YES | 2018-06-16 | 5 | Connection Installed. Billing Started | -
17 | 18 | HAMEED RAZA S/O AMEER UD DIN AT HOUSE #2 HAMZA STREET BOSAN ROAD MULTAN | 15171 | A-1b(03)T | 2018-04-03 | 13151717096201 | 6 | 5.2 | Preimer Energy (Pvt) Ltd. | Yes | DGL/358/2018 | SABZA ZAR | Installed | 2018-08-29 | YES | 2018-09-24 | 5.2 | Connection Installed. Billing Started | -
18 | 19 | MUSHTAQ AHAMAD LAGHARI S-O MUHAMAMD AKBAR LAGHARI VILLAGE RAHIM ABAD SADIQABAD | 15645 | A-1b(03)T | 2018-04-13 | New 28156451202700 and Old 05156451202700 | 12 | 12 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/463/2018 | RAHIM ABAD | Installed | 2018-09-14 | YES | 2018-10-15 | 12 | Connection Installed. Billing Started | -
19 | 20 | FATIMA JAFAR W-O MUHAMMAD JAFAR CHOUDHARY, HOUSE NO. 383-C BUCH VILLAS MULTAN | 15175 | A-1b(03)T | 2018-07-10 | 15151758880903 | 5 | 3.06 | Preimer Energy (Pvt) Ltd. | Yes | DGL/526/2018 | BUTCH VILLAS | Installed | 2019-05-10 | NO | - | 3.06 | Connection Installed on 10/05/2019. | Billing not started from 05/2019 to 11/2019. Billing will start in 12/2019. Informed to SDO, XEN & SE in 08, 09 and 10/2019 and 11/2019.
20 | 21 | MUHAMMAD HUSSAIN TAHIR S-O MUKHTIAR AHMAD, TAHIR MEDICAL COMPLEX, 73-R BANGLOW ROAD HAROONABAD | 15821 | A-2c(06)T | 2018-01-30 | 27158210754604 | 160 | 30 | M/S Creative Electronics | Yes | DGL/561/2018 | BANGALOW ROAD | Installed | 2019-02-01 | YES | 2019-03-04 | 30 | Connection Installed. Billing Started | Site was checked by M&T on 31/07/2019 and accuracy found Ok.
21 | 22 | ALI SHAH S/O MUREED HUSSAIN SHAH MOHALLAH LAL SHAH MAKHDOOM RASHID MULTAN | 15127 | A-1b(03)T | 2017-07-14 | 17151271746812 | 5 | 3.97 | POWER PROJECTS ORGNAIZATION | Yes | DGL/768/2018 | MAKHDOOM RASHID CITY | Installed | 2019-01-28 | YES | 2019-04-27 | 3.97 | Connection Installed. Billing Started | -
22 | 23 | Ms. SOBIA AKRAM W/O MUHAMMAD AKRAM CHAK No. 131/10 R JAHANIAN | 15915 | A-2c(06)T | 2018-08-31 | New 28159152947315 Old 20159152947315 | 5 | 5.12 | Preimer Energy (Pvt) Ltd. | Yes | DGL/608/2018 | PIR SAQDIQ SHAH | Installed | 2018-11-01 | YES | 2018-12-03 | 5.12 | Connection Installed. Billing Started | -
23 | 24 | MUHAMMAD SARWAR S/O ABDUL MAJEED PUNJAB DEGREE COLLEGE AZIM ABAD BUREWALA | 15333 | A-3(A) (66) | 2018-08-16 | 27153332500302 | 200 | 192 | Preimer Energy (Pvt) Ltd. | Yes | DGL/620/2018 | CITY-3 | Installed | 2018-10-08 | YES | 2018-11-06 | 192 | Connection Installed. Billing Started | Meter was rechecked by M&T on 24/10/2019 and 15/11/2019 and found within permissible Limits.
24 | 25 | AZEEM AKRAM S/O MUHAMMAD AKRAM SUPERIOR COLLEGE VEHARI ROAD HASIL PUR | 15452 | A-1b(03)T | 2018-09-28 | NEW 28154520023600 OLD 28154520120216 | 13 | 19.44 | Preimer Energy (Pvt) Ltd. | Yes | DGL/691/2018 | VEHARI ROAD | Installed | 2019-02-21 | YES | 2019-03-13 | 19.44 | Connection Installed. Billing Started | Letter sent to XEN for Checking of meters as opened message appeared on screen on 11/11/2019. MCO posted and meter replaced in 11/2019 billing.
25 | 26 | MUHAMMAD JUNAID MASOOD HOUSE #66-M, WAPDA TOWN PHASE II MULTAN | 15175 | A-1b(03)T | 2018-10-07 | 17151753124630 | 5 | 7.15 | Sky Electric (PVT) Limited | Yes | DGL/1134/2018 | WAPDA TOWN | Installed | 2019-04-04 | NO | - | 7.15 | Connection Installed on 04/04/2019. | Billing not started in 05 to 11/ 2019. Billing will start in 12/2019. informed to SDO, XEN, SE in 08 to 11/2019. Informed to SE Multan via email and focal person for billing.
26 | 27 | SAIF ALI S/O CHOUDHARY SARDAR MUHAMMAD CHAK #106/DB YAZMAN, BAHAWALPUR | 15416 | A-1b(03)T | 2018-10-10 | 08154160646004 | 4.5 | 5.2 | Preimer Energy (Pvt) Ltd. | Yes | DGL/818/2018 | TAILWALA | Installed | 2019-03-06 | YES | 2019-06-17 | 5.2 | Connection Installed. Billing Started. | -
27 | 28 | MEHMOOD AHMAD SHEIKH S-O MUHAMMAD AHMAD SHEIKH NEAR REST HOUSE BAHAWALPUR | 15443 | A-1b(03)T | 2018-09-15 | NEW 04154430970800 OLD 18154430970800 | 6 | 10.24 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/732/2018 | GHANI PUR | Installed | 2019-02-25 | YES | 2019-04-12 | 10.24 | Connection Installed. Billing Started. | -
28 | 29 | MUHAMMAD KHALID ALVI S/O MUHAMMAD SHARIF ALVI 43-A GULGASHT COLONY MULTAN | 15171 | A-1b(03)T | 2018-10-01 | 04151715528700 | 5 | 5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/769/2018 | USMAN ABAD | Installed | 2019-01-18 | YES | 2019-02-13 | 5 | Connection Installed. Billing Started | -
29 | 30 | SAMINA MUJAHID W/O MUJAHID ALI AT 98-B BUCH VILLAS MULTAN | 15175 | A-1b(03)T | 2018-11-09 | 15151758884003 | 5 | 4.96 | Read Solar (PVT) Limited | Yes | DGL/819/2018 | BUTCH VILLAS | Installed | 2019-02-28 | YES | 2019-05-25 | 4.96 | Connection Installed. Billing Started | -
30 | 33 | SHAZIA ZUBAIR W-O ZUBAIR BILAL AT 12-E,OFFICERS COLONY MULTAN | 15172 | A-1b(03)T | 2018-10-29 | 18151723471501 | 5 | 7.4 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/1052/2019 | SHAMAS ABAD | Installed | 2019-05-03 | YES | 2019-05-29 | 7.4 | Connection Installed. Billing Started. | -
31 | 35 | MALIK MUHAMMAD IBRAHEEM S-O WAHID BUX AT H#1341 BM WAHID ABAD COLONY OLD SHUJA ABAD ROAD MULTAN | 15132 | A-1b(03)T | 2018-10-24 | 03151322240300 | 13 | 18.36 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/837/2018 | OLD SHUJAABAD ROAD | Installed | 2019-03-25 | YES | 2019-06-13 | 18.36 | Connection Installed. Billing Started. | -
32 | 36 | AHMAD RAZA SHIRAZI S-O IMTIAZ HUSSAIN SHIRAZ, SHERAZI DERA MOZA KHAIR SHAH SAHIWAL | 15512 | A-1b(03)T | 2018-11-04 | 19155121582101 | 5 | 4.87 | Sky Electric (PVT) Limited | Yes | DGL/880/2019 | QUTAB SHAHANA | Installed | 2019-05-16 | YES | 2019-05-30 | 4.87 | Connection Installed. Billing Started. | -
33 | 37 | MUHAMMAD KHAN S.O FAIZ ULLAH KHAN 55-A-3 ALTAF TOWN Multan | 15111 | A-1b(03)T | 2018-12-06 | 13151110928700 | 5 | 7.14 | Sky Electric (PVT) Limited | Yes | DGL/913/2019 | ALLAMA IQBAL | Installed | 2019-02-28 | YES | 2019-06-26 | 7.14 | Connection Installed. Billing Started. | -
34 | 38 | DR SHER MUHAMMAD AWAN CHAH QASIM WALA LODHRAN | 15421 | A-1b(03)T | 2018-12-06 | New16154210217400 Old 04154210217400 | 5 | 7.28 | Sky Electric (PVT) Limited | Yes | DGL/912/2019 | CITY LODHRAN | Installed | 2019-02-19 | YES | 2019-04-26 | 7.28 | Connection Installed. Billing Started | -
35 | 31 | MALIK NOOR ASGHAR BUCHA S/O MALIK NOOR MUHAMMAD BUCHA MAIN OFFICE BUILDING BUCH VILLAS BOSAN ROAD MULTAN | 15175 | A-2c(06)T | 2018-11-13 | 28151758887100 | 19 | 26.07 | Orient Energies (Pvt) Ltd. | Yes | DGL/911/2019 | BUTCH VILLAS | Installed | 2019-05-21 | YES | 2019-07-13 | 26.07 | Connection Installed. Billing Started | Net Meters Installed on 21/05/2019. BILLING STARTED IN 07/2019.
36 | 34 | SHAHID SARWAR CONTROL SHED CHAK # 69/12-L BUREWALA | 15331 | B2b(12)T | 2018-11-09 | 27153311095701 | 78 | 50.02 | Tesla Industries (Pvt) Limited. | Yes | DGL/910/2019 | 67/12L(SULTAN S.DIN) | Installed | 2019-06-25 | YES | 2019-08-03 | 50.02 | Connection Installed on 25/06/2019 Billing Started on 02/08/2019. | Generation License Issued by NEPRA on 23/01/2019. Meter was rechecked by M&T 1st on 24/10/2019 and found Ok.
37 | 32 | Mr. RIZWAN GHAFOOR 1284-R WAPDA TOWN PHASE -II MULTAN | 15175 | A-1b(03)T | 2018-11-12 | 17151753121112 | 10 | 10.07 | HISEL POWER PAKISTAN (Pvt) LIMITED | Yes | DGL/914/2019 | WAPDA TOWN | Installed | 2019-02-26 | YES | 2019-04-27 | 10.07 | Connection Installed. Billing Started. | -
38 | 39 | MUHAMMAD MUNEER ANJUM S/O GHULAM QADIR KHAN. HOUSE# 1408 BLOCK-S NORTHERN BYPASS ROAD WAPDA TOWN PHASE-II MULTAN | 15175 | A-1b(03)T | 2018-09-01 | 17151753129100 | 5 | 4.96 | Read Solar (PVT) Limited | Yes | DGL/947/2019 | WAPDA TOWN | Installed | 2019-04-15 | NO | - | 4.96 | Net Meters Installed on 15/04/2019 | Billing not started in 05/2019 to 11/2019. Inform to SDO, XEN, SE in 08, 09, 10 and 11/2019. Informed to SE Multan via email and focal person for billing.
39 | 40 | RIZWANA NAHEED W-O MIAN NAZEER AHMAD HOUSE# 1438BI TALEERI GARDEN ROAD VILLA LALA ZAR MUZAFFARGARH | 15711 | A-1b(03)T | 2018-12-04 | 18157111255900 | 5 | 7.5 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/976/2019 | T.P.S | Installed | 2019-06-11 | YES | 2019-06-27 | 7.5 | Connection Installed. Billing Started | Connection Installed. Billing Started
40 | 41 | ABDUL SAMMAD S-O MALIK FAZIL MUHAMMAD SHAD, (DISTRIBUTED GENERATOR), AT SADIQABAD #2 MULTAN | 15118 | A-1b(03)T | 2018-10-20 | 12151180980204 | 5 | 3.25 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/1029/2019 | NEW FAROOQ PURA | Installed | 2019-06-12 | YES | 2019-09-20 | 3.25 | Connection Installed. Billing Started | Net Meters Installed on 12/06/2019. Billing started in 09/2019.
41 | 42 | MUHAMMAD SARWAR S-O MIAN ABDUL MAJEED C/O GHAZALI EDUCATIONAL 441-EB CANAL GARDEN HOUSE #368-369 BUREWALA | 15333 | A-1b(03)T | 2018-12-26 | 05153330482845 | 5 | 6.5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/1060/2019 | CITY-3 | Installed | 2019-04-03 | YES | 2019-05-15 | 6.5 | Connection Installed. Billing Started. | -
42 | 43 | Dr. OZAIR AHMAD RAFIQ S-O MUHAMMAD RAFIQ MIAN 441-EB CANAL GARDEN HOUSE #370-371 BUREWALA | 15333 | A-1b(03)T | 2018-12-26 | 05153330482858 | 5 | 5.85 | Preimer Energy (Pvt) Ltd. | Yes | DGL/1059/2019 | CITY-3 | Installed | 2019-04-03 | YES | 2019-05-15 | 5.85 | Connection Installed. Billing Started. | -
43 | 44 | MUHAMMAD SALEEM QURESHI S-O MUHAMMAD NASEEB QURESHI HOUSE# 7-8 ABDALI COLONY MULTAN | 15117 | A-1b(03)T | 2018-12-06 | 28151170084802 | 19 | 8 | Sky Electric (PVT) Limited | Yes | DGL/1083/2019 | HASSAN PARWANA | Installed | 2019-05-27 | YES | 2019-07-13 | 8 | Connection Installed. Billing Started. | Net Meters Installed on 27/05/2019. Billing started in 07/2019
44 | 45 | MUSARAT ULLAH QURESHI S-O ALLAH BACHAYA QURESHI POST OFFICE HARRAND BASTI PANAH ALI JAMPUR RAJANPUR | 15247 | A-1b(03)T | 2018-10-17 | New 10152471123102 OLD 20152451123102 | 5 | 4.94 | Read Solar (PVT) Limited | Yes | DGL/1084/2019 | HARAND | Installed | 2019-06-22 | NO | - | 4.94 | Net Meters Installed on 22/06/2019 | DGL Issued on 07/03/2019. billing not started in 07, 08 , 09,10 and 11/2019. Billing will start in 12/2019. Informed to SE DG Khan by Dir (Mkt, Trf &CM) on telephone on 27/09/2019 at 1045hrs. Informed to xen by sdo net met in 11/2019 but not billed again. MCO Posted but Net Met Information not posted in 12/2019 Billing.
45 | 46 | TAHIRA HASSAN NAWAZ W-O RAI HASSAN NAWAZ KHAN AT NESTLE MILK CHILLER CHAK # 110-12-L CHICHAWATNI | 15544 | B2b(12)T | 2018-12-21 | 27155442161111 | 38 | 7.28 | Sky Electric (PVT) Limited | Yes | DGL/1099/2019 | KASSOWAL | Installed | 2019-10-22 | YES | 2019-11-04 | 7.28 | Generation License Issued by NEPRA on 14/03/2019 | Net meters Installed on 21/10/2019. Billing started in 10/2019 Billing cycle.
46 | 47 | FAISAL SALMAN SHEIKH S-O MUHAMMAD AKRAM SHEIKH. SH DIN MUHAMMAD TRUST HOSPITAL 321-EB BUREWALA | 15335 | A-1b(03)T | 2018-12-26 | 11153351601400 | 6 | 8.45 | Sky Electric (PVT) Limited | Yes | DGL/1107/2019 | SARWAR SHAH | Installed | 2019-06-16 | YES | 2019-07-20 | 8.45 | Connection Installed. Billing Started. | Net Meters Installed on 16/06/2019. Billing started in 07/2019
47 | 49 | SHAISTA FAROOQ W-O KHAWAJA FAROOQ AHMAD AT 1415-R WAPDA TOWN PHASE-II MULTAN | 15175 | A-1b(03)T | 2019-01-21 | 17151753119905 | 5 | 7.15 | Read Solar (PVT) Limited | Yes | DGL/1141/2019 | WAPDA TOWN | Installed | 2019-03-20 | YES | 2019-04-27 | 7.15 | Connection Installed. Billing Started. | -
48 | 50 | M/S ASKARI CNG FILLING STATION NEAR TOLE #10 KLP ROAD SADIQABAD | 15641 | A-2c(06)T | 2019-01-24 | 27156410003201 | 134 | 8.96 | Solar Sigma Pvt Limited. | Yes | DGL/1186/2019 | MANTHAR | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 10/04/2019 | Under Process for Installation of Net Meters
49 | 4 | MLK NOOR ASGHAR BUCHA S/O MLK NOOR MUHAMMAD BUCHA THE GRAND COMMERCIAL BUILDING BUCH VILLAS H/S BOSAN ROAD MTN | 15175 | A-2c(06)T | 2018-11-13 | 27151758887001 | 857 | 114.37 | Orient Energies (Pvt) Ltd. | Yes | DGL/83-I/2019 | BUTCH VILLAS | Installed | 2018-01-17 | YES | 2018-03-01 | 114.37 | Connection Installed. Billing Started. | -
50 | 51 | FAHAD KHALIL S-O PEERZADA KHALIL AHMED (C-O AHMAD RIZWAN SARFRAZ) CITY SCHOOL CAMPUS BAHAWALPUR | 15441 | A-3(A) (66) | 2019-02-28 | 27154410848302 | 158 | 46.2 | Solis Energy solutions (Pvt), Ltd. | Yes | DGL/1220/2019 | HOOT WALA | Installed | 2019-06-28 | YES | 2019-08-03 | 46.2 | Connection Installed. Billing Started. | Generation License Issued by NEPRA on 06/05/2019 & Net meters installed on 28/06/2019. Billing started on 03/08/2019.
51 | 48 | DR. SOHAIL MEHMOOD CH. S-O MUHAMMAD SADIQ MUSHTAQ 139-A HASHMI GARDEN BAHAWALPUR | 15441 | A-1b(03)T | 2018-12-21 | 20154413017500 | 7 | 10.24 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/1238/2019 | HASHMI GARDEN | Installed | 2019-05-23 | YES | 2019-07-31 | 10.24 | Connection Installed. Billing started in 07/2019. | -
52 | 52 | SAFIA FAROGH W-O FAROGH JALIL QUERSHI, HOUSE #6 A-2, MUHAMMAD HUSSAIN ROAD, MODEL TOWN -A BAHAWALPUR | 15441 | A-1b(03)T | 2019-02-28 | 14154410057700 | 5 | 7.5 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/1278/2019 | NLC | Installed | 2019-05-21 | YES | 2019-06-22 | 7.5 | Connection Installed. Billing Started | -
53 | 53 | C/O AURENGZAIB FEROZ S/O IFTIKHAR FEROZ (C/O AHMAD RIZWAN SARFRAZ) AT M/S CITY SCHOOL NEAR DILWAR COLLEGE NORTHERN BYPASS MULTAN | 15173 | A-3(A) (66) | 2019-02-25 | 27151730365512 | 68 | 46.2 | Solis Energy solutions (Pvt), Ltd. | Yes | DGL/1382/2019 | DAHER | Installed | 2019-07-16 | YES | 2019-08-03 | 46.2 | Connection Installed. Billing will started. | Generation License Issued by NEPRA on 28/05/2019. Billing started in 07/2019. Export units posted in 09/2019 billing.
54 | 55 | Mr. HAIDER AHSAN S-O AHSAN ZAHOOR HOUSE# 1052-7, AL- MUSTAFA COLONY LMQ ROAD MULTAN | 15171 | A-1b(03)T | 2019-04-09 | 01151715041800 | 6 | 8.91 | Masco Energy Services (Pvt) Limited 17-Km Multan Road Lahore. | Yes | DGL/1387/2019 | GULGASHT COLONY | Installed | 2019-06-22 | YES | 2019-07-10 | 8.91 | Net Meters Installed on 22/06/2019 | Change of name pending.
55 | 56 | AWAIS SHAFIQ S-O MUHAMMAD SHAFIQ HABIB PLAZA GT ROAD SAHIWAL RESIDENT OF H#359 BLOCK H STREET #3DHA LAHORE PHASE-VI | 15513 | A-2c(06)T | 2019-02-04 | 28155130407201 | 5 | 7.28 | Sky Electric (PVT) Limited | Yes | DGL/1383/2019 | LAHORE ROAD | Installed | 2019-10-07 | NO | - | 7.28 | Net meters installed on 07/10/2019 | Generation License Issued by NEPRA on 29/05/2019. Billing not started in 11/2019 and 12/2019. Billing will start in 01/2020. MCO not Posted and Net Met information not posted.
56 | 57 | MALIK MUHAMMAD IBRAHEEM S-O WAHID BUX AT SHANGRILLA HOTEL SADAR BAZAR MULTAN CANTT. | 15111 | A-2c(06)T | 2019-01-16 | 27151111824400 | 155 | 30.24 | Read Solar (PVT) Limited | Yes | DGL/1356/2019 | QUAID-I-AZAM ROAD | Installed | 2019-08-25 | YES | 2019-11-04 | 30.24 | Net Meters Installed on 25/08/2019. MCO Posted. Billing Started in 10/2019 billing. | Generation License Issued By Nepra On 07/05/2019. Billing Will Start In 10/2019. Mco Not Feeded And Billed In 08 And 09/2019. Display Washed Out And Checked By M&T 1st On 06/09/2019 And 26/09/2019 And Backup Meter Installed. Meter Replaced In 10/2019. Mco Posted But Export And Import Readings Are Not Posted In 10/2019 And 11/2019 Billing. Meters Replaced.
57 | 58 | MR. MUHAMMAD AMJAD S-O GHULAM RASOOL AT 437-EB MODEL TOWN BUREWALA | 15334 | A-1b(03)T | 2019-04-11 | 01153340075309 | 5 | 7.26 | M/s Power Highway | Yes | DGL/1384/2019 | CITY -II | Installed | 2019-06-10 | YES | 2019-07-10 | 7.26 | Net Meters Installed on 10/06/2019 | -
58 | 59 | Ms. RAHEELA BANO W-O KHAWAJA ATIQ UR REHMAN AT HOUSE #729-J SHAH RUKN E ALAM COLONY MULTAN | 15194 | A-1b(03)T | 2019-04-11 | 19151941032800 | 5 | 7.36 | Feston EngIneering Works Multan | Yes | DGL/1365/2019 | GULBERG CLNY | Installed | 2019-05-21 | YES | 2019-09-30 | 7.36 | Net Meters Installed on 21/05/2019 | MCO not feeded in billing of 05/2019. Billing not started in 06/2019 due incomplete posting of MCO for Net Meters and not in 07/2019. Billing started in 09/2019 export readings not posted. Readings posted in 10/2019. but peak units are in credit. Informed to sdo on phone on 06/11/2019. Billing revised in 11/2019. MCO and export posted. Defective meter replaced.
59 | 60 | M/S ASKARIA CNG C/O IMRAN AHMAD S-O IQBAL AHMED NEAR AZIZ HOTEL CHOWK MULTAN | 15132 | A-2c(06)T | 2019-01-15 | 27151320319501 | 117 | 8.96 | Solar Sigma Pvt Limited. | Yes | DGL/1490/2019 | WILLAYAT ABAD | Not Installed | - | - | - | - | Applied to NEPRA on 30/04/2019 and DGL issued on 14/06/2019. | Under Process for Installation of Net Meters. DN issued by XEN and Paid by Consumer on 15/11/2019. Material request is sent to SE Multan for approval on 19/11/2019 by XEN City Multan.
60 | 61 | Dr. MUHAMMAD ISMAIL BASHIR S-O BASHIR AHMAD AT NEW AL-SHIFA HOSPITAL, 42-B1, NUSRAT SHAHEED ROAD MUMTAZABAD MULTAN | 15121 | A-2c(06)T | 2019-04-27 | 31151211535300 | 5 | 5.88 | Feston EngIneering Works Multan | Yes | DGL/1489/2019 | GHEE MILL | Installed | 2019-07-04 | YES | 2019-07-10 | 5.88 | Connection Installed. Billing Started | -
61 | 62 | Mr. ATTAULLAH WAHALA S-O REHMAT ALI HOUSE#160-AHASHMI GARDEN BAHAWALPUR | 15441 | A-1b(03)T | 2019-04-01 | 20154412971800 | 4 | 5.76 | MAXELL POWER Pvt. Limited | Yes | DGL/1502/2019 | HASHMI GARDEN | Installed | 2019-07-04 | YES | 2019-07-31 | 5.76 | Connection Installed. Billing Started | Applied to NEPRA on 07/05/2019 and DGL Issued on 21/06/2019.
62 | 63 | Mr. TANVIR AHMAD S-O ASHIQ ALI C-O PRINCIPAL VOCATIONAL TRAINING INSTITUTE NEAR TTC COLLEGE MULTAN Ph#061-6780096 | 15173 | A-3(A) (66) | 2019-04-03 | 27151736305900 | 35 | 41.6 | M/S HARDON Solar (Pvt), Ltd. | Yes | DGL/2718/2019 | AHMAD FEEDER | Not Installed | - | - | - | - | Applied to NEPRA on 07/05/2019. and DGL issued on 07/11/2019. Under Process for installation of Net Meters. | Demand notice paid in 12/2019. Material reached at site on 08/01/2020.
63 | 65 | Dr. ABDUL SHAKOOR S-O CHOUDHARY MUHAMMAD ALI HOUSE#183-A HASHMI GARDEN BAHAWALPUR | 15441 | A-1b(03)T | 2019-03-18 | 20154413012500 | 6 | 8.71 | MAXELL POWER Pvt. Limited | Yes | DGL/1488/2019 | HASHMI GARDEN | Installed | 2019-07-15 | YES | 2019-07-31 | 8.71 | Connection Installed. Billing Started | Applied to NEPRA on 10/05/2019 AND DGL ISSUED ON 21/06/2019. Net Meters Installed on 05/07/2019
64 | 66 | MR. SHAHID HAMEED CHOHAN HOUSE # 1419 BLOCK# S PHASE-II WAPDA TOWN MULTAN | 15175 | A-1b(03)T | 2019-05-08 | 17151753120316 | 6 | 8.96 | Feston Engineering Works Multan | Yes | DGL/1602/2019 | WAPDA TOWN | Installed | 2019-07-05 | NO | - | 8.96 | Net Meters Installed on 05/07/2019 | Applied to NEPRA on 10/05/2019 and DGL Issued on 27/06/2019. Net Metering Billing will start in 12/2019. New Connection billing started in 08/2019. MCO not posted in 09/2019 & 10/2019 & 11/2019.
65 | 68 | M-S ASKARI CNG FILLING STATION ADDA KHAN PUR RAHIM YAR KHAN | 15611 | A-2c(06)T | 2019-01-22 | 27156110527203 | 134 | 8.96 | Solar Sigma Pvt Limited. | Yes | DGL/1686/2019 | ALLAMA IQBAL | Not Installed | - | - | - | - | APPLIED TO NEPRA ON 23/05/2019 | Under Process for Installation of Net Meters
66 | 69 | AHMAD HASSAN JAVED S-O JAVED ANWAR ABID AT HOUSE # 47-A HASHMI GARDEN BAHAWALPUR | 15441 | A-1b(03)T | 2019-05-13 | 20154413030800 | 6 | 8.71 | MAXELL POWER Pvt. Limited | Yes | DGL/1694/2019 | HASHMI GARDEN | Installed | 2019-07-26 | YES | 2019-07-31 | 8.71 | Connection Installed. Billing Started. | APPLIED TO NEPRA ON 29/05/2019.
67 | 70 | JAVED ANWAR ABID S-O SUBHAN ALI HOUSE # 4 DUBAI MAHAL ROAD BAHAWALPUR | 15441 | A-1b(03)T | 2019-05-13 | 20154413031100 | 6 | 8.71 | MAXELL POWER Pvt. Limited | Yes | DGL/1696/2019 | HASHMI GARDEN | Installed | 2019-07-26 | YES | 2019-10-01 | 8.71 | NET METERS INSTALLED . BILLING STARTED ON 01/10/2019 | APPLIED TO NEPRA ON 29/05/2019. Bill adjustment for 09/2019 is posted in 10/2019 Billing.
68 | 71 | Mr. ABDUL HAQ URF MADNI S/O SHAIKH MUHAMMAD ASLAM AT HOUSE# 521/A BOSAN ROAD MULTAN | 15171 | A-1b(03)T | 2019-05-30 | 14151717312100 | 6 | 8.91 | Masco Energy Services (Pvt) Limited 17-Km Multan Road Lahore. | Yes | DGL/1697/2019 | PIR KHURSHID COLONY | Installed | 2019-07-30 | YES | 2019-08-24 | 8.91 | NET METERS INSTALLED . BILLING STARTED. | APPLIED TO NEPRA ON 31/05/2019 AND DGL ISSUED ON 11/07/2019.
69 | 64 | Mr. SHAHZAIB KHAN S-O MUHAMMAD SARWAR KHAN HOUSE # 10/A SATELLITE TOWN BAHAWALPUR | 15419 | A-1b(03)T | 2019-05-16 | 20154191308600 | 8 | 11.7 | MAXELL POWER Pvt. Limited | Yes | DGL/1745/2019 | BADAR SHER | Installed | 2019-06-28 | YES | 2019-06-30 | 11.7 | Connection Installed. Billing Started. | APPLIED TO NEPRA ON 17/06/2019 and DGL issued on 18/07/2019. NET METERS INSTALLED & BILLING STARTED IN 06/2019
70 | 54 | CITY SCHOOL C-O AHMAD RIZWAN SARFRAZ SAHIWAL C-O NASIMA SHAHID HEADMISTRESS COMPREHENSIVE SCHOOL MUHAMMAD PUR ROAD SAHIWAL | 15512 | A-3(A) (66) | 2019-04-01 | 27155121064412 | 80 | 45.5 | Solis Energy solutions (Pvt), Ltd. | Yes | DGL/1833/2019 | CIVIL LINES | Installed | 2019-10-17 | YES | 2019-11-04 | 45.5 | Applied to NEPRA ON 20/06/2019 and DGL Issued on 31-07-2019 | Net Meters Installed on 17/10/2019. Billing started in 10/2019.
71 | 72 | MUHAMAMD USMAN S-O MUHAMMAD ARSHAD AT USMAN CONTROLLED SHED, BASTI DIN DAR BAHAWALPUR | 15442 | B2b(12)T | 2019-05-27 | 28154420602957 | 35 | 25.08 | Sky Electric (PVT) Limited | Yes | DGL/1802/2019 | GOTH MEHRAB | Installed | 2019-08-28 | YES | 2019-09-13 | 25.08 | Applied to NEPRA ON 26/06/2019 AND DGL issued on 19/07/2019. | Billing Started in 09/2019.
72 | 73 | MUHAMAMD UMAR FAROOQ S-O FAROOQ AHMAD AKHTAR ALVI, AT HOUSE #287-B, CAPRI STREET, MOHALLAH JALIL ABAD MULTAN | 15117 | A-1b(03)T | 2019-05-02 | 17151171051202 | 5 | 7.475 | Read Solar (PVT) Limited | Yes | DGL/1785/2019 | BOHER GATE | Installed | 2019-09-19 | YES | 2019-10-27 | 7.475 | Applied to NEPRA ON 26/06/2019 AND DGL issued on 19/07/2019. | Net Meters Installed on 19/09/2019. net meters billing start in 10/2019. MCO Posted. But on wrong reference number, mistake in CP 136. wrong readings posted in 10/2019 and 11/2019. Wrong offpeak 3 sets posted in cp 136 instead of 2.
73 | 74 | ZAHOOR UL HASSAN S-O AHMAD BUKHSH AT HAPPY ELECTRONICS SHALIMAR COLONY BOSAN ROAD MULTAN. | 15175 | A-2c(06)T | 2019-06-27 | 28151751340200 | 5 | 7.04 | Feston Engineering Works Multan | Yes | DGL/1916/2019 | NEW GARRAY WALA | Installed | 2019-09-16 | YES | 2019-12-13 | 7.04 | Applied to NEPRA ON 01/07/2019. And DGL Issued on 02/05/2019. | Net Meters Installed on 16/09/2019.MCO not feeded in 10/2019 and 11/2019. Billing started in 12/2019. MCO & Readings Posted.
74 | 75 | SALEEM NASIR S-O MUHAMMAD YOUNAS AT HOUSE #03-07 MALL ROAD MULTAN CANTT | 15111 | A-1a(01)T | 2019-07-01 | 03151110403105 | 5 | 7.15 | Tesla Industries (Pvt) Limited. | Yes | DGL/1923/2019 | ISMAILABAD | Installed | 2019-08-02 | YES | 2019-12-12 | 7.15 | Applied to NEPRA ON 04/07/2019 and DGL Issued on 02/08/2019. | Billing started in 12/2019. Billing is not started in 09/2019, 10/2019 and 11/2019. Informed to SE Multan by Dir (Mkt, Trf & CM) on telephone on 27/09/2019 at 1045hrs and to Basit khaleeq via email and whatsapp in 11/2019. New meter snap on bill but again not billed in 11/2019.
75 | 76 | Mr. KHALID USMAN S-O ABDUL GHAFFAR CHOUDHARY AT AL-UMAIR HOUSE CHAH SUNAREY WALA MULTAN PUBLIC SCHOOL ROAD MULTAN | 15175 | A-1b(03)T | 2019-05-15 | 28151753234800 | 20 | 15.18 | Masco Energy Services (Pvt) Limited 17-Km Multan Road Lahore. | Yes | DGL/2019/2019 | DARBAR PEER AKBAR SHAH | Installed | 2019-08-20 | YES | 2019-09-13 | 15.18 | Connection Installed. Billing Started | Applied to NEPRA ON 05/07/2019 and DGL issued on 02/08/2019.
76 | 77 | AYAZ ANWAR S-O MUHAMMAD ANWAR AT HOUSE #23, CANTT CANAL MULTAN | 15138 | A-1b(03)T | 2019-05-20 | 20151381523315 | 6 | 8.91 | Masco Energy Services (Pvt) Limited 17-Km Multan Road Lahore. | Yes | DGL/1949/2019 | GULSHAN IQBAL | Installed | 2019-08-02 | YES | 2019-10-01 | 8.91 | Applied to NEPRA ON 05/07/2019 and DGL issued on 19/07/2019. | Billing started in 09/2019. Import Export readings will post in 10/2019.
77 | 67 | Mr. FAISAL MASOOD S-O MUHAMMAD MUKHTAR AT 16-A OFFICERS COLONY SAHIWAL | 15551 | A-1b(03)T | 2019-05-16 | 03155510309400 | 6 | 8.58 | MAXELL POWER Pvt. Limited | Yes | DGL/2015/2019 | POLICE LINE | Installed | 2019-11-02 | YES | 2019-12-12 | 8.58 | Applied to NEPRA ON 08/07/2019 and DGL Issued on 02/08/2019. | Net Meters Installed on 02/11/2019 and billing started in 12/2019. Readings not posted in 12/2019. MCO posted but net metering information cp 136 change, NTN/GST CP not Posted. Set 3 and 4 not created in MCO in 11/2019. Informed to RO on Phone on 20/11/2019. MCO and Net Metering Informations are Posted but imp and exp redings are not posted in 12/2019.
78 | 78 | Mst. TAHIRA BEGUM W-O ABDUL WAHEED KHAN, WARD #1 TEHSIL KOT ADDU DISTT MUZAFFARGARH | 15721 | A-1a(01)T | 2019-03-23 | 19157212580700 | 5 | 7.04 | Feston Engineering Works Multan | Yes | DGL/1969/2019 | KOT ADDU | Installed | 2019-09-06 | YES | 2019-09-30 | 7.04 | Applied to NEPRA ON 08/07/2019 and DGL Issued on 02/08/2019. | Net Meters Installed and billing started in 09/2019. Letter sent to SDO for checking of meters and blank snaps on bill on 11/11/2019. Blank snaps on bill for 11/2019 billing also.
79 | 79 | MR. ARSALAN KHAN S-O MUHAMMAD NADIR KHAN AT HOUSE #73 BLOCK A PHASE-I WAPDA TOWN MULTAN | 15175 | A-1b(03)T | 2019-07-01 | 18151753050302 | 5 | 7.36 | Preimer Energy (Pvt) Ltd. | Yes | DGL/2011/2019 | WAPDA TOWN | Installed | 2019-09-14 | NO | - | 7.36 | Applied to NEPRA ON 09/07/2019 and DGL Issued on 02/08/2019.NET METERS INSTALLED on 14/09/2019. | MCO NOT POSTED IN 09/2019 & 10/2019 & 11/2019. BILLING WILL START IN 12/2019. List sent to SE Multan on 02/12/2019.
80 | 80 | MR. ARSALAN KHAN S-O MUHAMMAD NADIR KHAN AT HOUSE #73 BLOCK A PHASE-I WAPDA TOWN MULTAN | 15175 | A-1b(03)T | 2019-07-01 | 18151753050803 | 5 | 7.36 | Preimer Energy (Pvt) Ltd. | Yes | DGL/2010/2019 | WAPDA TOWN | Installed | 2019-09-14 | NO | - | 7.36 | Applied to NEPRA ON 09/07/2019 and DGL Issued on 02/08/2019.NET METERS INSTALLED on 14/09/2019. | MCO NOT POSTED IN 09/2019 & 10/2019 & 11/2019. BILLING WILL START IN 12/2019. List sent to SE Multan on 02/12/2019.
81 | 81 | SYED IQBAL ALI SHAH S/O SYED MUHAMMAD YOUNIS AT MUZAFARGARH SUZUKI MOTORS JHANG ROAD MUZAFARGARH | 15712 | A-2c(06)T | 2019-07-01 | 27157120053003 | 37 | 25.2 | Feston Engineering Works Multan | Yes | DGL/2239/2019 | TUBEWELL-3 | Installed | 2019-11-08 | YES | 2019-12-04 | 25.2 | Applied to NEPRA ON 10/07/2019. DGL Issued on 02/09/2019. | Net Meters Installed on 08/11/2019. Billing started in 11/2019.
82 | 82 | Mr. ASIM ABDUL GHAFOOR S-O ABDUL GHAFOOR AT HOUSE #1497-S WAPDA TOWN PHASE-II | 15175 | A-1b(03)T | 2019-06-11 | 17151753122916 | 10 | 14.84 | HISEL POWER PAKISTAN (Pvt) LIMITED | Yes | DGL/2009/2019 | WAPDA TOWN | Installed | 2019-09-24 | YES | 2019-10-28 | 14.84 | Net meters installed on 24/09/2019. billing will start in 10/2019. Mco not posted in 09/2019 AND POSTED IN 10/2019. BILL OK | Applied to NEPRA ON 10/07/2019 and DGL Issued on 02/08/2019. Billing started in 10/2019.
83 | 83 | Mr. ABDUL SHAKOOR S/O CH. ALI MUHAMMAD AT UPPER STORY, HOUSE#89-A, MUHAMMAD COLONY BAHAWALPUR | 15441 | A-2c(06)T | 2019-06-28 | 28154410573900 | 36.64 | 12.35 | Read Solar (PVT) Limited | Yes | DGL/1989/2019 | HASHMI GARDEN | Installed | 2019-10-22 | YES | 2019-11-13 | 12.35 | Applied to NEPRA ON 12/07/2019 and DGL Issued on 02/08/2019. | Net Meters Installed on 22/10/2019. Billing started in 11/2019 billing. Readings not posted in 11 and 12/2019 Billing. Correction of bill letter sent to RO on 27/12/2019. and reply of RO to DM MIS on 31-12-2019 and MCC BWP replied on 01-01-2020 that PITC can correct the readings and letter sent to PITC by them.
84 | 84 | Mr. MUHAMMAD AKBAR S-O MUMTAZ HUSSAIN AT MANGROTHA CHUNGI NEAR BISMILLAH ICE FACTORY MANGROTHA ROAD TEHSIL TAUNSA DISTT. DG KHAN. | 15262 | A-1b(03)T | 2019-07-02 | 05152620154139 | 6 | 4.95 | Masco Energy Services (Pvt) Limited 17-Km Multan Road Lahore. | Yes | DGL/2037/2019 | SHAH SULEMAN | Installed | 2019-08-02 | YES | 2019-08-16 | 4.95 | connection Installed Billing Started 02 16/08/2019 | Applied to NEPRA ON 15/07/2019 and DGL Issued on 02/08/2019.
85 | 85 | AHMAD RIZWAN SARFRAZ C-O THE CITY SCHOOL AT CITY SCHOOL CANAL BANK 435-EB BUREWALA | 15333 | A-3(A) (66) | 2019-07-02 | 27153332500305 | 75 | 45.5 | Solis Energy solutions (Pvt), Ltd. | Yes | DGL/2075/2019 | CITY-3 | Installed | 2019-10-26 | YES | 2019-11-04 | 45.5 | Applied to NEPRA ON 18/07/2019. DGL Issued on 28/08/2019. | Net Meters Installed on 26/10/2019. Billing started in 10/2019.
86 | 86 | MUHAMMAD SALEEM AKHTAR S-O MUHAMMAD IDREES AT MADINA HOSPITAL ROAD SABZAZAR COLONY BOSAN ROAD MULTAN | 15171 | A-1b(03)T | 2019-06-19 | 12151716964200 | 5 | 3.96 | Preimer Energy (Pvt) Ltd. | Yes | DGL/2194/2019 | KHAN VILLAGE ROAD | Installed | 2019-10-15 | YES | 2019-10-22 | 3.96 | Applied to NEPRA ON 23/07/2019. DGL ISSUED ON 17/09/2019. | NET METERS INSTALLED ON 15/10/2019. BILLING STARTED IN 10/2019.
87 | 87 | MUHAMMAD SOHAIL S-O MUHAMMAD RAMZAN AT HOUSE#213-D, HASHMI GARDEN BAHAWALPUR | 15441 | A-1b(03)T | 2019-07-01 | 20154413008700 | 7.5 | 10.56 | MAXELL POWER Pvt. Limited | Yes | DGL/2181/2019 | HASHMI GARDEN | Installed | 2019-09-27 | YES | 2019-10-01 | 10.56 | Meters Installed. Billing Started. | Applied to NEPRA ON 25/07/2019. DGL ISSUED ON 12/09/2019.
88 | 88 | AL-MUQADDIM FOUNDATION C-O KHALID USMAN AT WARD#10, KHUDAD COLONY MULTAN | 15118 | A-1a(01)T | 2019-07-20 | 04151180280216 | 69 | 20 | Masco Energy Services (Pvt) Limited 17-Km Multan Road Lahore. | Yes | DGL/2091/2019 | KHUDAAD COLONY | Not Installed | - | - | - | - | Applied to NEPRA ON 25/07/2019. DG Licence issued on 28/08/2019. | Under Process for Installation of Net Meters
89 | 89 | SHABBIR AHMAD S-O BASHIR AHMAD AT 11-A FARID TOWN SAHIWAL 0301-6920690 | 15512 | A-2c(06)T | 2019-06-17 | 28155121057500 | 6 | 8.54 | M/s Power Highway | Yes | DGL/2170/2019 | CIVIL LINES | Installed | 2019-10-20 | YES | 2019-11-13 | 8.54 | Applied to NEPRA ON 30/07/2019. DG Licence issued on 03/09/2019. | Net meters installed on 20/10/2019.Billing started in 11/2019.
90 | 90 | MUHAMMAD JAVAID S-O MUHAMMAD SULEMAN AT PLOT#5-E OFFICERS COLONY MULTAN | 15172 | A-1b(03)T | 2019-05-24 | 18151723482701 | 5 | 6.12 | Read Solar (PVT) Limited | Yes | DGL/2160/2019 | OFFICER COLONY | Installed | 2019-10-22 | NO | - | 6.12 | Applied to NEPRA ON 30/07/2019.DG Licence issued on 03/09/2019. | Net meters Installed on 22/10/2019. MCO not feeded in 10and 11/2019. Billing will start in 12/2019.
91 | 91 | SAEED AHMAD S-O MUHAMMAD SULEMAN AT HOUSE NO. 5/E2, OPPPOSITE QURAN ACCADEMY OFFICERS COLONY MULTAN 061-4544661, 03007349040 | 15172 | A-1a(01)T | 2019-05-24 | 18151723482700 | 5 | 6.88 | Read Solar (PVT) Limited | Yes | DGL/2159/2019 | OFFICER COLONY | Installed | 2019-10-22 | NO | - | 6.88 | Applied to NEPRA ON 30/07/2019. | Net meters Installed on 22/10/2019. MCO not feeded in 10/2019 AND 11 /2019. Billing will start in 12/2019.
92 | 93 | MUHAMMAD SHAHZAD SALEEM S-O ASHIQ MUHAMMAD AT CHAK #32 BC, DERA BAKHA, BAHAWALPUR. Ph#03027702822, 0300877152 | 15419 | A-1b(03)T | 2019-07-20 | 04154191576801 | 7.5 | 9 | Tesla Industries (Pvt) Limited. | Yes | DGL/2262/2019 | DERA BUKHA | Installed | 2019-09-27 | YES | 2019-09-27 | 9 | Received to MEPCO NET Metering Cell on 31/07/2019. Applied to NEPRA for DG License on 01/08/2019 | MCO not Feeded. Only Net Metering Information Feeded. Letter sent to SDO on 11/11/2019 for non feeding of MCO in 10/2019 bill. MCO feeded in 11/2019 Billing.
93 | 94 | TAWAKKUL NISAR S-O ABDUL GHAFOOR, AT HOUSE#2, GULSHAN-E-NOOR, SAHIWAL, Ph#03457777641 | 15551 | A-1a(01)T | 2019-06-10 | 12155511141657 | 5 | 7.28 | SLEEK SOLAR INTERNATIONAL (Pvt) Ltd. 622-A Peoples Colony No-1, Faisalabad Ph#041-8736256-57, 0346-8666256, 0322-4607712 | Yes | DGL/2273/2019 | KHAWAJA ARIF | Not Installed | - | - | - | - | Applied to NEPRA for DG License on 01/08/2019. DG Licence issued on 20/09/2019. | Under Process for Purchase and Installation of Net Meters.
94 | 95 | ZESHAN MASOOD S-O MASOOD AHMAD AT 24 -A, SARWAR SHAHEED ROAD, MODEL TOWN-A, BAHAWALPUR ph#03008685341, 03216830330, 03366683344 | 15441 | A-1b(03)T | 2019-05-24 | 14154410044306 | 5 | 7.4 | Read Solar (PVT) Limited | Yes | DGL/2271/2019 | NLC | Installed | 2019-12-20 | YES | 2019-12-24 | 7.4 | Applied to NEPRA for DG License on 01/08/2019. DG Licence issued on 20/09/2019. | Net Meters INSTALLED ON 20/12/2019. BILLING STARTED IN 12/2019 BUT EXPORT READINGS NOT POSTED. THESE WILL BE POSTED IN 01/2020 BILLING.
95 | 96 | MUHAMAMD IQBAL BHATTI S-O MUHAMMAD SHARIF BHATTI CHOWK GHANTA GHAR KONICA LABORATORY MULTAN PH#0302-7702822 | 15113 | A-2c(06)T | 2019-06-14 | 27151130688700 | 21 | 9.9 | Preimer Energy (Pvt) Ltd. | Yes | DGL/2322/2019 | ABDALI ROAD | Installed | 2019-08-29 | YES | 2019-09-04 | 9.9 | Applied to NEPRA ON 05/08/2019. | Net Meters Installed on 29/08/2019. Wrong Billing due to amr meter not removed and amr billing not stopped by SDO/RO in 08/2019. Billing corrected in 09/2019 billing.
96 | 97 | SULTAN AZIZ S-O ABDUL AZIZ AT HOUSE #17-B, FATEH SHARE COLONY SAHIWAL Ph#03006930693, 040-4405019 | 15514 | A-1a(01)T | 2019-07-27 | 05155140376200 | 5 | 7.5 | Renewable Power (Pvt) Limited, Plot# 3-A/ Industrial Estate, Jamrud Road, Peshawar | Yes | DGL/2264/2019 | T.V CORPORATION NEW | Installed | 2019-10-04 | NO | - | 3 | Applied to NEPRA for DG License on 02/08/2019. DG Licence issued on 20/09/2019. Applied to XEN for extension of DG facility for 3 to 7.5 KW on 23/12/2019. | Meter installed on 04/10/2019. MCO not posted in 10/2019. Billing will start in 11/2019. Net meter information only posted. Letter sent to sdo on ..
97 | 98 | MUHAMMAD AHMED FAROOQ S-O MUHAMMAD FAROOQ SALEEM AT VEHARI ROAD HASILPUR Ph#0300-7859889 | 15452 | A-2a(04) | 2019-06-25 | 02154520112601 | 4.37 | 5.28 | SLEEK SOLAR INTERNATIONAL (Pvt) Ltd. 622-A Peoples Colony No-1, Faisalabad Ph#041-8736256-57, 0346-8666256, 0322-4607712 | Yes | DGL/2542/2019 | VEHARI ROAD | Installed | 2019-10-04 | NO | - | 5.28 | Applied to NEPRA for DG License on 02/08/2019. DGL issued on 04/10/2019. | Net Meters installed on 04/10/2019. Net Met Information posted. MCO not Posted. Old meter snap on Bill in 11/2019. Billing will start in 12/2019.
98 | 99 | MALIK GHULAM HUSSAIN S-O MIR BAZ KHAN STREET NO. 8-C, MOHALLAH NEW NAQSHBAND COLONY KHANEWAL ROAD MULTAN Ph#0309-7245832 | 15173 | A-1b(03)T | 2019-08-05 | 18151735872101 | 5 | 7.04 | Feston EngIneering Works Multan | Yes | DGL/2318/2019 | TARIQ ABAD | Installed | 2019-11-09 | NO | - | 7.04 | APPLIED TO NEPRA ON 17/08/2019. DGL Issued on 02/10/2019. | CP 136 Addition for new connection not posted yet. Net Meters Installed on 09/11/2019. Billing not started in 11/2019. Billing will start in 12/2019.
99 | 100 | RASHID JAMAL BHATTI S/O MUHAMMAD SHARIF RASHID INDS. OIL COLD STORAGE, KARACHI BY PASS, GHANI PUR BAHAWALPUR, Ph. No. 0335-9950986, 0321-9542612, 042-35773070 | 15443 | B2b(12)T | 2019-08-01 | 27154430936310 | 294 | 108.9 | SLEEK SOLAR INTERNATIONAL (Pvt) Ltd. 622-A Peoples Colony No-1, Faisalabad Ph#041-8736256-57, 0346-8666256, 0322-4607712 | Yes | DGL/2347/2019 | GHANI PUR | Installed | 2019-12-10 | NO | - | 108.9 | APPLIED TO NEPRA ON 17/08/2019. DGL Issued on 02/10/2019. Net Meters installed on 10/12/2019 | Billing Will start in 12/2019.
100 | 101 | AHMAD RIZWAN SARFRAZ S-O CHAUDHRY SARFRAZ HUSSAIN C-O THE CITY SCHOOL DG KHAN CAMPUS, NEW DEFENCE VIEW HOUSING SOCIETY, JAMPUR ROAD NEAR INDUS UNIVERSITY DG KHAN. Ph# 042-35773070, 0335-9950986, 0321-9542612 | 15229 | A-3(A) (66) | 2019-08-01 | 27152290057105 | 193 | 101.4 | Solis Energy solutions (Pvt), Ltd. | Yes | DGL/2504/2019 | NEW DEFENCE VIEW HOUSING SCHEME | Not Installed | - | - | - | - | APPLIED TO NEPRA ON 26/08/2019. DGL ISSUED ON 06/11/2019. | Under Process for Installation of Net Meters. Meters handed over to M&T and checked. Committee constituted. Meters will be installed in next week.
101 | 102 | HAMEEDA SULTAN W-O MUHAMMAD SULTAN AT HOUSE NO. 265 STREET NO. 1 AL - MUSTAFA COLONY MULTAN Ph#0301-7471623 | 15173 | A-1a(01)T | 2019-08-01 | 17151735671400 | 5 | 7.29 | Preimer Energy (Pvt) Ltd. | Yes | DGL/2320/2019 | NAQSHBAND | Installed | 2019-10-21 | YES | 2019-10-27 | 7.29 | APPLIED TO NEPRA ON 17/08/2019. DGL Issued on 02/10/2019. | Net Meters Installed on 21/10/2019. Billing started in 11/2019.
102 | 103 | MUHAMMAD ZAFAR SAEED S-O MUHAMMAD SAEED AKHTAR HOUSE #8 G-1 STREET # 23 POLICE LINE ROAD MULTAN | 15113 | A-1a(01)T | 2019-08-05 | 12151131265800 | 5 | 5.61 | Masco Energy Services (Pvt) Limited 17-Km Multan Road Lahore. | Yes | DGL/2357/2019 | EXPRESS | Installed | 2019-10-15 | YES | 2019-10-22 | 5.61 | APPLIED TO NEPRA ON 20/08/2019. DGL Issued on 10/10/2019. | Net Meters Installed on 15/10/2019. Billing started in 10/2019.
103 | 104 | Mrs. HAMEEDA MAZHAR W-O MAZHAR ISHAQ AT HOUSE#6-A, WAPDA TOWN, PHASE-I MULTAN 0333-6101782, 0333-6052285 | 15175 | A-1b(03)T | 2019-07-30 | 18151753059501 | 8 | 10.5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/2386/2019 | WAPDA TOWN | Installed | 2019-10-28 | NO | - | 10.5 | APPLIED TO NEPRA ON 27/08/2019. and DGL issued on 02/10/2019. | Net Meters installed on 28/10/2019.MCO not posted in 11/2019. Billing will start in 12/2019
104 | 105 | AGHA ZAFAR ABBAS SALEEM S-O AGHA DOST MUHAMMAD SALEEM HOUSE# 1511-R WAPDA TOWN-II MULTAN | 15175 | A-1a(01)T | 2019-08-25 | 17151753120605 | 6 | 8.58 | Preimer Energy (Pvt) Ltd. | Yes | DGL/2357/2019 | WAPDA TOWN | Not Installed | - | - | - | - | APPLIED TO NEPRA ON 05/09/2019. DGL Issued on 10/10/2019 | Under Process for Installation of Net Meters. Meters are installed at Pole but only Interonnections are left. It will be connected next week.
105 | 108 | M/S SOLEX CHEMICALS (Pvt) LTD C-O MUHAMMAD ALTAF SHAHID S-O ABDUL RASHID. PLOT NO. 7-C-II INDUSTRIAL ESTATE MTN | 15118 | B2b(12)T | 2019-09-04 | 27151180020701 | 112 | 90.24 | Tesla Industries (Pvt) Limited. | Yes | DGL/2497/2019 | INDUSTRIAL ESTAT-1 | Installed | 2019-12-04 | NO | - | 90.24 | APPLIED TO NEPRA ON 17/09/2019. DGL Issued on 10/10/2019 | Net Meters installed on 04/12/2019. billing will start in 12/2019.
106 | 110 | AMJAD RAI S-O RAI ABDUL GHAFOOR KHAN AT 130-A, LANE-4, HASHMI GARDEN BAHAWALPUR Ph#0300-7818776 | 15441 | A-1b(03)T | 2019-08-21 | 20154413022204 | 7 | 9.44 | Renewable Power (Pvt) Limited, Plot# 3-A/ Industrial Estate, Jamrud Road, Peshawar | Yes | DGL/2660/2019 | HASHMI GARDEN | Installed | 2019-11-07 | NO | - | 9.44 | APPLIED TO NEPRA ON 24/09/2019. DGL ISSUED ON 06/11/2019. | Net Meters installed on 07/11/2019
107 | 111 | RAZIA BEGUM W-O MUHAMMAD RASHEED AT HOUSE #88, SATELLITE TOWN BUREWALA Ph#0331-7007977 | 15332 | A-1b(03)T | 2019-09-12 | 01153320081102 | 5 | 5.2 | Preimer Energy (Pvt) Ltd. | Yes | DGL/2689/2019 | CITY-4 | Installed | 2019-11-14 | NO | - | 5.2 | APPLIED TO NEPRA ON 24/09/2019. DGL ISSUED ON 31/10/2019. | Net meters installed on 14/11/2019. Billing not started in 11/2019. Billing will start in 12/2019
108 | 113 | MR. MAJOR GENERAL SAEED AHMAD WAHLA S-O MUHAMMAD ISMAEEL WAHLA AT CHAK # 183-7 R, FORT ABBASS Ph#0333-5768883 | 15824 | D-2b(50)T | 2019-09-12 | 29158241057603 | 15 | 9.24 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/2576/2019 | RAFIQ ABAD | Installed | 2019-11-04 | YES | 2019-12-05 | 9.24 | APPLIED TO NEPRA ON 25/09/2019. DGL Issued on 10/10/2019 | Net meters installed on 04/11/2019. Billing started in 11/2019 Billing.
109 | 109 | JAMIA MASJID SIDDIQ AKBAR SCHEEME NO. 2 SAHIWAL. C/O CH ABDUL GHAFOOR S-O CH YOUSAF ALI Ph#0321-7167167 | 15551 | A-1b(03)T | 2019-09-17 | 03155510244300 | 19 | 9.6 | MAXELL POWER Pvt. Limited | Yes | DGL/2833/2019 | POLICE LINE | Installed | 2020-01-04 | NO | - | 9.6 | APPLIED TO NEPRA ON 11/10/2019 and DGL ISSUED ON 20/11/2019 | Net Meters are installed on 04/01/2020. Under Process for Billing in 01/2020.
110 | 120 | Mr. TANVER KAUSAR SHEIKH S-O SHEIKH MUHAMMAD ALI AT HOUSE#82-E, WAPDA TOWN PHASE-I MULTAN PH# 03004555111 | 15175 | A-1b(03)T | 2019-10-14 | 17151753165521 | 7 | 10.005 | Preimer Energy (Pvt) Ltd. | Yes | DGL/2938/2019 | MDA COLONY | Installed | 2019-12-17 | NO | - | 10.005 | APPLIED TO NEPRA ON 17/10/2019. DGL ISSUED ON 02/12/2019 | Net Meters installed on 17/12/2019. Billing will start in 12/2019. MCO Posted but Net Met information not posted. Letter sent to RO on 03/01/2020.
111 | 121 | Mr. AHMAD TANVIR S-O TANVEER KAUSAR SHEIKH AT HOUSE#82-E, WAPDA TOWN PHASE-I MULTAN PH# 03041939288 | 15175 | A-1b(03)T | 2019-10-14 | 17151753165514 | 7 | 10.005 | Preimer Energy (Pvt) Ltd. | Yes | DGL/2937/2019 | MDA COLONY | Installed | 2019-12-17 | NO | - | 10.005 | APPLIED TO NEPRA ON 17/10/2019. DGL ISSUED ON 21/11/2019 | Net Meters installed on 17/12/2019. Billing will start in 12/2019. MCO Posted but Net Met information not posted. Letter sent to RO on 03/01/2020.
112 | 106 | Dr. PERVAIZ AKBAR KHAN S-O SARDAR ATTA MUHAMMAD KHAN AT HOUSE#22 TIPPU SULTAN ROAD MULTAN CANTT Ph#0322-6172448 | 15111 | A-1b(03)T | 2019-09-08 | 10151110738000 | 6 | 8.775 | Sky Electric (PVT) Limited | Yes | DGL/3186/2019 | ISMAILABAD | Not Installed | - | - | - | - | SENT TO XEN CANTT (OP) ON 12/09/2019 | APPLIED TO NEPRA ON 21/11/2019 and DGL issued on 30/12/2019. Under Process for Net Meters.
113 | 124 | Mr. ATTIQUE UR REHMAN QURESHI S-O SALEEM UD DIN QURESHI AT HOUSE#F-59, SHAH RUKN E ALAM MULTAN Ph# 03056115832 | 15191 | A-1b(03)T | 2019-10-18 | 13151911051306 | 5 | 7.26 | JKS (Pvt) Limited | Yes | NIL | S/RUKAN-E-ALAM | Not Installed | - | - | - | - | SENT TO XEN SHAH RUKN E ALAM Multan ON 21/10/2019 | XEN SENT TO SDO SRA ON 25/10/2019. Applied to NEPRA on 29/11/2019.
114 | 126 | Mr. MUHAMMAD SHAFIQUE S-O SALEEM UD DIN AT HOUSE#61, F-BLOCK SHAH RUKN E ALAM COLONY MULTAN. Ph#03056115832 | 15191 | A-1b(03)T | 2019-10-18 | 13151911051309 | 5 | 7.26 | JKS (Pvt) Limited | Yes | NIL | S/RUKAN-E-ALAM | Not Installed | - | - | - | - | SENT TO XEN SHAH RUKN E ALAM Multan ON 21/10/2019 | XEN SENT TO SDO SRA ON 25/10/2019. Applied to NEPRA on 29/11/2019.
115 | 116 | SHAZIA SHAHAB RAHMANI W-O SHAHAB SAQIB REHMANI AT HOUSE #12 DCAZ ABASSAI ROAD MODEL TOWN BAHAWALPUR Ph # | 15441 | A-1b(03)T | 2019-10-03 | 15154410095703 | 5 | 5.2 | M Square R Engineering Services, 148 D Block Faisal Town Lahore, Ph# 042-35221414, 04535160099. | Yes | NIL | MODEL TOWN A | Not Installed | - | - | - | - | APPLIED TO NEPRA ON 21/11/2019 | SENT TO XEN MODEL TOWN BAHAWALPUR ON 04/10/2019. Received back on 20/11/2019. copies sent to xen and sdo.
116 | 115 | MUHAMMAD SALEEM S-O HAJI ABDUL LATIF AT ASHRAFABAD NEAR MARBLE FACTORY, JHANGHI WALA ROAD LODHRAN Ph # 0300-8682175 | 15421 | A-1b(03)T | 2019-10-03 | 17154210289960 | 5 | 7.4 | MAXELL POWER Pvt. Limited | Yes | NIL | COLONY | Not Installed | - | - | - | - | APPLIED TO NEPRA ON 18/11/2019 | SENT TO XEN LODHRAN ON 04/10/2019.Received from xen on 13/11/2019
117 | 125 | Mrs ROBINA PERVEEN W/O MUHAMMAD JAVED AT HOUSE#47-111, SABZAZAR COLONY NEAR MASJID ABU HURRAIRA BOSAN ROAD MULTAN. Ph#03056115832 | 15171 | A-1b(03)T | 2019-10-18 | 20151718306100 | 6 | 8.91 | JKS (Pvt) Limited | Yes | NIL | WAINS | Not Installed | - | - | - | - | Applied To NEPRA on 19/11/2019 | SENT TO XEN Musa Pak Multan ON 21/10/2019. Received on 18-11-2019 in MEPCO Net Metering Cell Multan
118 | 107 | Mrs. AYESHA RASHID W-O FAZAL ELAHI KHANEWAL ROAD NEAR CHOWK KHUMARAN WALA MULTAN Ph#0333-6168465 | 15173 | A-2c(06)T | 2019-10-01 | 27151736449310 | 68 | 29.7 | SLEEK SOLAR INTERNATIONAL (Pvt) Ltd. 622-A Peoples Colony No-1, Faisalabad Ph#041-8736256-57, 0346-8666256, 0322-4607712 | Yes | DGL/3135/2019 | H.ABAD | Not Installed | - | - | - | - | Applied To NEPRA on 28/10/2019. DGL ISSUED ON 16/12/2019. | UNDER PROCESS FOR NOC FOR PURCHASE OF NET METERS.
119 | 123 | MUHAMMAD HUSSAIN SHAHID S-O ALLAH BUX AT MMC COSMETIC INDUSTRY KHANEWAL ROAD QADIR PUR RANWAN MULTAN, Ph#03216342004 | 15195 | B2b(12)T | 2019-10-18 | 27151950648808 | 360 | 99 | JKS (Pvt) Limited. 278, Block D, opf housing society, Raiwand Road Lahore Ph#042-35230701 | Yes | DGL/3263/2019 | RAWAN | Not Installed | - | - | - | - | SENT TO SE (OP) Multan ON 21/10/2019. Received from SE Multan on 05/11/2019. APPLIED TO NEPRA on 08/11/2019. | DGL issued on 30/12/2019 and under process for installation of meters.
120 | 114 | SHARIF INDUSTRIES RICE MILL AT KHANEWAL ROAD QADIR PUR RAWAN MULTAN Ph#03008630962 | 15195 | B3(14)T | 2019-09-30 | 30151950749204 | 800 | 200 | Tesla Industries (Pvt) Limited. | NO | NIL | RAWAN | Not Installed | - | - | - | - | SENT TO CE (P&E) ON 30/09/2019 | SENT TO XEN (op) FOR VERIFICATION OF SYSTEM
121 | 122 | Mr. MUHAMMAD SALEEM AKHTAR S-O FATEH MUHAMMAD, AT ALFATAH RIAZABAD ROAD, QADIR PUR RAN TOWN MULTAN, Ph #0300-6321157. | 15195 | A-1a(01)T | 2019-10-10 | 04151950494100 | 6 | 8.91 | AYK (Pvt) Ltd. | Yes | DGL/3213/2019 | RAWAN | Not Installed | - | - | - | - | APPLIED TO NEPRA ON 31/10/2019 AND DGL ISSUED ON 24/12/2019. UNDER PROCESS FOR INSTALLATION OF NET METERS. | SENT TO XEN SHAH RUKN E ALAM Multan ON 18/10/2019. RECEIVED BACK FROM XEN ON 31/10/2019. NOC issued by XEN. Meters Purchased by Consumer and will be installed next week.
122 | 118 | Mr. WASEEM ASLAM S-O MUHAMMAD ASLAM, AT HOUSE #03, SHAHBAZ TOWN NEAR BLOCK E, SHAH RUKN E ALAM COLONY MULTAN Ph#03217311111 | 15192 | A-1a(01)T | 2019-10-10 | 08151921024727 | 5 | 3.84 | Hardon (Pvt) Limited | Yes | DGL/3268/2020 | NEW MULTAN | Not Installed | - | - | - | - | APPLIED TO NEPRA on 08/11/2019. DGL issued on 06/01/2020. Under Process for Installation of Net Meters. | SENT TO XEN SHAH RUKN E ALAM Multan ON 11/10/2019. Forward to sdo on 21/10/2019 by xen sra. Received from xen on 06/11/2019.
123 | 119 | Mr. SUMEER BASHEER S-O MUHAMMAD BASHIR, AT HOUSE#6, LAL SHAHBAZ TOWN NEAR E BLOCK SHAH RUKN E ALAM COLONY MULTAN Ph#03226777717 | 15192 | A-1a(01)T | 2019-10-10 | 08151921024737 | 5 | 3.9 | Hardon (Pvt) Limited | Yes | DGL/3267/2020 | NEW MULTAN | Not Installed | - | - | - | - | APPLIED TO NEPRA on 08/11/2019. DGL issued on 06/01/2020. Under Process for Installation of Net Meters. | SENT TO XEN SHAH RUKN E ALAM Multan ON 11/10/2019. For ward to sdo on 21/10/2019 by xen sra. Received from xen on 06/11/2019.
124 | 112 | Mr. MUHAMMAD AFZAL S-O GHULAM MUHAMMAD, AT HOUSE#69-B, MODEL TOWN SADIQABAD, PH#03458405801, FOR DG FACILITY 4.875 KW AGAINST A/C#0915642098623 | 15642 | A-1a(01)T | 2019-09-20 | 09156420986235 | 5 | 4.875 | Sky Electric (PVT) Limited | Yes | NIL | SETTLITE TOWN | Not Installed | - | - | - | - | APPLIED TO NEPRA ON 18/11/2019 | SENT TO XEN SADIQBAD ON 23/09/2019. Received from xen on 13/11/2019
125 | 127 | Mrs. KHALIDA ISMAIL W-O MUHAMMAD ISMAIL SAAD AT HOUSE#312 NEW SHALIMAR COLONY BOSAN ROAD MULTAN Ph#0335-8644893, 0300-4003150 TAIMUR | 15175 | A-1b(03)T | 2019-09-20 | 19151758243300 | 5 | 7.48 | Tesla Industries (Pvt) Limited. | Yes | DGL/3136/2019 | DARBAR PEER AKBAR SHAH | Not Installed | - | - | - | - | APPLIED TO NEPRA on 28/10/2019. DGL ISSUED ON 19/12/2019. | UNDER PROCESS FOR INSTALLATION OF METERS. (Meters are not available with installer)
126 | 128 | MIAN MUHAMMAD ANWAR ZAHID S-O CHAUDHRY MUHAMMAD RASHEED AT BLING HOTEL BESIDES BUSINESS CITY PLAZA BOSAN ROAD MULTAN Ph#0321-6837646 & 061-6212322 | 15171 | A-2c(06)T | 2019-10-28 | 27151717325807 | 76 | 50 | Preimer Energy (Pvt) Ltd. | Yes | DGL/3214/2019 | SABZA ZAR | Not Installed | - | - | - | - | SENT TO XEN Musa Pak Multan ON 21/10/2019 and received on 05/12/2019 by hand by consumer. | Applied to NEPRA on 05/12/2019 and DGL Issued on 19/12/2019. Under Process for Installation of Net Meters.
127 | 129 | NAEEM AHMAD S-O GHULAM GAUS NEAR CIVIL HOSPITAL ABDUL HAKIM Ph#0300-8798804 | 15933 | A-1a(01)T | 2019-10-21 | 3159330219710 | 6 | 8.25 | Preimer Energy (Pvt) Ltd. | NO | NIL | CITY | Not Installed | - | - | - | - | SENT TO XEN (op) ON 31/10/2019 | 0
128 | 130 | Mr. Ch. PERVAIZ IQBAL S-O Ch ANDUL SATTAR AT BILAWAL HOUSE MULTAN PUBLIC SCHOOL ROAD MULTAN Ph#0321-6668833 | 15175 | A-2c(06)T | 2019-11-07 | 28151750610819 | 12 | 17.55 | Sky Electric (PVT) Limited | NO | NIL | DARBAR PEER AKBAR SHAH | Not Installed | - | - | - | - | After secrutiny of files at Net Metering Cell, files are sent to XEN Musa Pak for further process on 11/11/2019. | 0
129 | 131 | Mr. MUHAMMAD WAQAS KHAN S-O MUHAMMAD ZAHID KHAN AT IBRAHIM GARDENS BYPASS ROAD MULTAN Ph#0321-8471717 | 15174 | A-1b(03)T | 2019-11-07 | 20151743101806 | 7 | 10.005 | Sky Electric (PVT) Limited | Yes | NIL | MEHMOOD KOT | Not Installed | - | - | - | - | After secrutiny of files at Net Metering Cell, files are sent to XEN Musa Pak for further process on 11/11/2019. | File received on 09/12/2019 after signature. Applied to NEPRA on 10/12/2019.
130 | 132 | Mr. MUHAMMAD SHAHID S-O MUHAMMAD SAEED KHAN AT IBRAHIM GARDENS BYPASS ROAD MULTAN Ph#03216308088 | 15174 | A-1b(03)T | 2019-11-07 | 20151743101810 | 7 | 10.005 | Sky Electric (PVT) Limited | Yes | NIL | MEHMOOD KOT | Not Installed | - | - | - | - | After secrutiny of files at Net Metering Cell, files are sent to XEN Musa Pak for further process on 11/11/2019. | File received on 09/12/2019 after signature. Applied to NEPRA on 10/12/2019.
131 | 133 | Mr. RASHID MUNIR RAMAY S-O MUHAMMAD MUNIR RAMAY, AT HOUSE#168, STREET #2, FAISAL BAGH STREET, NEW CENTRAL JAIL ROAD BAHAWALPUR, Ph#03336301996 | 15444 | A-1a(01)T | 2019-11-06 | 05154440563166 | 5 | 5.2 | Tesla Industries (Pvt) Limited. | Yes | NIL | BADAR-UD-DIN SHAHEED | Not Installed | - | - | - | - | Applied to NEPRA on 13/11/2019 | -
132 | 134 | Mr. ASHIQ HUSSAIN BHATTI S-O KHUDA BUX AT CH #128-A TDA, DERA SHEIKHU BHATTI BROTHERS, DASTI WALA LAYYAH Ph#03077370726 | 15731 | B1b(09)T | 2019-11-26 | 28157312033800 | 19 | 19.26 | Orient Energies (Pvt) Ltd. | Yes | NIL | CITY | Not Installed | 0 | 0 | 0 | 0 | SENT TO XEN (op) ON 26/11/2019. Received from XEN on 09/12/2019 AND SENT BACK TO XEN FOR STAMP. RECEIVED BACK ON 18/12/2019. | APPLED TO NEPRA ON 18/12/2019.
133 | 135 | Mrs. SAMEENA MEER W-O MEHFOOZ AHMAD AT HOUSE#105-B, WAPDA TOWN PHASE-I, NOTHERN BYPASS ROAD MULTAN Ph#0300-2275555 | 15175 | A-1b(03)T | 2019-11-11 | 18151753071400 | 6 | 9 | Masco Energy Services (Pvt) Limited 17-Km Multan Road Lahore. | Yes | NIL | WAPDA TOWN | Not Installed | - | - | - | - | APPLIED TO NEPRA ON 19/11/2019 | -
134 | 136 | NAVEED NISAR S-O NISAR AHMAD, AT M-S PRIME PACKAGES 83-A, INDUSTRIAL ESTATE MULTAN. Ph#061-6538802-03 , 0300-8636456 | 15118 | B2b(12)T | 2019-11-21 | 30151180005502 | 310 | 58.29 | Orient Energies (Pvt) Ltd. | Yes | NIL | INDUSTRIAL ESTAT-1 | Not Installed | 0 | 0 | 0 | 0 | SENT TO SE (OP) MULTAN ON 21/11/2019 AND RECEIVED BACK ON 11/12/2019 | APPLIED TO NEPRA FOR DG LICENSE ON 12/12/2019.
135 | 137 | Mr. AZIZ RAFIQ S-O MUHAMMAD RAFIQ AT BILLAY KA DERA RESTURANT NEAR ASKARI PETROL PUMP MUZAFFAR GARH ROAD MULTAN. Ph#03008738222 | 15138 | A-2c(06)T | 2019-11-21 | 27151380675007 | 76 | 50.04 | Preimer Energy (Pvt) Ltd. | Yes | NIL | SHER SHAH | Not Installed | 0 | 0 | 0 | 0 | SENT TO SE (OP) MULTAN ON 21/11/2019 AND RECEIVED BACK ON 18/12/2019. | APPLIED TO NEPRA FOR DG LICENSE ON 18/12/2019.
136 | 138 | Dr. MAZHAR UL HAQ S-O MUHAMMAD ATTA ULLAH HOUSE#25-C-1, SHABBIR SHAHEED ROAD MODEL TOWN -A BAHAWALPUR Ph#03006847525 | 15441 | A-1b(03)T | 2019-09-12 | 15154410085500 | 7.38 | 5.6 | ADAPTIVE TECHNOLIGIES (Pvt) Ltd.SUITE#3, 4TH FLOOR DEAN ARCADE, BLOCK-8, CLIFTON, KARACHI. PH#(92-213)586 5896, 586 8044 | Yes | DGL/3374/2020 | MODEL TOWN A | Not Installed | - | - | - | - | Applied to NEPRA on 22/11/2019. DGL issued on 06/01/2020. Under Process for Installation of Net Meters. | 0
137 | 139 | Dr. SHEHBAZ AHMED QURESHI S-O FAIZ AHMAD QURESHI, AT BX-128-2 NEW SADIQ COLONY BAHAWALPUR, Ph#03006848384 | 15441 | A-1b(03)T | 2019-09-11 | 18154410464306 | 5 | 7.245 | ADAPTIVE TECHNOLIGIES (Pvt) Ltd.SUITE#3, 4TH FLOOR DEAN ARCADE, BLOCK-8, CLIFTON, KARACHI. PH#(92-213)586 5896, 586 8044 | Yes | NIL | N.MAHAL(CANTT) | Not Installed | - | - | - | - | Applied to NEPRA on 22/11/2019. | 0
138 | 140 | Dr. SHAHBAZ AHMAD QURESHI S-O HAFIZ FAIZ AHMAD QURESHI, AT-BX-293-1 NEW SADIQ COLONY BAHAWALPUR, Ph#03233385000 | 15441 | A-1b(03)T | 2019-09-12 | 18154410464313 | 6 | 8.9 | ADAPTIVE TECHNOLIGIES (Pvt) Ltd.SUITE#3, 4TH FLOOR DEAN ARCADE, BLOCK-8, CLIFTON, KARACHI. PH#(92-213)586 5896, 586 8044 | Yes | DGL/3375/2020 | N.MAHAL(CANTT) | Not Installed | - | - | - | - | Applied to NEPRA on 22/11/2019. DGL issued on 06/01/2020. Under Process for Installation of Net Meters. | 0
139 | 141 | MAKKI MASJID ANSAR COLONY C-O Mr. ABBASS RAZA S-O MUHAMMAD ILYAS AT MAKKI MASJID ANSAR COLONY NEAR RAILWAY PHATAK MULTAN Ph#03008730425 | 15194 | A-1a(01)T | 2019-11-25 | 15151940860105 | 5 | 7.28 | Preimer Energy (Pvt) Ltd. | NO | NIL | SHARIF PURA | Not Installed | - | - | - | - | SENT TO XEN (op) ON 26/11/2019 and received from XEN on 01/01/2020 and unsigned copy due to incomplete installation ( Breakers and Disconnection switch) | file is sent again to XEN (OP) for signing of agreement after removing the objection of SDO (OP) Gulberg on 10/01/2020
140 | 142 | AL HUDA MOSQUE SHAH RUKN E ALAM COLONY MULTAN C-O Mr. MUHAMMAD ATTAULLAH KHAN S-O HAJI MUHAMMAD NAWAZ KHAN AT HOUSE#13, BLOCK F SHAH RUKN E ALAM COLONY MULTAN Ph#03000648115, 03336104905 | 15191 | A-1b(03)T | 2019-11-25 | 13151911050701 | 7 | 8.45 | Preimer Energy (Pvt) Ltd. | Yes | NIL | S/RUKAN-E-ALAM | Not Installed | - | - | - | - | SENT TO XEN (op) ON 26/11/2019. Received from XEN on 01/01/2020. Applied to NEPRA on 01/01/2020. | 0
141 | 143 | Mr. MUHAMMAD ATTAULLAH KHAN S-O HAJI MUHAMMAD NAWAZ KHAN AT TAHEEM PLAZA, PLOT#23-24 BLOCK G, SHAH RUKN E ALAM COLONY MULTAN Ph# 03000648115, 03336104905 | 15191 | A-2c(06)T | 2019-11-25 | 28151911014601 | 10 | 10.78 | Preimer Energy (Pvt) Ltd. | Yes | NIL | S/RUKAN-E-ALAM | Not Installed | - | - | - | - | SENT TO XEN (op) ON 26/11/2019. Received from XEN on 01/01/2020. Applied to NEPRA on 01/01/2020. | 0
142 | 144 | Mr. MUHAMMAD NASAR ULLAH KHAN S-O ABDUL SATTAR NADVI AT HOUSE #C-1-504, PROFESSOR COLONY IN FRONT OF EID GAH MUZAFFAR GARH Ph#03336168465, 03006865100 , 03337485400 | 15711 | A-1a(01)T | 2019-11-25 | 10157110708502 | 6 | 7.26 | M Square R Engineering Services, 148 D Block Faisal Town Lahore, Ph# 042-35221414, 04535160099. | Yes | NIL | YADGAR CLUB | Not Installed | - | - | - | - | Applied to NEPRA on 27/11/2019 | 0
143 | 145 | Mr. MUHAMMAD TARIQ RASHEED S-O SHEIKH ABDUL RASHEED HOUSE#1275 MOHALLAH NASHAMEN COLONY NEAR ROOMI CHOWK BOSAN ROAD MULTAN Ph#03456334522 & 03040001024 | 15171 | A-1a(01)T | 2019-11-25 | 19151718130200 | 6 | 8.71 | Masco Energy Services (Pvt) Limited 17-Km Multan Road Lahore. | NO | NIL | SABZA ZAR | Not Installed | - | - | - | - | SENT TO XEN (op) ON 26/11/2019 | 0
144 | 146 | YUSUF ALI QAIM TRUST C-O TAHIR YUSUF CHOUDHARY S-O CH. YUSUF ALI QAIM AT YUSUF ALI QAIM TRUST CHAK #10 FW HASIL PUR MUKHTARABAD PH#0300-4666325 | 15452 | A-3(A) (66) | 2019-11-22 | 28154521152704 | 20 | 8.1 | PANTERA ENERGY (Pvt) Ltd. 14A, XX COMMERCIAL, PHASE-3 DHA, LAHORE Ph#042-35894174 | NO | NIL | AL-TAHIR | Not Installed | - | - | - | - | SENT TO XEN (op) ON 26/11/2019 | 0
145 | 147 | HASCOL PETROL PUMP C-O MUHAMMAD MANSHA S-O MANZOOR AHMAD CHAK #80-10 R, PEROWAL KHANEWAL Ph#0323-3238880, 0321-4412716 (NOW Owner Mr. HAMID KHAN Ph#0321-4412716, HASCOL PETROL PUMP AND MARQUEE UNDER FUEL EXPERT Ltd. ) | 15913 | A-2c(06)T | 2019-11-22 | 27159132372601 | 130 | 80.85 | PANTERA ENERGY (Pvt) Ltd. 14A, XX COMMERCIAL, PHASE-3 DHA, LAHORE Ph#042-35894174 | NO | NIL | PEER ASGHAR ALI SHAH | Not Installed | - | - | - | - | SENT TO XEN (op) ON 26/11/2019 | 0
146 | 148 | Mr. MUHAMMAD UMER RASHEED S-O SHEIKH ABDUL RASHEED AT HOUSE#1275-W-XXXIV, NEAR ROOMI CHOWK, NASHEMAN COLONY, MAIN BOSAN ROAD MULTAN, Ph#03006307504 | 15171 | A-1b(03)T | 2019-11-11 | 19151718130300 | 6 | 8.71 | Masco Energy Services (Pvt) Limited 17-Km Multan Road Lahore. | Yes | NIL | SABZA ZAR | Not Installed | - | - | - | - | Applied to NEPRA on 27/11/2019 | 0
147 | 149 | Mrs. ZULAIKHA FURQAN W-O FURQAN RAFIQ MIRZA AT HOUSE#47, AL JANAT HOMES , SULTANABAD COLONY MULTAN PH#03008639288 | 15171 | A-1b(03)T | 2019-11-27 | 15151717476600 | 8 | 11.7 | Sky Electric (PVT) Limited | NO | NIL | NAWAB PUR ROAD | Not Installed | - | - | - | - | SENT TO XEN (op) ON 29/11/2019 | APPLIED TO MEPCO IN 27/11/2019 BY POST
148 | 150 | MANAGER MCB MAIN BRANCH SADIQABAD C-O Mr. HAMAYUN RASHEED S-O RASHEED AHMAD, AT MCB MAIN BRANCH SADIQABAD Ph#03337417710 | 15641 | A-2c(06)T | 2019-11-27 | 27156410653200 | 40 | 11.7 | Sky Electric (PVT) Limited | NO | NIL | JINAH TOWN | Not Installed | - | - | - | - | SENT TO XEN (op) ON 29/11/2019 | APPLIED TO MEPCO IN 27/11/2019 BY POST
149 | 151 | Mr. ANWAR HUSSAIN S-O Ch. MEHAR DIN, AT COLD STORAGE BUDHLA SANAT ROAD, MOUZA NAI WALA MULTAN Ph#03218375218 | 15192 | B2b(12)T | 2019-11-29 | 27151920857501 | 150 | 100.5 | Tesla Industries (Pvt) Limited. | Yes | NIL | NEW MULTAN | Not Installed | - | - | - | - | Received to NET Metering Cell on 29/11/2019. Applied to NEPRA ON 04/12/2019. | Waited for Demand Draft Rs.5000/- and Consumer and Wittness ID Cards.Informed to Installer by SDO on 29/11/2019
150 | 152 | Mr. ARIF SATTAR S-O SHEIKH ABDUL SATTAR RESIDENT OF HOUSE # 06, CANTT CANAL VIEW MOHALLAH WALAYATABAD #1 MULTAN Ph#03216326000, 03210001024 | 15138 | A-1a(01)T | 2019-12-03 | 20151381523307 | 5 | 7.48 | Tesla Industries (Pvt) Limited. | Yes | NIL | GULSHAN IQBAL | Not Installed | - | - | - | - | Received to NET Metering Cell on 03/12/2019 | Sent to XEN City on 03/12/2019 and received back on 12/12/2019 by hand from installer. APPLIED TO NEPRA FOR DG LICENSE ON 12/12/2019.
151 | 153 | Mr. SHEIKH MEHTAB ALI RAZA S-O SHEIKH TANVEER UL HASSAN AT CITY PETROLEUM DERA ADDA MULTAN Ph#03009635079, 03097067870 | 15117 | A-2c(06)T | 2019-08-31 | 28151170161900 | 6 | 8.7 | Preimer Energy (Pvt) Ltd. | Yes | NIL | HASSAN PARWANA | Not Installed | - | - | - | - | Received to NET Metering Cell on 03/12/2019 | Applied to NEPRA ON 04/12/2019
152 | 155 | Mr. MUSHTAQ AHMAD S-O MUHAMMAD BUX AT HOUSE#1-224 ASIF STREET MAIN TAUNSA ROAD GARDEN TOWN MULTAN CANTT. Ph#061-4547642 & 0300-6324131. | 15138 | A-1a(01)T | 2019-12-04 | 15151380070902 | 5 | 7.41 | Preimer Energy (Pvt) Ltd. | Yes | NIL | GARDEN TOWN | Not Installed | - | - | - | - | Received to NET Metering Cell on 04/12/2019 | Applied to NEPRA ON 04/12/2019
153 | 156 | Mr. KHAWAJA MAQBOOL MUSTAFA S-O KHAWAJA MUHAMMAD YOUSAF AT BASTI BHAGSAR MOZA KAYAN PUR MULTAN Ph# 03009222990 | 15118 | A-1b(03)T | 2019-12-06 | 20151181511507 | 6 | 8.96 | Preimer Energy (Pvt) Ltd. | Yes | NIL | BAHAUDDIN ZAKARIYA | Not Installed | - | - | - | - | Received to NET Metering Cell on 06/12/2019 | Applied to NEPRA ON 06/12/2019
154 | 157 | SHAHIDA ATA W-O ATTA-UL-HAQ AT HOUSE#3,AHMED VILLAS NOTHERN BYPASS ROAD MULTAN,CHAH TIBBI WALA SHALIMAR COLONY, MULTAN Ph#03006938506 | 15175 | A-1b(03)T | 2019-12-10 | 20151758411400 | 5.5 | 6.82 | M/s Power Highway 5th Floor, Venus Plaza, 7 Egerton Road, Lahore. Tel: 042-36370380-81, 92 3111 197 197 Email: info@powerhighway.net | Yes | NIL | DARBAR PEER AKBAR SHAH | Not Installed | - | - | - | - | Received to NET Metering Cell on 10/12/2019 FROM XEN Office | Applied to NEPRA ON 10/12/2019
155 | 158 | NADEEM UR REHMAN KHAN KHAKWANI S-O SAIF UR REHMAN KHAKWANI AT SHARIF PURA NEW SHALIMAR COLONY MOHALLAH REHMAN STREET MULTAN Ph#0305-6925898, 0321-8375218 | 15175 | A-1b(03)T | 2019-12-10 | 19151758146200 | 7.48 | 5 | Tesla Industries (Pvt) Limited. | Yes | NIL | DARBAR PEER AKBAR SHAH | Not Installed | - | - | - | - | Received to NET Metering Cell on 10/12/2019 and sent to xen musapak on 11/12/2019. | received from musa pak by hand by consumer on 27/12/2019 and applied to NEPRA on 27/12/2019.
156 | 159 | Mr. WAHEED AKBAR S-O AKBAR ALI RESIDENT OF CHAK#109, 9-L, POST OFFICE INAYAT ELAHI COLONY SAHIWAL, Ph#03156140140 | 15552 | B2b(12)T | 2019-12-13 | 27155521387501 | 80 | 48 | E CUBE SOLUTIONS (Pvt) Ltd., 2nd Floor, Bukhari Heights, 17 Quaid Commercial, Bahria Town, Lahore Ph#0316-4500061 | NO | NIL | BUDH DHAKOO | Not Installed | - | - | - | - | Received to NET Metering Cell on 13/12/2019 FROM Installer by Post. Forwarded to XEN (OP) Sahiwal 2nd Division. | 0
157 | 160 | Mr. MUHAMMAD YOUSAF S-O MAHER MUHAMMAD KHAN, RESIDENT AT,CHAK # 82-5L KATOOR WALA , SAHIWAL Ph# 03337798801 | 15513 | A-1a(01)T | 2019-12-18 | 07155130572505 | 7 | 10.24 | Sky Electric (PVT) Limited | Yes | NIL | MAIZ FORM | Not Installed | - | - | - | - | Received to NET Metering Cell on 18/12/2019 FROM CONSUMER BY HAND. | Applied to NEPRA on 18/12/2019
158 | 161 | MR. GUL MUHAMMAD S-O YOUSAF KHAN AT ARSALAN BROTHERS PSO PUMP JAIL CHOWK VEHARI ROAD, MULTAN Ph#061-4230400, 0301-8383529, 0300-8867507 | 15125 | A-2c(06)T | 2019-12-18 | 31151250927000 | 19 | 26.5 | Preimer Energy (Pvt) Ltd. | Yes | NIL | GHALA MANDI | Not Installed | - | - | - | - | Received to NET Metering Cell on 18/12/2019 FROM CONSUMER BY HAND. | Applied to NEPRA on 18/12/2019
159 | 162 | Ch. RASHID ALI JAJJA S-O Ch. MUMTAZ AHMAD JAJJA RESIDENT AT JAJJA HOUSE, STREET #5, HABIB COLONY, GULBERG ROAD BAHAWALPUR.Ph#0301-4441654 | 15443 | A-1b(03)T | 2019-12-20 | 19154430051802 | 5 | 7.04 | M Square R Engineering Services, 148 D Block Faisal Town Lahore, Ph# 042-35221414, 04535160099. | NO | NIL | MODEL TOWN B | Not Installed | - | - | - | - | Received to NET Metering Cell on 20/12/2019 FROM CONSUMER BY HAND. AND SENT TO XEN MODEL TOWN ON 20/12/2019. | 0
160 | 163 | Mr. TARIQ HABIB KHAN S-O HABIB AHMAD KHAN RESIDENT AT HOUSE#33-Y, STREET#03, TARIQ BIN ZIAD COLONY SAHIWAL Ph#03330240687 | 15513 | A-1a(01)T | 2019-12-20 | 15155131348501 | 5 | 5 | Renewable Power (Pvt) Limited, Plot# 3-A/ Industrial Estate, Jamrud Road, Peshawar | Yes | NIL | TARIQ BIN ZAID | Not Installed | - | - | - | - | Received to NET Metering Cell on 20/12/2019 FROM INSTALLER BY TCS. AND SENT TO NEPRA ON 20/12/2019. | 0
161 | 164 | Mr. SAUD MAJEED S-O ABDUL MAJEED RESIDENT AT BANGLA SAUD MAJEED NEAR NOOR MAHAL OPPOSITE HASHMI GARDEN CHOWK FAWARA ROAD BAHAWALPUR Ph#0300-8780456 | 15441 | A-1b(03)T | 2019-12-20 | 27154410626793 | 78 | 33.6 | AYK (Pvt) Ltd. | NO | NIL | N.MAHAL(CANTT) | Not Installed | - | - | - | - | Received to NET Metering Cell on 20/12/2019 FROM INSTALLER BY TCS. AND SENT TO XEN ON 20/12/2019. | 0
162 | 165 | Mr. MUHAMMAD SOHAIB ZIA S-O Ch. ZIA UL HAQ RESIDENT AT HOUSE# 113, PAM VIEW HOUSING SCHEEME, SAHIWAL Ph#0321-7167167 | 15514 | A-1b(03)T | 2019-12-23 | 14155141136625 | 5 | 5.6 | MAXELL POWER Pvt. Limited | Yes | NIL | MADHALI SHARIF | Not Installed | - | - | - | - | Received to NET Metering Cell on 23/12/2019 FROM INSTALLERAFTER SIGNATURES FROM FIELD OFFICES BY TCS AND SENT TO NEPRA ON 23/12/2019. | 0
163 | 166 | Mr. NASIR IQBAL KAYANI S-O ABDUL MAJEED KAYANI RESIDENT AT HOUSE#94-A, RAFEE GARDEN SAHIWAL Ph#0321-7167167 | 15514 | A-1b(03)T | 2019-12-23 | 14155141164216 | 5 | 7.26 | MAXELL POWER Pvt. Limited | Yes | NIL | RAFI GARDEN | Not Installed | - | - | - | - | Received to NET Metering Cell on 23/12/2019 FROM INSTALLERAFTER SIGNATURES FROM FIELD OFFICES BY TCS AND SENT TO NEPRA ON 23/12/2019. | 0
164 | 92 | Mr. MOHSIN ZULFIQAR S-O ZULFIQAR ALI, AT HOUSE#65-A, STREET #7, ALMAJEED PARDISE SOCIETY RAFI QAMAR ROAD BAHAWALPUR Ph# 03009680333 | 15414 | A-1b(03)T | 2019-12-30 | 19154141548700 | 8 | 10.24 | E CUBE SOLUTIONS (Pvt) Ltd., 2nd Floor, Bukhari Heights, 17 Quaid Commercial, Bahria Town, Lahore Ph#0316-4500061 | Yes | NIL | DARBAR MAHAL | Not Installed | - | - | - | - | Received to NET Metering Cell on 16/07/2019 FROM CONSUMER AND RETURNED DUE TO INCOMPLETE FILE AND RESUBMITTED ON 03/01/2020 AFTER COMPLETION BY TCS. | APPLIED TO NEPRA ON 03/01/2020.
164 | [5 empty] | Total KW | 12507.87 | 3783.92 |  | 152 | 2886.28 |  | 103 |  | 82 | Total KW | 2449.935 | 2116.655 | 81
[5 empty] | XEN | 161.93
[5 empty] | SE | 80.85
[5 empty] | CE | 200
[5 empty] | SUM | 442.78
[5 empty] | BILL | 337.78
[5 empty] | COMP | 2116.655
[5 empty] | CON | 431.845
[5 empty] | Total | 3783.92

## abstract
MEPCO Net Metering Status |  |  | As on 10-01-2020
Description | No. | Load (KW) | Remarks
Applications Received | 164 | 3783.92 | Applications received in MEPCO Net Metering Cell Multan
Generation licences applied to NEPRA | 152 | 3341.14 | Applications were applied to NEPRA for DG License by MEPCO Net Metering Cell Multan. Remaining applications are sent to Field Offices.
Generation licences issued by NEPRA | 121 | 2886.28 | -
Connections Installed | 103 | 2449.935 | Remaining Meters will be installed after provision of meters by consumers and Tested by M&T.
Connections Where Billing Started | 82 | 2116.655 | -
KWh EXPORTED TO MEPCO TILL 11/2019 |  | 6,52,405 KWh | 78 BILLED CONNECTIONS