## Net-Metering-Info
NET METERING APPLICATION(S) INFORMATION/STATUS
| COMPANY NAME: MEPCO | [16 empty] | Dated:10-06-2019
Sr. No | Application No. | Name of Applicant | Sub Division Code | Tariff | Application Date | Reference No. | Sanctioned Load | Required Load for Net Metering | Name of Installer | Applied To NEPRA (Yes or No) | Generation Licence | Feeder | Installation Status (Installed or Uninstalled) | Installation Date | Billing Started (Yes or No) | Billing Start Date | Generation (KW) | Remarks | Current Position (What is Present Status i.e. either with installer or SDO or NEPRA etc.)
1 | 1 | OFFICE BUILDING TEHSILDAR LODHRAN NEAR MARKET COMMITTEE OFFICE LODHRAN | 15421 | A-1b(03)T | 2016-06-18 | New 15154210167800 Old 03154210167800 | 11 | 3 | M/S Creative Electronics | Yes | DGL/75/2017 | City Lodhran | Installed | 2018-01-06 | Yes | 2018-01-10 | 3 | Connection Installed. Billing Started | -
2 | 2 | XEN CIVIL MEPCO | 15173 | A-3(66) | 2016-07-12 | 13151734972100 | 12 | 3 | Reap | Yes | DGL/48/2017 | Wapda Colony | Installed | 2016-07-28 | Yes | 2016-08-23 | 3 | Connection Installed. Billing Started | -
3 | 3 | KHALID NAZEER CMISSIONER SAHIWAL | 15512 | A-3(66) | 2016-08-12 | 12155121038000 | 7 | 3 | M/S Creative Electronics | Yes | DGL/74/2017 | Civil Lines | Installed | 2018-05-10 | Yes | 2018-06-20 | 3 | Connection Installed. Billing Started | -
4 | 4 | MALIK NOOR ASGHAR BUCHA S/O MLK NOOR MUHAMMAD BUCHA THE GRAND COMMERCIAL BUILDING BUCH VILLAS H/S BOSAN ROAD MTN | 15175 | A-2c(06)T | 2016-09-12 | 27151758887001 | 857 | 25.5 | Orient Energies (Pvt) Ltd. | Yes | DGL/83/2017 | Buch Villas | Installed | 2018-01-17 | Yes | 2018-03-01 | 25.5 | Connection Installed. Billing Started | DGL Cancelled due to enhancement application and new license 114.37 kw license issued.
5 | 5 | Asif Iqbal SM Bashir Agencies | 15514 | New A-2c(06)T, Old A-2a(04) | 2016-12-15 | New 28155140275502 and old 03155140275502 | 5 | 4.62 | Royal Energy Sultan Electronics | Yes | DGL/80/2017 | College Road | Installed | 2018-01-18 | Yes | 2018-02-12 | 4.62 | Connection Installed. Billing Started | -
6 | 6 | MUHAMMAD ARSHAD NADEEM S-O MHAMMAD ASHIQ ST NO 1 MADINA ABAD CLY MTN MULTAN | 15132 | A-1b(03)T | 2017-01-06 | 13151322030405 | 5 | 10 | Solar Tech. | Yes | DGL/117/2017 | Timber Market | Installed | 2017-12-17 | Yes | 2017-12-21 | 10 | Connection Installed. Billing Started | -
7 | 7 | SAJIDA KHALID W/O CH.KHALID LATIF PUNJAB SMALL INDUSTRIES MTN | 15175 | A-1b(03)T | 2017-01-26 | 17151753136101 | 5 | 10 | Pak Friends Enterprises | Yes | DGL/107/2017 | Darbar Peer Akbar Shah | Installed | 2017-12-19 | Yes | 2017-12-20 | 10 | Connection Installed. Billing Started | -
8 | 8 | UNILEVER PAKISTAN LIMITED TEA FACTORY CHAK NO.88-A10R KHANEWAL | 15913 | B3(14)T | 2017-02-08 | 27159132372500 | 503 | 110 | Reon | Yes | DGL/106/2017 | UNILEVER TEA FACTORY | Installed | 2018-01-16 | Yes | 2018-02-03 | 110 | Connection Installed. Billing Started | -
9 | 9 | KHAWAJA MUHAMMAD YOUNIS S-O KHAWAJA MUHAMMAD MASOOD FATIMA MODEL SCHOOL MULTAN ROAD K.WALA | 15921 | A-1b(03)T | 2017-03-03 | 28159210647407 | 6 | 5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/76/2017 | Spinning Unit-2 | Installed | 2017-12-21 | Yes | 2018-02-13 | 5 | Connection Installed. Billing Started | -
10 | 10 | KH MUHAMMAD YOUNIS S-O MUHAMMAD MASOOD 13 B OFFICER CLY MULTAN | 15172 | A-1b(03)T | 2017-03-03 | 18151723474200 | 12 | 32 | Preimer Energy (Pvt) Ltd. | Yes | DGL/78/2017 | Eid Gah Road | Installed | 2017-12-19 | Yes | 2017-12-27 | 32 | Connection Installed. Billing Started | -
11 | 11 | MEHMOOD TEXTILE MILLS LTD MULTAN LOHARI GATE MULTAN CITY | 15113 | A-2c(06)T | 2017-03-03 | 27151130721400 | 200 | 64 | Preimer Energy (Pvt) Ltd. | Yes | DGL/77/2017 | Abdali Road | Installed | 2018-01-29 | Yes | 2018-02-03 | 64 | Connection Installed. Billing Started | -
12 | 12 | Kh M YOUNAS M/S MASOOD SPINNING MILLS UNIT NO.02 04-KM MULTAN ROAD KABIR WALA | 15921 | B3(14)T | 2017-03-03 | 30159212533901 | 4999 | 320 | Preimer Energy (Pvt) Ltd. | Yes | DGL/79/2017 | Masood Spinning Unit-2 | Installed | 2018-01-31 | Yes | 2018-02-03 | 320 | Connection Installed. Billing Started | -
13 | 13 | SHABBIR AHMAD S-O MIRAJ DIN EASTREN PRODUCTS-VITAL TEA LTD QAZI WALA HAROON ABAD | 15821 | B2b(12)T | 2017-12-26 | 27158210966702 | 482 | 304 | REON | Yes | DGL/478/2018 | KHATAN | Installed | 2018-11-03 | Yes | 2019-01-03 | 304 | Connection Installed. Billing Started | -
14 | 14 | NAIMAT ULLAH S.O ALLAH BACHAYA QURESHI 259-N WAPDA TOWN-11 MTN | 15175 | A-1b(03)T | 2017-06-01 | 17151753132415 | 5 | 10 | SOLAR MASTER | Yes | DGL/128/2017 | Wapda Town | Installed | 2017-12-19 | YES | 2017-12-20 | 10 | Connection Installed. Billing Started | -
15 | 15 | NASEEM AHMAD/ FAZAL CLOTH MILLS 59/3 ABDALI ROAD MULTAN | 15117 | A-2c(06)T | 2018-02-19 | 27151170144100 | 145 | 88 | Preimer Energy (Pvt) Ltd. | Yes | DGL/349/2018 | Hassan Perwana | Installed | 2018-05-15 | Yes | 2018-06-01 | 88 | Connection Installed. Billing Started | -
16 | 16 | ALLIED ENGINEERING & SERVICES HAMID PUR KANORA SHER SHAH BY PASS MTN | 15138 | B2b(12)T | 2018-03-09 | 27151380994405 | 60 | 23.76 | AYK (Pvt) Ltd. | Yes | DGL/343/2018 | Basti Balail | Installed | 2018-10-18 | Yes | 2019-01-03 | 23.76 | Connection Installed. Billing Started | -
17 | 17 | AMIR AWAIS GHAURI BX-586/1 SADIQ COLONY BAHAWAL PUR | 15441 | A-2c(06)T | 2018-03-12 | 17154410396400 | 5 | 5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/348/2018 | N.Mahal(Cantt) | Installed | 2018-05-15 | Yes | 2018-06-16 | 5 | Connection Installed. Billing Started | -
18 | 18 | HAMEED RAZA S/O AMEER UD DIN AT HOUSE #2 HAMZA STREET BOSAN ROAD MULTAN | 15171 | A-1a(01) | 2018-04-03 | 13151717096201 | 6 | 5.2 | Preimer Energy (Pvt) Ltd. | Yes | DGL/358/2018 | Sabzazar | Installed | 2018-08-29 | Yes | 2018-09-24 | 5.2 | Connection Installed. Billing Started | -
19 | 19 | MUSHTAQ AHAMAD LAGHARI S-O MUHAMAMD AKBAR LAGHARI VILLAGE RAHIM ABAD SADIQABAD | 15645 | A-1a(01) | 2018-04-13 | New 28156451202700 and Old 05156451202700 | 12 | 12 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/463/2018 | RAHIM ABAD | Installed | 2018-09-14 | Yes | 2018-10-15 | 12 | Connection Installed. Billing Started | -
20 | 20 | FATIMA JAFAR W-O MUHAMMAD JAFAR CHOUDHARY, HOUSE NO. 383-C BUCH VILLAS MULTAN | 15175 | A-1b(03)T | 2018-07-10 | 15151758880903 | 5 | 3.06 | Preimer Energy (Pvt) Ltd. | Yes | DGL/526/2018 | Butch Villas | Installed | 2019-05-10 | - | - | 3.06 | Connection Installed. Billing will start in 05/2019. | Billing will start in 06/2019.MCO not forwarded by SDO office to RO office in 05/2019. LETTER SENT TO XEN FOR TIMELY BILLING.
21 | 21 | MUHAMMAD HUSSAIN TAHIR S-O MUKHTIAR AHMAD, 73-R BANGLOW ROAD HAROONABAD | 15821 | A-2c(06)T | 2018-01-30 | 27158210754604 | 160 | 30 | M/S Creative Electronics | Yes | DGL/561/2018 | Banglow Road | Installed | 2019-02-06 | Yes | 2019-03-04 | 30 | Connection Installed. Billing Started | -
22 | 22 | ALI SHAH S/O MUREED HUSSAIN SHAH MOHALLAH LAL SHAH MAKHDOOM RASHID MULTAN | 15127 | A-1a(01) | 2017-07-14 | 17151271746812 | 3 | 3.97 | POWER PROJECTS ORGNAIZATION | Yes | DGL/768/2018 | MAKHDOOM RASHID CITY | Installed | 2019-01-28 | Yes | 2019-04-27 | 3.97 | Connection Installed. Billing Started | -
23 | 23 | Ms. SOBIA AKRAM W/O MUHAMMAD AKRAM CHAK No. 131/10 R JAHANIAN | 15915 | New A-2c(06)T, Old A-2a(04) | 2018-08-31 | New 28159152947315 Old 20159152947315 | 5 | 5.12 | Preimer Energy (Pvt) Ltd. | Yes | DGL/608/2018 | PIR SADIQ SHAH | Installed | 2018-11-01 | Yes | 2018-12-03 | 5.12 | Connection Installed. Billing Started | -
24 | 24 | MUHAMMAD SARWAR S/O ABDUL MAJEED PUNJAB DEGREE COLLEGE AZIM ABAD BUREWALA | 15333 | A-2c(06)T | 2018-08-16 | 27153332500302 | 200 | 192 | Preimer Energy (Pvt) Ltd. | Yes | DGL/620/2018 | City-3 | Installed | 2018-10-08 | Yes | 2018-11-06 | 192 | Connection Installed. Billing Started |  | 12960
25 | 25 | AZEEM AKRAM S/O MUHAMMAD AKRAM SUPERIOR COLLEGE VEHARI ROAD HASIL PUR | 15452 | A-1b(03)T | 2018-09-28 | 28154520120216 | 13 | 19.44 | Preimer Energy (Pvt) Ltd. | Yes | DGL/691/2018 | VEHARI ROAD | Installed | 2019-02-21 | Yes | 2019-03-13 | 19.44 | Connection Installed. Billing Started | - | 9180
26 | 26 | MUHAMMAD JUNAID MASOOD HOUSE #66-M, WAPDA TOWN PHASE II MULTAN | 15175 | A-1b(03)T | 2018-10-07 | 17151753124630 | 5 | 7.15 | Sky Electric (PVT) Limited | Yes | DGL/1134/2018 | Wapda Town | Installed | 2019-04-04 | NO | - | 7.15 | Net Meters Installed on 04/04/2019 | Billing will start in 06/2019. MCO IS NOT FORWARDED BY SDIV YET TO RO OFFICE. LETTER SENT TO XEN FOR TIMELY BILLING. Billing is not started in 05/2019.
27 | 27 | SAIF ALI S/O CHOUDHARY SARDAR MUHAMMAD CHAK #106/DB YAZMAN, BAHAWALPUR | 15416 | A-1a(01)T | 2018-10-10 | 08154160646004 | 4.5 | 5.2 | Preimer Energy (Pvt) Ltd. | Yes | DGL/818/2018 | Tail Wala | Installed | 2019-03-06 | NO | - | 5.2 | Net Meters Installed on 06/03/2019 | Billing will start in 05/2019. MCO IS NOT FORWARDED BY SDIV YET TO RO OFFICE. REMINDER LETTER SENT TO XEN FOR TIMELY BILLING BUT NOT BILLED IN 04/2019 & 05/2019.
28 | 28 | MEHMOOD AHMAD SHEIKH S-O MUHAMMAD AHMAD SHEIKH NEAR REST HOUSE BAHAWALPUR | 15443 | A-1b(03)T | 2018-09-15 | NEW 04154430970800 OLD 18154430970800 | 6 | 10.24 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/732/2018 | GHANI PUR | Installed | 2019-02-25 | Yes | 2019-04-12 | 10.24 | Connection Installed. Billing Started. | -
29 | 29 | MUHAMMAD KHALID ALVI S/O MUHAMMAD SHARIF ALVI 43-A GULGASHT COLONY MULTAN | 15171 | A-1a(01)T | 2018-10-01 | 04151715528700 | 5 | 5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/769/2018 | USMANABAD | Installed | 2019-01-18 | Yes | 2019-02-13 | 5 | Connection Installed. Billing Started | - | 82896
30 | 30 | SAMINA MUJAHID W/O MUJAHID ALI AT 98-B BUCH VILLAS MULTAN | 15175 | A-1b(03)T | 2018-11-09 | 15151758884003 | 5 | 4.96 | Read Solar (PVT) Limited | Yes | DGL/819/2018 | Buch Villas | Installed | 2019-02-28 | Yes | 2019-05-25 | 4.96 | Connection Installed. Billing Started | -
31 | 33 | SHAZIA ZUBAIR W-O ZUBAIR BILAL AT 12-E,OFFICERS COLONY MULTAN | 15172 | A-1b(03)T | 2018-10-29 | 18151723471501 | 5 | 7.4 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/1052/2019 | Shams abad | Installed | 2019-05-03 | Yes | 2019-05-29 | 7.4 | Connection Installed. Billing Started. | Wrong peak units posted in billing of 05/2019. zero units posted in off peak. Informed to Mr. Tayyab MCC Multan.
32 | 35 | MALIK MUHAMMAD IBRAHEEM S-O WAHID BUX AT H#1341 BM WAHID ABAD COLONY OLD SHUJA ABAD ROAD MULTAN | 15132 | A-1b(03)T | 2018-10-24 | 03151322240300 | 13 | 18.36 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/837/2018 | Old Shujabad Road | Installed | 2019-03-25 | NO | - | 18.36 | Meter installed on 25/03/2019 | Billing will start in 05/2019. LETTER SENT TO XEN FOR TIMELY BILLING. BUT NOT BILLED IN 04/2019.
33 | 36 | AHMAD RAZA SHIRAZI S-O IMTIAZ HUSSAIN SHIRAZ, SHERAZI DERA MOZA KHAIR SHAH SAHIWAL | 15512 | A-1b(03)T | 2018-11-04 | 19155121582101 | 5 | 4.87 | Sky Electric (PVT) Limited | Yes | DGL/880/2018 | QUTAB SHAHANA | Installed | 2019-05-16 | NO | - | 4.87 | Meter installed on 16/05/2019 | Billing will start in 05/2019 Billing Cycle.
34 | 37 | MUHAMMAD KHAN S.O FAIZ ULLAH KHAN 55-A-3 ALTAF TOWN Multan | 15111 | A-1b(03)T | 2018-12-06 | 13151110928700 | 5 | 7.14 | Sky Electric (PVT) Limited | Yes | DGL/913/2019 | Allama Iqbal | Installed | 2019-02-28 | NO | - | 7.14 | Net Meters Installed on 28/02/2019 | Billing will start in 06/2019. MCO IS NOT FORWARDED BY SDIV YET TO RO OFFICE. LETTER SENT TO XEN FOR TIMELY BILLING. Billing is not started in 05/2019.
35 | 38 | DR SHER MUHAMMAD AWAN CHAH QASIM WALA LODHRAN | 15421 | A-1a(01) | 2018-12-06 | New16154210217400 Old 04154210217400 | 5 | 7.28 | Sky Electric (PVT) Limited | Yes | DGL/912/2019 | City Lodhran | Installed | 2019-02-19 | Yes | 2019-04-26 | 7.28 | Connection Installed. Billing Started | Wrong peak units posted in billing of 05/2019. zero units posted in off peak. Informed to Mr. Tayyab MCC Multan.
36 | 31 | MALIK NOOR ASGHAR BUCHA S/O MALIK NOOR MUHAMMAD BUCHA MAIN OFFICE BUILDING BUCH VILLAS BOSAN ROAD MULTAN | 15175 | A-2c(06)T | 2018-11-13 | 28151758887100 | 19 | 26.07 | Orient Energies (Pvt) Ltd. | Yes | DGL/911/2018 | Buch Villas | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 23/01/2019 | Demand notice for CTs and Box was paid by Consumer. Meter will be handed over to Subdivision & M&T soon by Consumer.
37 | 34 | SHAHID SARWAR CONTROL SHED CHAK # 69/12-L BUREWALA | 15331 | B2b(12)T | 2018-11-09 | 27153311095701 | 78 | 50.02 | Tesla Industries (Pvt) Limited. | Yes | DGL/910/2018 | 67/12L (Sultan S.Din) | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 23/01/2019 | CTs, Box and Meters were provided by Consumer and handed over to Subdivision. The meters will be sent soon by subdivision to M&T .
38 | 32 | Mr. RIZWAN GHAFOOR 1284-R WAPDA TOWN PHASE -II MULTAN | 15175 | A-1b(03)T | 2018-11-12 | 17151753121112 | 10 | 10.07 | HISEL POWER PAKISTAN (Pvt) LIMITED | Yes | DGL/914/2018 | Wapda Town | Installed | 2019-02-26 | Yes | 2019-04-27 | 10.07 | Connection Installed. Billing Started | -
39 | 39 | MUHAMMAD MUNEER S/O GHULAM QADIR KHAN. HOUSE# 1408 BLOCK-S NORTHERN BYPASS ROAD WAPDA TOWN PHASE-II MULTAN | 15175 | A-1b(03)T | 2018-09-01 | 15151753129100 | 5 | 4.96 | Read Solar (PVT) Limited | Yes | DGL/947/2019 | WAPDA TOWN | Installed | 2019-04-15 | No | - | 4.96 | Net Meters Installed on 15/04/2019 | Billing will start in 05/2019
40 | 40 | RIZWANA NAHEED W-O MIAN NAZEER AHMAD HOUSE# 1438BI TALEERI GARDEN ROAD VILLA LALA ZAR MUZAFFARGARH | 15711 | A-1a(01) | 2018-12-04 | 18157111255900 | 5 | 7.5 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/976/2019 | MUZAFFARGARH | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 30/01/2019 | Under Process for Net Meters. Meters are to be provided by consumer.
41 | 41 | ABDUL SAMMAD S-O MALIK FAZIL MUHAMMAD SHAD, (DISTRIBUTED GENERATOR), AT SADIQABAD #2 MULTAN | 15118 | A-1b(03)T | 2018-10-20 | 12151180980204 | 5 | 3.25 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/1029/2019 | NEW FAROOQ PURA | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 21/02/2019 | Under Process for Net Meters. Meters delivered to sdo on 30/04/2019
42 | 42 | MUHAMMAD SARWAR S-O MIAN ABDUL MAJEED C/O GHAZALI EDUCATIONAL 441-EB CANAL GARDEN HOUSE #368-369 BUREWALA | 15333 | A-1b(03)T | 2018-12-26 | 05153330482845 | 5 | 6.5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/1060/2019 | CITY-3 | Installed | 2019-04-03 | Yes | 2019-05-15 | 6.5 | Net Meters Installed on 03/04/2019 | Billing started on 15/05/2019
43 | 43 | Dr. OZAIR AHMAD RAFIQ S-O MUHAMMAD RAFIQ MIAN 441-EB CANAL GARDEN HOUSE #370-371 BUREWALA | 15333 | A-1b(03)T | 2018-12-26 | 05153330482858 | 5 | 5.85 | Preimer Energy (Pvt) Ltd. | Yes | DGL/1059/2019 | CITY-3 | Installed | 2019-04-03 | Yes | 2019-05-15 | 5.85 | Net Meters Installed on 03/04/2019 | Billing started on 15/05/2019
44 | 44 | MUHAMMAD SALEEM QURESHI S-O MUHAMMAD NASEEB QURESHI HOUSE# 7-8 ABDALI COLONY MULTAN | 15117 | A-1b(03)T | 2018-12-06 | 28151170084802 | 19 | 8 | Sky Electric (PVT) Limited | Yes | DGL/1083/2019 | Hassan Perwana | Installed | 2019-05-27 | - | - | 8 | Net Meters Installed on 27/05/2019 | Billing will start in 06/2019
45 | 45 | MUSARAT ULLAH QURESHI S-O ALLAH BACHAYA QURESHI POST OFFICE HARRAND BASTI PANAH ALI JAMPUR RAJANPUR | 15245 | A-1b(03)T | 2018-10-17 | 20152451123102 | 5 | 4.94 | Read Solar (PVT) Limited | Yes | DGL/1084/2019 | HARAND | Not Installed | - | - | - | - | DGL Issued on 07/03/2019 | Under Process for Net Meters
46 | 46 | TAHIRA HASSAN NAWAZ W-O RAI HASSAN NAWAZ KHAN MILK CHILLER CHAK # 110-12-L CHICHAWATNI | 15544 | B2b(12)T | 2018-12-21 | 27155442161111 | 38 | 7.28 | Sky Electric (PVT) Limited | Yes | DGL/1099/2019 | Kassowal | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 14/03/2019 | Under Process for Net Meters. DN Paid and meters will be delivered on Tuesday 21/05/2019.
47 | 47 | FAISAL SALMAN SHEIKH S-O MUHAMMAD AKRAM SHEIKH. SH DIN MUHAMMAD TRUST HOSPITAL 321-EB BUREWALA | 15335 | A-1a(01) | 2019-01-20 | 11153351601400 | 6 | 8.45 | Sky Electric (PVT) Limited | Yes | DGL/1107/2019 | Sarwar Shah | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 13/03/2019 | Under Process for Net Meters. Meters Delivered to sdo on 08/05/2019.
48 | 49 | SHAISTA FAROOQ W-O KHAWAJA FAROOQ AHMAD AT 1415-R WAPDA TOWN PHASE-II MULTAN | 15175 | A-1b(03)T | 2019-01-21 | 17151753119905 | 5 | 7.15 | Read Solar (PVT) Limited | Yes | DGL/1141/2019 | Wapda Town | Installed | 2019-03-20 | Yes | 2019-04-27 | 7.15 | Connection Installed. Billing Started | -
49 | 50 | M/S ASKARI CNG FILLING STATION NEAR TOLE #10 KLP ROAD SADIQABAD | 15641 | A-2c(06)T | 2019-01-24 | 27156410003201 | 134 | 8.96 | Solar Sigma Pvt Limited. | Yes | DGL/1186/2019 | Manthar | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 10/04/2019 | Under Process for Net Meters
50 | 04-ext | MLK NOOR ASGHAR BUCHA S/O MLK NOOR MUHAMMAD BUCHA THE GRAND COMMERCIAL BUILDING BUCH VILLAS H/S BOSAN ROAD MTN | 15175 | A-2c(06)T | 2018-11-13 | 27151758887001 | 857 | 114.37 | Orient Energies (Pvt) Ltd. | Yes | DGL/83-I/2017 | Buch Villas | Installed | 2018-01-17 | Yes | 2018-03-01 | 114.37 | Applied to NEPRA for extention of DGL license from 25.50 to 114.37 on 12/03/2019. License Issued on 17/04/2019 and old license cancelled. | Enhancement of DGL Sr. 4. The meter is already installed. | 114.37
51 | 51 | FAHAD KHALIL S-O PEERZADA KHALIL AHMED (C-O AHMAD RIZWAN SARFRAZ) CITY SCHOOL CAMPUS BAHAWALPUR | 15441 | A-3(A) (66) | 2019-02-28 | 27154410848302 | 158 | 46.2 | Solis Energy solutions (Pvt), Ltd. | Yes | DGL/1220/2019 | Hoot Wala | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 06/05/2019 | Under Process for Net Meters
52 | 48 | DR. SOHAIL MEHMOOD CH. S-O MUHAMMAD SADIQ MUSHTAQ 139-A HASHMI GARDEN BAHAWALPUR | 15441 | A-1b(03)T | 2018-12-21 | 20154413017500 | 7 | 10.24 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/1238/2019 | Hashmi Garden | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 12/04/2019 | NOC issued from XEN OP for self purchase of meter ON 16/04/2019. Under Process for installation of Net Meters.
53 | 52 | SAFIA FAROGH W-O FAROGH JALIL QUERSHI, HOUSE #6 A-2, MUHAMMAD HUSSAIN ROAD, MODEL TOWN -A BAHAWALPUR | 15441 | A-1a(01) | 2019-02-28 | 14154410057700 | 5 | 7.5 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/1278/2019 | NLC | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 25/04/2019 | NOC issued from XEN OP for self purchase of meter. Under Process for Net Meters.
54 | 53 | C/O AURENGZAIB FEROZ S/O IFTIKHAR FEROZ (C/O AHMAD RIZWAN SARFRAZ) AT M/S CITY SCHOOL NEAR DILWAR COLLEGE NORTHERN BYPASS MULTAN | 15173 | A-3(A) (66) | 2019-02-25 | 27151730365512 | 68 | 46.2 | Solis Energy solutions (Pvt), Ltd. | Yes | DGL/1382/2019 | DAHER | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 28/05/2019 | Applied to NEPRA on 03/04/2019. Under process for Net Meters.
55 | 55 | Mr. HAIDER AHSAN S-O AHSAN ZAHOOR HOUSE# 1052-7, AL- MUSTAFA COLONY LMQ ROAD MULTAN | 15171 | A-1a(01) | 2019-04-09 | 01151715041800 | 6 | 8.91 | Masco Energy Services (Pvt) Limited 17-Km Multan Road Lahore. | Yes | DGL/1387/2019 | GHULGASHT COLONY | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 30/05/2019 | Applied to NEPRA on 18/04/2019. Under process for Net Meters.
56 | 56 | AWAIS SHAFIQ S-O MUHAMMAD SHAFIQ HABIB PLAZA GT ROAD SAHIWAL | 15513 | A-2c(06)T | 2019-02-04 | 28155130407201 | 5 | 7.28 | Sky Electric (PVT) Limited | Yes | DGL/1383/2019 | Lahore Road | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 29/05/2019 | Applied to NEPRA on 19/04/2019. Under process for Net Meters.
57 | 57 | MALIK MUHAMMAD IBRAHEEM S-O WAHID BUX AT SHANGRILLA HOTEL SADAR BAZAR MULTAN CANTT. | 15111 | A-2c(06)T | 2019-01-16 | 27151111824400 | 155 | 30.24 | Read Solar (PVT) Limited | Yes | DGL/1356/2019 | Quaid-e-Azam Road | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 07/05/2019 | Under Process for Net Meters | 7360
58 | 58 | MR. MUHAMMAD AMJAD S-O GHULAM RASOOL AT 437-EB MODEL TOWN BUREWALA | 15334 | A-1a(01) | 2019-04-11 | 01153340075309 | 5 | 7.26 | M/s Power Highway | Yes | DGL/1384/2019 | City-II | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 29/05/2019 | Applied to NEPRA on 24/04/2019. Under process for Net Meters.
59 | 59 | Ms. RAHEELA BANO W-O KHAWAJA ATIQ UR REHMAN AT HOUSE #729-J SHAH RUKN E ALAM COLONY MULTAN | 15194 | A-1a(01) | 2019-04-11 | 19151941032800 | 5 | 7.36 | Feston Engineering Works Multan | Yes | DGL/1365/2019 | Gulberg Colony | Installed | 2019-05-21 | No | - | 7.36 | Net Meters Installed on 21/05/2019 | Billing will start in 05/2019.
60 | 60 | M/S ASKARIA CNG C/O IMRAN AHMAD S-O IQBAL AHMED NEAR AZIZ HOTEL CHOWK MULTAN | 15132 | A-2c(06)T | 2019-01-15 | 27151320319501 | 117 | 8.96 | Solar Sigma Pvt Limited. | Yes | NIL | Willayat abad | Not Installed | - | - | - | - | Applied to NEPRA on 30/04/2019
61 | 61 | Dr. MUHAMMAD ISMAIL BASHIR S-O BASHIR AHMAD AT NEW AL-SHIFA HOSPITAL, 42-B1, NUSRAT SHAHEED ROAD MUMTAZABAD MULTAN | 15121 | A-2c(06)T | 2019-04-27 | 31151211535300 | 5 | 5.88 | Feston EngIneering Works Multan | Yes | NIL | Ghee Mill | Not Installed | - | - | - | - | Applied to NEPRA on 30/04/2019
62 | 62 | Mr. ATTAULLAH WAHALA S-O REHMAT ALI HOUSE#160-AHASHMI GARDEN BAHAWALPUR | 15441 | A-1a(01) | 2019-04-01 | 20154412971800 | 4 | 5.76 | MAXELL POWER Pvt. Limited | Yes | NIL | Hashmi Garden | Not Installed | - | - | - | - | Applied to NEPRA on 07/05/2019
63 | 63 | Mr. TANVIR AHMAD S-O ASHIQ ALI C-O PRINCIPAL VOCATIONAL TRAINING SCHOOL NEAR TTC COLLEGE MULTAN | 15173 | A-3(A) (66) | 2019-04-03 | 27151736305900 | 35 | 41.6 | M/S HARDON Solar (Pvt), Ltd. | Yes | NIL | Ahmad | Not Installed | - | - | - | - | Applied to NEPRA on 07/05/2019
64 | 65 | Dr. ABDUL SHAKOOR S-O CHOUDHARY MUHAMMAD ALI HOUSE#183-A HASHMI GARDEN BAHAWALPUR | 15441 | A-1b(03)T | 2019-03-18 | 20154413012500 | 6 | 8.71 | MAXELL POWER Pvt. Limited | Yes | NIL | Hashmi Garden | Not Installed | - | - | - | - | Applied to NEPRA on 10/05/2019
65 | 66 | MR. SHAHID HAMEED CHOHAN HOUSE # 1419 BLOCK# S PHASE-II WAPDA TOWN MULTAN | 15175 | A-1b(03)T | 2019-05-08 | 17151753120316 | 6 | 8.96 | Feston Engineering Works Multan | Yes | NIL | Wapda Town | Not Installed | - | - | - | - | Applied to NEPRA on 10/05/2019
66 | 68 | M-S ASKARI CNG FILLING STATION ADDA KHAN PUR RAHIM YAR KHAN | 15611 | A-2c(06)T | 2019-01-22 | 27156110527203 | 134 | 8.96 | Solar Sigma Pvt Limited. | Yes | NIL | Allama Iqbal | Not Installed | - | - | - | - | APPLIED TO NEPRA ON 23/05/2019
67 | 69 | AHMAD HASSAN JAVED S-O JAVED ANWAR ABID AT HOUSE # 47-A HASHMI GARDEN BAHAWALPUR | 15441 | A-1a(01) | 2019-05-13 | 20154413030800 | 6 | 8.71 | MAXELL POWER Pvt. Limited | Yes | NIL | Hashmi Garden | Not Installed | - | - | - | - | APPLIED TO NEPRA ON 29/05/2019
68 | 70 | JAVED ANWAR ABID S-O SUBHAN ALI HOUSE # 4 DUBAI MAHAL ROAD BAHAWALPUR | 15441 | A-1a(01) | 2019-05-13 | 20154413031100 | 6 | 8.71 | MAXELL POWER Pvt. Limited | Yes | NIL | Hashmi Garden | Not Installed | - | - | - | - | APPLIED TO NEPRA ON 29/05/2019
[6 empty] | Total KW | 8853.5 | 1894.58 | [7 empty] | Total KW | 1508.03

## abstract
Progress of Net Metering (Dated: 10-06-2019)
Description | Detail | Capacity (KW) | Remarks
No. of Applications Received | 68 | 1894.58 | -
Generation licences applied to NEPRA | 68 | 1895 | -
Generation licences issued by NEPRA | 59 | 1788.33 | -
Generation licences pending at NEPRA | 9 | 106.67 | Applied To NEPRA in 04/2019 & 05/2019
No. of Connections Installed | 43 | 1508.03 | Billing of 34 Connections Started. 06# connections billing will start in 05/2019.3# connection billing will start in 06/2019.
No. of Applications/License Cancelled | 1 | 25.5 | 1 # license of 25.50 KW cancelled and new enhanced license of 114.37 KW issued on 17/04/2019
Applications Under Process | 16 | 254.8 | Meters will be installed after provision of meters by consumers and Tested by M&T.

## circle wise abstract
MEPCO Circlewise Progress of Net Metering on Roshan Pakistan App (Dated:10-06-2019)
Circles Names | Circles Codes | Total Sanctioned/ Connected Load (KW) | Total required load for Net Metering (KW) | Generation (KW) | Total Applications | Billing Started | Applied to NEPRA | Application/ License Cancelled | Total connections |  | Remarks
[9 empty] | Installed | Remaining
Multan | 15100 | 1813 | 634.98 | 451.48 | 33 | 16 | 4 | 1 | 24 | 8 | 4# Connections Applied To NEPRA For DG License 07/05/2019 & 10/05/2019. 3# applications are under process for Net Meters. 1 license is cancelled by NEPRA after issuance of new enhancement License. | 0.57
Dera Ghazi Khan | 15200 | 5 | 4.94 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1# Applied To NEPRA For DG License On 12/01/2019 License Issued on 07/03/2019. under Process for net meters.
Vehari | 15300 | 299 | 270.06 | 204.35 | 8 | 3 | 2 | 0 | 3 | 5 | 3#connections are under process for net meters. 2# applications are applied to NEPRA for Generation License.
Bahawalpur | 15400 | 236.5 | 145.99 | 50.16 | 11 | 5 | 2 | 0 | 5 | 6 | 2 connections Billing will start in 04/2019. 2# applications applied to NEPRA on 07/05/2019 & 10/05/2019 . 2# Connections are under Process for Net Meters.
Sahiwal | 15500 | 60 | 27.05 | 12.49 | 5 | 2 | 0 | 0 | 3 | 2 | 2# applications are under process for net meters.
Rahim Yar Khan | 15600 | 280 | 29.92 | 12 | 3 | 1 | 0 | 0 | 1 | 2 | 1# connection applied to NEPRA on 06/03/2019 and Generation License issued on 10/04/2019. under process for installation of meters. 1# connection applied to NEPRA on 23/05/2019.
Muzaffargarh | 15700 | 5 | 7.5 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Applied to NEPRA on 11/01/2019 for DG License and NEPRA Issued the License on 30/01/2019. Application is under Process for Net Meters.
Bahawal Nagar | 15800 | 642 | 334 | 334 | 2 | 2 | 0 | 0 | 2 | 0 | -
Khanewal | 15900 | 5512 | 440.12 | 440.12 | 4 | 4 | 0 | 0 | 4 | 0 | -
Total |  | 8852.5 | 1894.56 | 1504.6 | 68 | 33 | 8 | 1 | 42 | 25 | 06# connections billing will start in 05/2019. 03 # connections billing will start in 06/2019.

## tariff wise abstract
Progress of Net Metering Tariff wise Abstract (Dated: 10-06-2019)
Sr. No. | Type | Tariff | No. Of Connections | Load Kw | Meters Installed | Load Kw | Under Process
1 | Domestic | A-1a(01) | 15 | 108.81 | 7 | 46.01 | 3 # Connections are under process. 4# connections applied to NEPRA on 24/04/2019, 07/05/2019 & 29/05/2019.
|  | A-1b(03)T | 26 | 231.25 | 21 | 194.99 | 2# connections applied to NEPRA on 10/05/2019. 05# connections are under process for Net Meters.
2 | Commercial | A-2c(06)T | 16 | 599.46 | 9 | 503.07 | Billing of 9 connections started. 5# Connections are under process for net meters. 2#connections are applied to NEPRA on 30/04/2019 & 23/05/2019.
3 | Govt. Dept. Connections | A-3(66) | 2 | 6 | 2 | 6 | MEPCO Net Metering Cell & Zila Council Sahiwal connections Installed. Billing started.
4 | School Connections | A-3(66) (A) | 3 | 134 | 0 | 0 | City School System Bahawalpur & Multan.one connection of Vocaional College Multan. Applied to NEPRA on 07/05/2019. 1#License of Bahawalpur is issued on 06/05/2019. 1# application is under process for Net-Meters
5 | Industrial | B2b(12)T | 4 | 385.06 | 2 | 327.8 | 2# connections under process for Net Meter. | 7.5
6 |  | B3(14)T | 2 | 430 | 2 | 430 | Connection Installed. Billing started.
|  | Total | 68 | 1894.58 | 43 | 1507.87 | Billing of 34 Connections Started. 03 connections billing will start in 06/2019.

## year wise abstract
YEARWISE NET METERING APPLICATION(S) INFORMATION/STATUS
COMPANY NAME: MEPCO | [8 empty] | Dated: | 10-06-2019
Description | 2016 |  | 2017 |  | 2018 |  | 2019 |  | TOTAL Connections | TOTAL Load | Pending connections 2018/2019 | Pending Load 2018/2019 | REMARKS
| Connections | Load For Net Metering (KW) | Connections | Load For Net Metering (KW) | Connections | Load For Net Metering (KW) | Connections | Load For Net Metering (KW)
Number of Connections applied to MEPCO | 5 | 39.12 | 10 | 868 | 20 | 465.1 | 33 | 522.36 | 68 | 1894.58 | - | - | 68 applications received.
Number of Generation Licenses applied to NEPRA | 0 | 0 | 13 | 600.12 | 22 | 772.1 | 33 | 522.4 | 68 | 1894.58 | - | - | 68 applications applied to NEPRA.
Number of Generation Licenses issued by NEPRA | 0 | 0 | 13 | 600.12 | 21 | 826.34 | 25 | 361.87 | 59 | 1788.33 | 8 | 80.75 | Applied to NEPRA in 04/2019 & 05/2019. 59 applications Licenses issued by NEPRA. |  | 3.25 |  |  | 215.88
Applications/ License Cancelled | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 25.5 | 1 | 25.5 | - | - | 1 # DGL cancelled due to enhancement in License and NEPRA has issued new License on 17/04/2019. | 35.91
Number of Connections Installed | 1 | 3 | 5 | 67 | 15 | 1165.2 | 22 | 272.83 | 43 | 1508.03 | 16 | 280.3 | 12 connections meters will be installed after provision of meters by consumers and Tested from M&T. |  |  | 192 | 902.32
Number of Connections Where Billing Started | 1 | 3 | 4 | 62 | 16 | 1170.2 | 13 | 206.73 | 34 | 1441.93 | 9 | 66.1 | 6# Connections of 45.75 KW billing will start in 05/2019. 3# Connection of 20.35 KW billing will start in 06/2019. |  |  | 192 | 192
710.32
65.26
[12 empty] | 8.24 | 13.2
58.11
45.75

## dg licences sheet
NEPRA Generation Licences for MEPCO Net Metering Consumers Till Dated: 10-06-2019
Sr.# | Date | Expiry Date | Generation Licence No. And Application No. And Name
1 | 2017-02-02 | 2020-02-01 | Generation Licence No. DGL/48/2017 - Licence Application No. LAN-48 - MEPCO Head Quarters, Khanewal Road, Multan
2 | 2017-03-28 | 2020-03-27 | Generation Licence No. DGL/76/2017 - Licence Application No. LAN-76 - Mr. Khawaja M. Younus, Multan
3 | 2017-04-04 | 03/04/2020. This license cancelled and new 114.37 kw License issued on 17/04/2019 | Generation Licence No. DGL/83/2017 - Licence Application No. LAN-83 Mr. Malik Noor Asghar Bucha, Multan
4 | 2017-04-04 | 2020-04-03 | Generation Licence No. DGL/79/2017 - Licence Application No. LAN-79 - Mr. Khawaja M. Ilyas, Masood Spinning Mills, Kabirwala
5 | 2017-04-04 | 2020-04-03 | Generation Licence No. DGL/77/2017 - Licence Application No. LAN-77 - Mr. Khawaja M. Younus, Mahmood Textile Mills, Multan
6 | 2017-04-04 | 2020-04-03 | Generation Licence No. DGL/80/2017 - Licence Application No. LAN-80 - Mr. Asif Iqbal, Sahiwal
7 | 2017-04-13 | 2020-04-12 | Generation Licence No. DGL/78/2017 - Licence Application No. LAN-78 - Mr. Khawaja Muhammad Younus, Multan
8 | 2017-05-17 | 2020-05-16 | Generation Licence No. DGL/74/2017 - Licence Application No. LAN-74 - Zila Council, Iqbal Road, Sahiwal
9 | 2017-05-22 | 2020-05-21 | Generation Licence No. DGL/75/2017 - Licence Application No. LAN-75 - Office of the Deputy Commissioner, Lodhran
10 | 2017-06-13 | 2020-06-12 | Generation Licence No. DGL/107/2017 - Licence Application No. LAN-107 - Mrs. Sajida Khalid, Multan
11 | 2017-07-10 | 2020-07-09 | Generation Licence No. DGL/106/2017 Licence Application No. LAN-106 Unilever Khanewal Tea Factory, Khanewal
12 | 2017-07-12 | 2020-07-11 | Generation Licence No. DGL/128/2017 Licence Application No. LAN-128 Mr. Naimat Ullah Qureshi, Multan
13 | 2017-07-12 | 2020-07-11 | Generation Licence No. DGL/117/2017 Licence Application No. LAN-117 Mr. Muhammad Arshad Nadeem, Multan
14 | 2018-04-16 | 2025-04-15 | Generation Licence No. DGL/343/2018 Licence Application No. LAN-343 Allied Engineering & Services, Multan
15 | 2018-04-16 | 2025-04-15 | Generation Licence No. DGL/348/2018 Licence Application No. LAN-348 Mr. Amir Owais Ghauri, Bahawalpur
16 | 2018-04-20 | 2025-04-19 | Generation Licence No. DGL/349/2018 Licence Application No. LAN-349 Fazal Cloth Mills Limited, Multan
17 | 2018-04-24 | 2025-04-23 | Generation Licence No. DGL/358/2018 Licence Application No. LAN-358 Mr. Hameed Raza, Multan
18 | 2018-07-06 | 2025-07-05 | Generation Licence No. DGL/463/2018 Licence Application No. LAN-463 Mr. Mushtaq Ahmad Laghari Village Rahimabad Tehsil Sadiqabad
19 | 2018-07-12 | 2025-07-11 | Generation Licence No. DGL/478/2018 - Licence Application No. LAN-478 - Mr. Shabbir Ahmad, Eastern Products (Private) Limited, MEPCO
20 | 2018-08-16 | 2025-08-15 | Generation Licence No. DGL/526/2018 - Licence Application No. LAN-526 - Ms. Fatima Jafar, MEPCO
21 | 2018-09-03 | 2025-09-02 | Generation Licence No. DGL/561/2018 - Licence Application No. LAN-561 -Mr. Muhammad Hussain Tahir, MEPCO
22 | 2018-09-25 | 2025-09-24 | Generation Licence No. DGL/608/2018 - Licence Application No. LAN-608 - Ms. Sobia Akram, MEPCO
23 | 2018-09-25 | 2025-09-24 | Generation Licence No. DGL/620/2018 - Licence Application No. LAN-620 - Mr. Muhammad Sarwar, for 192.0 KW photo voltaic solar based distributed generation facility located at Punjab Degree College, Azim Abad, Burewala
24 | 2018-10-24 | 2025-10-23 | Generation Licence No. DGL/691/2018 - Licence Application No. LAN-691 GL Azeem Akram, for 19.44 KW photo voltaic solar based distributed generation facility located at Superior College, Vehari Road, Hasilpur
25 | 2018-11-19 | 2025-11-18 | Generation Licence No. DGL/732/2018 - Licence Application No. LAN-732 - Mr. Sheikh Mahmood, MEPCO
26 | 2018-11-20 | 2025-11-19 | Generation Licence No. DGL/769/2018 - Licence Application No. LAN-769 - Mr. Muhammad Khalid Alvi, MEPCO
27 | 2018-11-23 | 2025-11-22 | Generation Licence No. DGL/768/2018 - Licence Application No. LAN-768 - Mr. Ali Shah, MEPCO
28 | 2018-12-19 | 2025-12-18 | Generation Licence No. DGL/819/2018 Licence Application No. LAN-819 Ms. Samina Mujahid, MEPCO
29 | 2018-12-27 | 2025-12-26 | Generation Licence No. DGL/818/2018 Licence Application No. LAN-818 Ch. Saif Ali, MEPCO
30 | 2018-12-27 | 2025-12-26 | Generation Licence No. DGL/837/2018 Licence Application No. LAN-837 Malik Muhammad Ibraheem, MEPCO
31 | 2019-01-21 | 2026-01-20 | Generation Licence No. DGL/911/2019 - Licence Application No. LAN-911 - Mr. Malik Noor Asghar Bucha, MEPCO
32 | 2019-01-21 | 2026-01-20 | Generation Licence No. DGL/910/2019 - Licence Application No. LAN-910 - Mr. Shahid Sarwar, MEPCO
33 | 2019-01-18 | 2026-01-17 | Generation Licence No. DGL/880/2019 - Licence Application No. LAN-880 - Mr. Ahmad Raza Sherazi, MEPCO
34 | 2019-01-23 | 2026-01-22 | Generation Licence No. DGL/914/2019 Licence Application No. LAN-914 Mr. Rizwan Ghafoor, MEPCO
35 | 2019-01-23 | 2026-01-22 | Generation Licence No. DGL/913/2019 Licence Application No. LAN-913 Mr. Muhammad Khan Sadozai, MEPCO
36 | 2019-01-23 | 2026-01-22 | Generation Licence No. DGL/912/2019 Licence Application No. LAN-912 Malik Sher Muhammad Awan, MEPCO
37 | 2019-01-25 | 2026-01-24 | Generation Licence No. DGL/947/2019 Licence Application No. LAN-947 Mr. Muhammad Muneer Anjum, MEPCO
38 | 2019-01-30 | 2026-01-29 | Generation Licence No. DGL/976/2019 - Licence Application No. LAN-976 - Ms. Rizwana Naheed, MEPCO
39 | 2019-01-21 | 2026-01-20 | Generation Licence No. DGL/1029/2019 Licence Application No. LAN-1029 Mr. Abdul Samad, MEPCO
40 | 2019-02-26 | 2026-02-25 | Generation Licence No. DGL/1052/2019 Licence Application No. LAN-1052 Ms. Shazia Zubair, MEPCO
41 | 2019-02-26 | 2026-02-25 | Generation Licence No. DGL/1059/2019 Licence Application No. LAN-1059 Dr. Ozair Ahmad, MEPCO
42 | 2019-02-26 | 2026-02-25 | Generation Licence No. DGL/1060/2019 Licence Application No. LAN-1060 Mr. Muhammad Sarwar, MEPCO
43 | 2019-03-07 | 2026-03-06 | Generation Licence No. DGL/1083/2019 Licence Application No. LAN-1083 Mr. Muhammad Saleem Qureshi, MEPCO
44 | 2019-03-07 | 2026-03-06 | Generation Licence No. DGL/1084/2019 Licence Application No. LAN-1084 Mr. Musarat Ullah Qureshi, MEPCO
45 | 2019-03-13 | 2026-03-12 | Generation Licence No. DGL/1107/2019 - Licence Application No. LAN-1107 - Mr. Faisal Salman Sheikh, MEPCO
46 | 2019-03-14 | 2026-03-13 | Generation Licence No. DGL/1099/2019 - Licence Application No. LAN-1099 - Ms. Tahira Hassan Nawaz, MEPCO
47 | 2019-03-15 | 2026-03-14 | Generation Licence No. DGL/1134/2019 - Licence Application No. LAN-1134 - Mr. M. Junaid Masood, MEPCO
48 | 2019-03-21 | 2026-03-20 | Generation Licence No. DGL/1141/2019 - Licence Application No. LAN-1141 - Ms. Shaista Farooq, MEPCO
49 | 2019-04-10 | 2026-04-09 | Generation Licence No. DGL/1186/2019 - Licence Application No. LAN-1186 - M/s Askari CNG Filling Station, MEPCO
50 | 2019-04-12 | 2026-04-11 | Generation Licence No. DGL/1238/2019 - Licence Application No. LAN-1238 - Dr. Sohail Mehmood Ch.MEPCO
51 | 2019-04-17 | 2026-04-16 | Generation Licence No. DGL/83-I/2019 - Licence Application No. LAN-83-I - Malik Noor Asghar Bucha, MEPCO
52 | 2019-04-25 | 2026-04-24 | Generation Licence No. DGL/1278/2019 - Licence Application No. LAN-1278 - Ms. Safia Farogh, MEPCO
53 | 2019-05-06 | 2026-05-05 | Generation Licence No. DGL/1220/2019 - Licence Application No. LAN-1220 - Mr. Fahad Khalil, MEPCO
54 | 2019-05-07 | 2026-05-06 | Generation Licence No. DGL/1365/2019 - Licence Application No. LAN-1365 - Ms. Raheela Bano, MEPCO
55 | 2019-05-07 | 2026-05-06 | Generation Licence No. DGL/1356/2019 - Licence Application No. LAN-1356 - Malik Muhammad Ibraheem, MEPCO
56 | 2019-05-28 | 2026-05-27 | Generation Licence No. DGL/1382/2019 - Licence Application No. LAN-1382 - M/s City School (Private) Limited, MEPCO
57 | 2019-05-29 | 2026-05-28 | Generation Licence No. DGL/1383/2019 - Licence Application No. LAN-1383 - Mr. Awais Shafiq, MEPCO
58 | 2019-05-29 | 2026-05-28 | Generation Licence No. DGL/1384/2019 - Licence Application No. LAN-1384 - Mr. Muhammad Amjad, MEPCO
59 | 2019-05-30 | 2026-05-29 | Generation Licence No. DGL/1387/2019 - Licence Application No. LAN-1387 - Mr. Haider Ahsan, MEPCO

## installer abstract
ABSTRACT OF INSTALLERS OF NET METERING CONNECTIONS IN MEPCO (10-06-2019)
Sr. No. | Installer | No. Of Consumers
1 | Ayk (Pvt) Ltd. | 1
2 | Catkin Engineering Sale And Services (Pvt) Ltd. | 8
3 | Hisel Power Pakistan (Pvt) Limited | 1
4 | M/S Creative Electronics | 3
5 | M/s Power Highway 5th Floor, Venus Plaza, 7 Egerton Road, Lahore. Tel: 042-36370380-81 Email: info@powerhighway.net | 1
6 | Masco Energy Services (Pvt) Limited 17-Km Multan Road Lahore Ph#92-42-37511851-54, 37511694-97 | 1
7 | Orient Energies (Pvt) Ltd. | 3
8 | Pak Friends Enterprises | 1
9 | Power Projects Organization | 1
10 | Premier Energy (Pvt) Ltd. | 15
11 | Read Solar (Pvt) Limited | 5
12 | Reap | 1
13 | Reon | 2
14 | Royal Energy Sultan Electronics | 1
15 | Sky Electric (Pvt) Limited | 8
16 | Solar Master | 1
17 | Solar Sigma Pvt Limited. Solar Sigma Centre Pwd Society, Main Express Highway Islamabad | 3
18 | Solar Tech. | 1
19 | Solis Energy solutions (Pvt), Ltd. C-18, Block-4, Clifton, Karachi Pakistan, Tel. 021-35876531 | 2
20 | Tesla Industries (Pvt) Limited. | 1
21 | FESTON engineering Works, Office #3 Clock Plaza Chowk Ghanta Ghar, Multan. Cell#0345-6005551 | 3
22 | MAXELL POWER Pvt. Limited, G-12 & 13 Younas Centre, 30 Hall Road, Lahore Tel#042-111-441-441 | 4
23 | M/S HARDON Solar (Pvt), Ltd., at Office#326, Johar Avenue Canal Road Lahore, Tel. 042-35240526 | 1
| Total | 68

## installer detail
LIST OF INSTALLERS OF NET METERING CONNECTIONS IN MEPCO Dated : 10/06/2019
Sr. No. | License # | Consumer name and address | Installer | No. Of Connections
1 |  | ALLIED ENGINEERING & SERVICES HAMID PUR KANORA SHER SHAH BY PASS MTN | AYK (Pvt) Ltd. | 1
2 |  | MUSHTAQ AHAMAD LAGHARI S-O MUHAMAMD AKBAR LAGHARI VILLAGE RAHIM ABAD SADIQABAD | Catkin Engineering Sale and Services (Pvt) Ltd. | 8
3 |  | MEHMOOD AHMAD SHEIKH S-O MUHAMMAD AHMAD SHEIKH NEAR REST HOUSE BAHAWALPUR | Catkin Engineering Sale and Services (Pvt) Ltd.
4 |  | SHAHZIA ZUBAIR W-O ZUBAIR BILAL AT 12-E,OFFICERS COLONY MULTAN | Catkin Engineering Sale and Services (Pvt) Ltd.
5 |  | MALIK MUHAMMAD IBRAHEEM S-O WAHID BUX AT H#1341 BM WAHID ABAD COLONY OLD SHUJA ABAD ROAD MULTAN | Catkin Engineering Sale and Services (Pvt) Ltd.
6 |  | RIZWANA NAHEED W-O MIAN NAZEER AHMAD HOUSE# 1438BI TALEERI GARDEN ROAD VILLA LALA ZAR MUZAFFARGARH | Catkin Engineering Sale and Services (Pvt) Ltd.
7 |  | ABDUL SAMMAD S-O MALIK FAZIL MUHAMMAD SHAD, (DISTRIBUTED GENERATOR), AT SADIQABAD #2 MULTAN | Catkin Engineering Sale and Services (Pvt) Ltd.
8 |  | DR. SUHAIL MEHMOOD CH. S-O MUHAMMAD SADIQ MUSHTAQ 139-A HASHMI GARDEN BAHAWALPUR | Catkin Engineering Sale and Services (Pvt) Ltd.
9 |  | SAFIA FAROGH W-O FAROGH JALIL QUERSHI, HOUSE #6 A-2, MUHAMMAD HUSSAIN ROAD, MODEL TOWN -A BAHAWALPUR | Catkin Engineering Sale and Services (Pvt) Ltd.
10 |  | Mr. RIZWAN GHAFOOR 1284-R WAPDA TOWN PHASE -II MULTAN | HISEL POWER PAKISTAN (Pvt) LIMITED | 1 | SAFIA FAROGH W-O FAROGH JALIL QUERSHI, HOUSE #6 A-2, MUHAMMAD HUSSAIN ROAD, MODEL TOWN -A BAHAWALPUR | Catkin Engineering Sale and Services (Pvt) Ltd. | 1
11 |  | OFFICE BUILDING TEHSILDAR LODHRAN NEAR MARKET COMMITTEE OFFICE LODHRAN | M/S Creative Electronics | 3
12 |  | KHALID NAZEER CMISSIONER SAHIWAL | M/S Creative Electronics
13 |  | MUHAMMAD HUSSAIN TAHIR S-O MUKHTIAR AHMAD, 73-R BANGLOW ROAD HAROONABAD | M/S Creative Electronics
14 |  | MALIK NOOR ASGHAR BUCHA S/O MLK NOOR MUHAMMAD BUCHA THE GRAND COMMERCIAL BUILDING BUCH VILLAS H/S BOSAN ROAD MTN | Orient Energies (Pvt) Ltd. | 3
15 |  | MALIK NOOR ASGHAR BUCHA S/O MALIK NOOR MUHAMMAD BUCHA MAIN OFFICE BUILDING BUCH VILLAS BOSAN ROAD MULTAN | Orient Energies (Pvt) Ltd.
16 |  | MALIK NOOR ASGHAR BUCHA S/O MLK NOOR MUHAMMAD BUCHA THE GRAND COMMERCIAL BUILDING BUCH VILLAS H/S BOSAN ROAD MTN | Orient Energies (Pvt) Ltd.
17 |  | SAJIDA KHALID W/O CH.KHALID LATIF PUNJAB SMALL INDUSTRIES MTN | Pak Friends Enterprises | 1
18 |  | ALI SHAH S/O MUREED HUSSAIN SHAH MOHALLAH LAL SHAH MAKHDOOM RASHID MULTAN | POWER PROJECTS ORGNAIZATION | 1
19 |  | KHAWAJA MUHAMMAD YOUNIS S-O KHAWAJA MUHAMMAD MASOOD FATIMA MODEL SCHOOL MULTAN ROAD K.WALA | Preimer Energy (Pvt) Ltd. | 15
20 |  | KH MUHAMMAD YOUNIS S-O MUHAMMAD MASOOD 13 B OFFICER CLY MULTAN | Preimer Energy (Pvt) Ltd.
21 |  | MEHMOOD TEXTILE MILLS LTD MULTAN LOHARI GATE MULTAN CITY | Preimer Energy (Pvt) Ltd.
22 |  | Kh M YOUNAS M/S MASOOD SPINNING MILLS UNIT NO.02 04-KM MULTAN ROAD KABIR WALA | Preimer Energy (Pvt) Ltd.
23 |  | NASEEM AHMAD/ FAZAL CLOTH MILLS 59/3 ABDALI ROAD MULTAN | Preimer Energy (Pvt) Ltd.
24 |  | AMIR AWAIS GHAURI BX-586/1 SADIQ COLONY BAHAWAL PUR | Preimer Energy (Pvt) Ltd.
25 |  | HAMEED RAZA S/O AMEER UD DIN AT HOUSE #2 HAMZA STREET BOSAN ROAD MULTAN | Preimer Energy (Pvt) Ltd.
26 |  | FATIMA JAFAR W-O MUHAMMAD JAFAR CHOUDHARY, HOUSE NO. 383-C BUCH VILLAS MULTAN | Preimer Energy (Pvt) Ltd.
27 |  | SOBIA AKRAM W/O MUHAMMAD AKRAM CHAK No. 131/10 R JAHANIAN | Preimer Energy (Pvt) Ltd.
28 |  | MUHAMMAD SARWAR S/O ABDUL MAJEED PUNJAB DEGREE COLLEGE AZIM ABAD BUREWALA | Preimer Energy (Pvt) Ltd.
29 |  | AZEEM AKRAM S/O MUHAMMAD AKRAM SUPERIOR COLLEGE VEHARI ROAD HASIL PUR | Preimer Energy (Pvt) Ltd.
30 |  | SAIF ALI S/O CHOUDHARY SARDAR MUHAMMAD CHAK #106/DB YAZMAN, BAHAWALPUR | Preimer Energy (Pvt) Ltd.
31 |  | MUHAMMAD KHALID ALVI S/O MUHAMMAD SHARIF ALVI 43-A GULGASHT COLONY MULTAN | Preimer Energy (Pvt) Ltd.
32 |  | MUHAMMAD SARWAR S-O MIAN ABDUL MAJEED 441-EB CANAL GARDEN HOUSE #368-369 BUREWALA | Preimer Energy (Pvt) Ltd.
33 |  | Dr. OZAIR AHMAD RAFIQ S-O MUHAMMAD RAFIQ MIAN 441-EB CANAL GARDEN HOUSE #370-371 BUREWALA | Preimer Energy (Pvt) Ltd.
34 |  | SAMINA MUJAHID W/O MUJAHID ALI AT 98-B BUCH VILLAS MULTAN | Read Solar (PVT) Limited | 5
35 |  | MUHAMMAD MUNEER S/O GHULAM QADIR KHAN. HOUSE# 1408 BLOCK-S NORTHERN BYPASS ROAD WAPDA TOWN PHASE-II MULTAN | Read Solar (PVT) Limited
36 |  | MUSARAT ULLAH QURESHI S-O ALLAH BACHAYA QURESHI POST OFFICE HARRAND BASTI PANAH ALI JAMPUR RAJANPUR | Read Solar (PVT) Limited
37 |  | SHAISTA FAROOQ W-O KHAWAJA FAROOQ AHMAD AT 1415-R WAPDA TOWN PHASE-II MULTAN | Read Solar (PVT) Limited
38 |  | MALIK MUHAMMAD IBRAHEEM S-O WAHID BUX AT SHANGRILLA HOTEL SADAR BAZAR MULTAN CANTT. | Read Solar (PVT) Limited
39 |  | XEN CIVIL MEPCO | Reap | 1
40 |  | UNILEVER PAKISTAN LIMITED TEA FACTORY CHAK NO.88-A10R KHANEWAL | REON | 2
41 |  | SHABBIR AHMAD S-O MIRAJ DIN EASTREN PRODUCTS-VITAL TEA LTD QAZI WALA HAROON ABAD | REON
42 |  | Asif Iqbal SM Bashir Agencies | Royal Energy Sultan Electronics | 1
43 |  | MUHAMMAD JUNAID MASOOD HOUSE #66-M, WAPDA TOWN PHASE II MULTAN | Sky Electric (PVT) Limited 33-A, sector XX, Khayaban-e-Iqbal, Phase 3, DHA Lahore. +92 42 3713 2675-78,+92 303 410 2010 | 8
44 |  | AHMAD RAZA SHIRAZI S-O IMTIAZ HUSSAIN SHIRAZ, SHERAZI DERA MOZA KHAIR SHAH SAHIWAL | Sky Electric (PVT) Limited
45 |  | MUHAMMAD KHAN S.O FAIZ ULLAH KHAN 55-A-3 ALTAF TOWN Multan | Sky Electric (PVT) Limited
46 |  | DR SHER MUHAMMAD AWAN CHAH QASIM WALA LODHRAN | Sky Electric (PVT) Limited
47 |  | MUHAMMAD SALEEM QURESHI S-O MMUHAMMAD NASEEB QURESHI HOUSE# 7-8 ABDALI COLONY MULTAN | Sky Electric (PVT) Limited
48 |  | TAHIRA HASSAN NAWAZ W-O RAI HASSAN NAWAZ KHAN MILK CHILLER CHAK # 110-12-L CHICHAWATNI | Sky Electric (PVT) Limited
49 |  | FAISAL SALMAN SHEIKH S-O MUHAMMAD AKRAM SHEIKH. SH DIN MUHAMMAD TRUST HOSPITAL 321-EB BUREWALA | Sky Electric (PVT) Limited
50 |  | AWAIS SHAFIQ S-O MUHAMMAD SHAFIQ HABIB PLAZA GT ROAD SAHIWAL | Sky Electric (PVT) Limited
51 |  | NAIMAT ULLAH S.O ALLAH BACHAYA QURESHI 259-N WAPDA TOWN-11 MTN | SOLAR MASTER | 1
52 |  | M/S ASKARI CNG FILLING STATION NEAR TOLE #10 KLP ROAD SADIQABAD | Solar Sigma Pvt Limited. Solar Sigma Centre PWD Society, Main Express Highway Islamabad | 3
53 |  | M/S ASKARIA CNG C/O IMRAN AHMAD S-O IQBAL AHMED NEAR AZIZ HOTEL CHOWK MULTAN | Solar Sigma Pvt Limited. Solar Sigma Centre PWD Society, Main Express Highway Islamabad
54 |  | M-S ASKARI CNG FILLING STATION ADDA KHAN PUR RAHIM YAR KHAN | Solar Sigma Pvt Limited. Solar Sigma Centre PWD Society, Main Express Highway Islamabad
55 |  | MUHAMMAD ARSHAD NADEEM S-O MHAMMAD ASHIQ ST NO 1 MADINA ABAD CLY MULTAN | Solar Tech. | 1
56 |  | FAHAD KHALIL S-O PEERZADA KHALIL AHMED (C-O AHMAD RIZWAN SARFRAZ) CITY SCHOOL CAMPUS BAHAWALPUR | Solis Energy solutions (Pvt), Ltd. C-18, Block-4, Clifton, Karachi Pakistan, Tel. 021-35876531 | 2
57 |  | SHAHID SARWAR CONTROL SHED CHAK # 69/12-L BUREWALA | Tesla Industries (Pvt) Limited. | 1
58 |  | Mr. HAIDER USMAN S-O AHSAN ZAHOOR HOUSE# 1052-7, AL- MUSTAFA COLONY LMQ ROAD MULTAN | Masco Energy Services (Pvt) Limited 17-Km Multan Road Lahore Ph#92-42-37511851-54, 37511694-97 | 1
59 | B/3/1/Net Met/PH/17/45 | MR. MUHAMMAD AMJAD S-O GHULAM RASOOL AT 437-EB MODEL TOWN BUREWALA | M/s Power Highway 5th Floor, Venus Plaza, 7 Egerton Road, Lahore. Tel: 042-36370380-81 Email: info@powerhighway.net | 1
60 |  | RAHEELA BANO W-O KHAWAJA ATIQ UR REHMAN AT HOUSE #729-J SHAH RUKN E ALAM COLONY MULTAN | FESTON Engineering Works, Office #3 Clock Plaza Chowk Ghanta Ghar, Multan. Cell#0345-6005551 | 3
61 |  | Dr. MUHAMMAD ISMAIL BASHIR S-O BASHIR AHMAD AT NEW AL-SHIFA HOSPITAL, 42-B1, NUSRAT SHAHEED ROAD MUMTAZABAD MULTAN | FESTON Engineering Works, Office #3 Clock Plaza Chowk Ghanta Ghar, Multan. Cell#0345-6005551
62 |  | MR. SHAHID HAMEED CHOHAN HOUSE # 1419 BLOCK# S PHASE-II WAPDA TOWN MULTAN | FESTON Engineering Works, Office #3 Clock Plaza Chowk Ghanta Ghar, Multan. Cell#0345-6005551
63 |  | Mr. ATTAULLAH WAHALA S-O REHMAT ALI HOUSE#160-AHASHMI GARDEN BAHAWALPUR | MAXELL POWER Pvt. Limited, G-12 & 13 Younas Centre, 30 Hall Road, Lahore Tel#042-111-441-441 | 4
64 |  | Dr. ABDUL SHAKOOR S-O CHOUDHARY MUHAMMAD ALI HOUSE#183-A HASHMI GARDEN BAHAWALPUR | MAXELL POWER Pvt. Limited, G-12 & 13 Younas Centre, 30 Hall Road, Lahore Tel#042-111-441-441
65 |  | AHMAD HASSAN JAVED S-O JAVED ANWAR ABID AT HOUSE # 47-A HASHMI GARDEN BAHAWALPUR | MAXELL POWER Pvt. Limited, G-12 & 13 Younas Centre, 30 Hall Road, Lahore Tel#042-111-441-441
66 |  | JAVED ANWAR ABID S-O SUBHAN ALI HOUSE # 4 DUBAI MAHAL ROAD BAHAWALPUR | MAXELL POWER Pvt. Limited, G-12 & 13 Younas Centre, 30 Hall Road, Lahore Tel#042-111-441-441
67 |  | Mr. TANVIR AHMAD S-O ASHIQ ALI C-O PRINCIPAL VOCATIONAL TRAINING SCHOOL NEAR TTC COLLEGE MULTAN | M/S HARDON Solar (Pvt), Ltd., at Office#326, Johar Avenue Canal Road Lahore, Tel. 042-35240526 | 1
|  |  | Total | 68

## Sheet2
Sub Division Code | Tariff | Application Date | Reference No. | Sanctioned Load | Required Load for Net Metering | Name of Installer | Applied To NEPRA (Yes or No) | Generation Licence | Feeder | Installation Status (Installed or Uninstalled) | Installation Date | Billing Started (Yes or No) | Billing Start Date | Generation (KW) | Remarks | Current Position (What is Present Status i.e. either with installer or SDO or NEPRA etc.)
15171 | A-1a(01) | 2018-04-03 | 13151717096201 | 6 | 5.2 | Preimer Energy (Pvt) Ltd. | Yes | DGL/358/2018 | Sabzazar | Installed | 2018-08-29 | Yes | 2018-09-24 | 5.2
15645 | A-1a(01) | 2018-04-13 | New 28156451202700 and Old 05156451202700 | 12 | 12 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/463/2018 | RAHIM ABAD | Installed | 2018-09-14 | Yes | 2018-10-15 | 12
15127 | A-1a(01) | 2017-07-14 | 17151271746812 | 3 | 3.97 | POWER PROJECTS ORGNAIZATION | Yes | DGL/768/2018 | MAKHDOOM RASHID CITY | Installed | 2019-01-28 | NO | - | 3.97
15421 | A-1a(01) | 2018-12-06 | New 161542110217400 Old 04154210217400 | 5 | 7.28 | Sky Electric (PVT) Limited | Yes | DGL/912/2019 | City Lodhran | Installed | 2019-02-19 | NO | - | 7.28
15335 | A-1a(01) | 2019-01-20 | 11153351601400 | 6 | 8.45 | Sky Electric (PVT) Limited | Yes | DGL/1107/2019 | Sarwar Shah | Not Installed | - | - | - | -
15441 | A-1a(01) | 2019-02-28 | 14154410057700 | 5 | 7.5 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | NIL | NLC | Not Installed | - | - | - | -
15416 | A-1a(01)T | 2018-10-10 | 08154160646004 | 4.5 | 5.2 | Preimer Energy (Pvt) Ltd. | Yes | DGL/818/2018 | Tail Wala | Installed | 2019-03-06 | NO | - | 5.2
15171 | A-1a(01)T | 2018-10-01 | 04151715528700 | 5 | 5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/769/2018 | USMANABAD | Installed | 2019-01-18 | Yes | 2019-02-13 | 5
15711 | A-1a(01) | 2018-12-04 | 18157111255900 | 5 | 7.5 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/976/2019 | MUZAFFARGARH | Not Installed | - | - | - | -
|  | 9 |  | 51.5 | 62.1 | [8 empty] | 38.65
15421 | A-1b(03)T | 2016-06-18 | New 15154210167800 Old 03154210167800 | 11 | 3 | M/S Creative Electronics | Yes | DGL/75/2017 | City Lodhran | Installed | 2018-01-06 | Yes | 2018-01-10 | 3
15132 | A-1b(03)T | 2017-01-06 | 13151322030405 | 5 | 10 | Solar Tech. | Yes | DGL/117/2017 | Timber Market | Installed | 2017-12-17 | Yes | 2017-12-21 | 10
15175 | A-1b(03)T | 2017-01-26 | 17151753136101 | 5 | 10 | Pak Friends Enterprises | Yes | DGL/107/2017 | Darbar Peer Akbar Shah | Installed | 2017-12-19 | Yes | 2017-12-20 | 10
15921 | A-1b(03)T | 2017-03-03 | 28159210647407 | 6 | 5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/76/2017 | Spinning Unit-2 | Installed | 2017-12-21 | Yes | 2018-02-13 | 5
15172 | A-1b(03)T | 2017-03-03 | 18151723474200 | 12 | 32 | Preimer Energy (Pvt) Ltd. | Yes | DGL/78/2017 | Eid Gah Road | Installed | 2017-12-19 | Yes | 2017-12-27 | 32
15452 | A-1b(03)T | 2018-09-28 | 28154520120216 | 13 | 19.44 | Preimer Energy (Pvt) Ltd. | Yes | DGL/691/2018 | VEHARI ROAD | Installed | 2019-02-21 | Yes | 2019-03-13 | 19.44
15175 | A-1b(03)T | 2018-10-07 | 17151753124630 | 5 | 7.15 | Sky Electric (PVT) Limited | Yes | DGL/1134/2018 | Wapda Town | Not Installed | - | - | - | -
15443 | A-1b(03)T | 2018-09-15 | 18154430970800 | 6 | 10.24 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/732/2018 | GHANI PUR | Installed | 2019-02-25 | NO | - | 10.24
15175 | A-1b(03)T | 2018-11-09 | 15151758884003 | 5 | 4.96 | Read Solar (PVT) Limited | Yes | DGL/819/2018 | Buch Villas | Installed | 2019-02-28 | NO | - | 4.96
15172 | A-1b(03)T | 2018-10-29 | 18151723471501 | 5 | 7.4 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/1052/2019 | Shams abad | Not Installed | - | - | - | -
15132 | A-1b(03)T | 2018-10-24 | 03151322240300 | 13 | 18.36 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/837/2018 | Old Shujabad Road | Installed | 2019-03-25 | - | - | 18.36
15512 | A-1b(03)T | 2018-11-04 | 19155121582101 | 5 | 4.87 | Sky Electric (PVT) Limited | Yes | DGL/880/2018 | QUTAB SHAHANA | Not Installed | - | - | - | -
15111 | A-1b(03)T | 2018-12-06 | 13151110928700 | 5 | 7.14 | Sky Electric (PVT) Limited | Yes | DGL/913/2019 | Allama Iqbal | Installed | 2019-02-28 | NO | - | 7.14
15175 | A-1b(03)T | 2018-11-12 | 17151753121112 | 10 | 10.07 | HISEL POWER PAKISTAN (Pvt) LIMITED | Yes | DGL/914/2018 | Wapda Town | Installed | 2019-02-26 | - | - | 10.07
15175 | A-1b(03)T | 2018-09-01 | 15151753129100 | 5 | 4.96 | Read Solar (PVT) Limited | Yes | DGL/947/2019 | WAPDA TOWN | Not Installed | - | - | - | -
15118 | A-1b(03)T | 2018-10-20 | 12151180980204 | 5 | 3.25 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/1029/2019 | NEW FAROOQ PURA | Not Installed | - | - | - | -
15333 | A-1b(03)T | 2018-12-26 | 05153330482845 | 5 | 6.5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/1060/2019 | CITY-3 | Installed | 2019-04-03 | - | - | 6.5
15333 | A-1b(03)T | 2018-12-26 | 05153330482858 | 5 | 5.85 | Preimer Energy (Pvt) Ltd. | Yes | DGL/1059/2019 | CITY-3 | Not Installed | 2019-04-03 | - | - | 5.85
15117 | A-1b(03)T | 2018-12-06 | 28151170084802 | 19 | 8 | Sky Electric (PVT) Limited | Yes | DGL/1083/2019 | Hassan Perwana | Not Installed | - | - | - | -
15245 | A-1b(03)T | 2018-10-17 | 20152451123102 | 5 | 4.94 | Read Solar (PVT) Limited | Yes | DGL/1084/2019 | HARAND | Not Installed | - | - | - | -
15175 | A-1b(03)T | 2019-01-21 | 17151753119905 | 5 | 7.15 | Read Solar (PVT) Limited | Yes | DGL/1141/2019 | Wapda Town | Not Installed | - | - | - | -
15441 | A-1b(03)T | 2018-12-21 | 20154413017500 | 7 | 10.24 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | NIL | Hashmi Garden | Not Installed | - | - | - | -
15175 | A-1b(03)T | 2017-06-01 | 17151753132415 | 5 | 10 | SOLAR MASTER | Yes | DGL/128/2017 | Wapda Town | Installed | 2017-12-19 | YES | 2017-12-20 | 10
15175 | A-1b(03)T | 2018-07-10 | 15151758880903 | 5 | 3.06 | Preimer Energy (Pvt) Ltd. | Yes | DGL/526/2018 | Butch Villas | Not Installed | - | - | - | -
|  | 24 |  | 172 | 213.58 | [8 empty] | 152.56
15175 | A-2c(06)T | 2016-09-12 | 27151758887001 | 857 | 25.5 | Orient Energies (Pvt) Ltd. | Yes | DGL/83/2017 | Buch Villas | Installed | 2018-01-17 | Yes | 2018-03-01 | 25.5
15113 | A-2c(06)T | 2017-03-03 | 27151130721400 | 200 | 64 | Preimer Energy (Pvt) Ltd. | Yes | DGL/77/2017 | Abdali Road | Installed | 2018-01-29 | Yes | 2018-02-03 | 64
15333 | A-2c(06)T | 2018-08-16 | 27153332500302 | 200 | 192 | Preimer Energy (Pvt) Ltd. | Yes | DGL/620/2018 | City-3 | Installed | 2018-10-08 | Yes | 2018-11-06 | 192
15175 | A-2c(06)T | 2018-11-13 | 28151758887100 | 19 | 26.07 | Orient Energies (Pvt) Ltd. | Yes | DGL/911/2018 | Buch Villas | Not Installed | - | - | - | -
15641 | A-2c(06)T | 2019-01-24 | 27156410003201 | 134 | 8.96 | Solar Sigma Pvt Limited. | Yes | NIL | Manthar | - | - | - | - | -
15175 | A-2c(06)T | 2018-11-13 | 27151758887001 | 0 | 88.87 | Orient Energies (Pvt) Ltd. | Yes | NIL | Buch Villas | - | - | - | - | -
15117 | A-2c(06)T | 2018-02-19 | 27151170144100 | 145 | 88 | Preimer Energy (Pvt) Ltd. | Yes | DGL/349/2018 | Hassan Perwana | Installed | 2018-05-15 | Yes | 2018-06-01 | 88
15441 | A-2c(06)T | 2018-03-12 | 17154410396400 | 5 | 5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/348/2018 | N.Mahal(Cantt) | Installed | 2018-05-15 | Yes | 2018-06-16 | 5
15821 | A-2c(06)T | 2018-01-30 | 27158210754604 | 160 | 30 | M/S Creative Electronics | Yes | DGL/561/2018 | Banglow Road | Installed | 2019-02-06 | Yes | 2019-03-04 | 30
15915 | A-2c(06)T | 2018-08-31 | New 28159152947315 Old 20159152947315 | 5 | 5.12 | Preimer Energy (Pvt) Ltd. | Yes | DGL/608/2018 | PIR SADIQ SHAH | Installed | 2018-11-01 | Yes | 2018-12-03 | 5.12
15514 | A-2c(06)T | 2016-12-15 | New 28155140275502 and old 03155140275502 | 5 | 4.62 | Royal Energy Sultan Electronics | Yes | DGL/80/2017 | College Road | Installed | 2018-01-18 | Yes | 2018-02-12 | 4.62
|  | 11 |  | 1730 | 538.14 | [8 empty] | 414.24
15173 | A-3(66) | 2016-07-12 | 13151734972100 | 12 | 3 | Reap | Yes | DGL/48/2017 | Wapda Colony | Installed | 2016-07-28 | Yes | 2016-08-23 | 3
15512 | A-3(66) | 2016-08-12 | 12155121038000 | 7 | 3 | M/S Creative Electronics | Yes | DGL/74/2017 | Civil Lines | Installed | 2018-05-10 | Yes | 2018-06-20 | 3
|  | 2 |  | 19 | 6 | [8 empty] | 6 | 0
15441 | A-3(A) (66) | 2019-02-28 | 27154410848302 | 158 | 46.2 | Solis Energy solutions (Pvt), Ltd. | Yes | NIL | Hoot Wala | Not Installed | - | - | - | -
15173 | A-3(A) (66) | 2019-02-25 | 27151730365512 | 68 | 46.2 | Solis Energy solutions (Pvt), Ltd. | Yes | NIL | DAHER | Not Installed | - | - | - | -
|  | 2 |  | 226 | 92.4 | [8 empty] | 0
15821 | B2b(12)T | 2017-12-26 | 27158210966702 | 482 | 304 | REON | Yes | DGL/478/2018 | KHATAN | Installed | 2018-11-03 | Yes | 2019-01-03 | 304
15138 | B2b(12)T | 2018-03-09 | 27151380994405 | 60 | 23.76 | AYK (Pvt) Ltd. | Yes | DGL/343/2018 | Basti Balail | Installed | 2018-10-18 | Yes | 2019-01-03 | 23.76
15331 | B2b(12)T | 2018-11-09 | 27153311095701 | 78 | 50.02 | Tesla Industries (Pvt) Limited. | Yes | DGL/910/2018 | 67/12L (Sultan S.Din) | Not Installed | - | - | - | -
15544 | B2b(12)T | 2018-12-21 | 27155442161111 | 38 | 7.28 | Sky Electric (PVT) Limited | Yes | DGL/1099/2019 | Kassowal | Not Installed | - | - | - | -
|  | 4 |  | 658 | 385.06 | [8 empty] | 327.76
15913 | B3(14)T | 2017-02-08 | 27159132372500 | 503 | 110 | Reon | Yes | DGL/106/2017 | UNILEVER TEA FACTORY | Installed | 2018-01-16 | Yes | 2018-02-03 | 110
15921 | B3(14)T | 2017-03-03 | 30159212533901 | 4999 | 320 | Preimer Energy (Pvt) Ltd. | Yes | DGL/79/2017 | Masood Spinning Unit-2 | Installed | 2018-01-31 | Yes | 2018-02-03 | 320
|  | 2 |  | 5502 | 430 | [8 empty] | 430
|  | 54 |  | 8358.5 | 1727.28 | [8 empty] | 1369.21

## Sheet3
Application No. | Name of Applicant | Sub Division Code | Tariff | Application Date | Reference No. | Sanctioned Load | Required Load for Net Metering | Name of Installer | Applied To NEPRA (Yes or No) | Generation Licence | Feeder | Installation Status (Installed or Uninstalled) | Installation Date | Billing Started (Yes or No) | Billing Start Date | Generation (KW) | Remarks | Current Position (What is Present Status i.e. either with installer or SDO or NEPRA etc.)
37 | MUHAMMAD KHAN S.O FAIZ ULLAH KHAN 55-A-3 ALTAF TOWN Multan | 15111 | A-1b(03)T | 2018-12-06 | 13151110928700 | 5 | 7.14 | Sky Electric (PVT) Limited | Yes | DGL/913/2019 | Allama Iqbal | Installed | 2019-02-28 | NO | - | 7.14 | Net Meters Installed on 28/02/2019 | Billing will start in 04/2019. MCO IS NOT FORWARDED BY SDIV YET TO RO OFFICE. LETTER SENT TO XEN FOR TIMELY BILLING.
11 | MEHMOOD TEXTILE MILLS LTD MULTAN LOHARI GATE MULTAN CITY | 15113 | A-2c(06)T | 2017-03-03 | 27151130721400 | 200 | 64 | Preimer Energy (Pvt) Ltd. | Yes | DGL/77/2017 | Abdali Road | Installed | 2018-01-29 | Yes | 2018-02-03 | 64 | Connection Installed. Billing Started | -
15 | NASEEM AHMAD/ FAZAL CLOTH MILLS 59/3 ABDALI ROAD MULTAN | 15117 | A-2c(06)T | 2018-02-19 | 27151170144100 | 145 | 88 | Preimer Energy (Pvt) Ltd. | Yes | DGL/349/2018 | Hassan Perwana | Installed | 2018-05-15 | Yes | 2018-06-01 | 88 | Connection Installed. Billing Started | -
44 | MUHAMMAD SALEEM QURESHI S-O MMUHAMMAD NASEEB QURESHI HOUSE# 7-8 ABDALI COLONY MULTAN | 15117 | A-1b(03)T | 2018-12-06 | 28151170084802 | 19 | 8 | Sky Electric (PVT) Limited | Yes | DGL/1083/2019 | Hassan Perwana | Not Installed | - | - | - | - | DGL Issued on 07/03/2019 | Under Process for Net Meters
41 | ABDUL SAMMAD S-O MALIK FAZIL MUHAMMAD SHAD, (DISTRIBUTED GENERATOR), AT SADIQABAD #2 MULTAN | 15118 | A-1b(03)T | 2018-10-20 | 12151180980204 | 5 | 3.25 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/1029/2019 | NEW FAROOQ PURA | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 21/02/2019 | Under Process for Net Meters
22 | ALI SHAH S/O MUREED HUSSAIN SHAH MOHALLAH LAL SHAH MAKHDOOM RASHID MULTAN | 15127 | A-1a(01) | 2017-07-14 | 17151271746812 | 3 | 3.97 | POWER PROJECTS ORGNAIZATION | Yes | DGL/768/2018 | MAKHDOOM RASHID CITY | Installed | 2019-01-28 | NO | - | 3.97 | Net Meters installed on 28/01/2019 | Billing will start in 04/2019. MCO IS NOT FORWARDED BY SDIV YET TO RO OFFICE. LETTER SENT TO XEN FOR TIMELY BILLING.
6 | MUHAMMAD ARSHAD NADEEM S-O MHAMMAD ASHIQ ST NO 1 MADINA ABAD CLY MTN MULTAN | 15132 | A-1b(03)T | 2017-01-06 | 13151322030405 | 5 | 10 | Solar Tech. | Yes | DGL/117/2017 | Timber Market | Installed | 2017-12-17 | Yes | 2017-12-21 | 10 | Connection Installed. Billing Started | -
35 | MALIK MUHAMMAD IBRAHEEM S-O WAHID BUX AT H#1341 BM WAHID ABAD COLONY OLD SHUJA ABAD ROAD MULTAN | 15132 | A-1b(03)T | 2018-10-24 | 03151322240300 | 13 | 18.36 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/837/2018 | Old Shujabad Road | Installed | 2019-03-25 | - | - | 18.36 | Meter installed on 25/03/2019 | Billing will start in 04/2019. LETTER SENT TO XEN FOR TIMELY BILLING.
16 | ALLIED ENGINEERING & SERVICES HAMID PUR KANORA SHER SHAH BY PASS MTN | 15138 | B2b(12)T | 2018-03-09 | 27151380994405 | 60 | 23.76 | AYK (Pvt) Ltd. | Yes | DGL/343/2018 | Basti Balail | Installed | 2018-10-18 | Yes | 2019-01-03 | 23.76 | Connection Installed. Billing Started | -
18 | HAMEED RAZA S/O AMEER UD DIN AT HOUSE #2 HAMZA STREET BOSAN ROAD MULTAN | 15171 | A-1a(01) | 2018-04-03 | 13151717096201 | 6 | 5.2 | Preimer Energy (Pvt) Ltd. | Yes | DGL/358/2018 | Sabzazar | Installed | 2018-08-29 | Yes | 2018-09-24 | 5.2 | Connection Installed. Billing Started | -
29 | MUHAMMAD KHALID ALVI S/O MUHAMMAD SHARIF ALVI 43-A GULGASHT COLONY MULTAN | 15171 | A-1a(01)T | 2018-10-01 | 04151715528700 | 5 | 5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/769/2018 | USMANABAD | Installed | 2019-01-18 | Yes | 2019-02-13 | 5 | Connection Installed. Billing Started | -
55 | Mr. HAIDER USMAN S-O AHSAN ZAHOOR HOUSE# 1052-7, AL- MUSTAFA COLONY LMQ ROAD MULTAN | 15171 | A-2c(06)T | 2019-04-09 | 01151715041800 | 6 | 8.91 | Masco Energy Services (Pvt) Limited 17-Km Multan Road Lahore. | Yes | NIL | GHULGASHT COLONY | Not Installed | - | - | - | - | Applied to NEPRA on 18/04/2019 | -
10 | KH MUHAMMAD YOUNIS S-O MUHAMMAD MASOOD 13 B OFFICER CLY MULTAN | 15172 | A-1b(03)T | 2017-03-03 | 18151723474200 | 12 | 32 | Preimer Energy (Pvt) Ltd. | Yes | DGL/78/2017 | Eid Gah Road | Installed | 2017-12-19 | Yes | 2017-12-27 | 32 | Connection Installed. Billing Started | -
33 | SHAZIA ZUBAIR W-O ZUBAIR BILAL AT 12-E,OFFICERS COLONY MULTAN | 15172 | A-1b(03)T | 2018-10-29 | 18151723471501 | 5 | 7.4 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/1052/2019 | Shams abad | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 26/02/2019 | Under Process for Net Meters
2 | XEN CIVIL MEPCO | 15173 | A-3(66) | 2016-07-12 | 13151734972100 | 12 | 3 | Reap | Yes | DGL/48/2017 | Wapda Colony | Installed | 2016-07-28 | Yes | 2016-08-23 | 3 | Connection Installed. Billing Started | -
53 | C/O AURENGZAIB FEROZ S/O IFTIKHAR FEROZ (C/O AHMAD RIZWAN SARFRAZ) AT M/S CITY SCHOOL NEAR DILWAR COLLEGE NORTHERN BYPASS MULTAN | 15173 | A-3(A) (66) | 2019-02-25 | 27151730365512 | 68 | 46.2 | Solis Energy solutions (Pvt), Ltd. | Yes | NIL | DAHER | Not Installed | - | - | - | - | Applied to NEPRA on 03/04/2019 | -
4 | MALIK NOOR ASGHAR BUCHA S/O MLK NOOR MUHAMMAD BUCHA THE GRAND COMMERCIAL BUILDING BUCH VILLAS H/S BOSAN ROAD MTN | 15175 | A-2c(06)T | 2016-09-12 | 27151758887001 | 857 | 25.5 | Orient Energies (Pvt) Ltd. | Yes | DGL/83/2017 | Buch Villas | Installed | 2018-01-17 | Yes | 2018-03-01 | 25.5 | Connection Installed. Billing Started | -
7 | SAJIDA KHALID W/O CH.KHALID LATIF PUNJAB SMALL INDUSTRIES MTN | 15175 | A-1b(03)T | 2017-01-26 | 17151753136101 | 5 | 10 | Pak Friends Enterprises | Yes | DGL/107/2017 | Darbar Peer Akbar Shah | Installed | 2017-12-19 | Yes | 2017-12-20 | 10 | Connection Installed. Billing Started | -
14 | NAIMAT ULLAH S.O ALLAH BACHAYA QURESHI 259-N WAPDA TOWN-11 MTN | 15175 | A-1b(03)T | 2017-06-01 | 17151753132415 | 5 | 10 | SOLAR MASTER | Yes | DGL/128/2017 | Wapda Town | Installed | 2017-12-19 | YES | 2017-12-20 | 10 | Connection Installed. Billing Started | -
20 | FATIMA JAFAR W-O MUHAMMAD JAFAR CHOUDHARY, HOUSE NO. 383-C BUCH VILLAS MULTAN | 15175 | A-1b(03)T | 2018-07-10 | 15151758880903 | 5 | 3.06 | Preimer Energy (Pvt) Ltd. | Yes | DGL/526/2018 | Butch Villas | Not Installed | - | - | - | - | Generation License Issued by NEPRA. DN for bidirectional meters issued to Consumer and paid by Consumer. Demand of Meter sent to Manager (MM) | Under Process for Net Meters
26 | MUHAMMAD JUNAID MASOOD HOUSE #66-M, WAPDA TOWN PHASE II MULTAN | 15175 | A-1b(03)T | 2018-10-07 | 17151753124630 | 5 | 7.15 | Sky Electric (PVT) Limited | Yes | DGL/1134/2018 | Wapda Town | Installed | 2019-04-04 | NO | - | 7.15 | Net Meters Installed on 04/04/2019 | Billing will start in 04/2019
30 | SAMINA MUJAHID W/O MUJAHID ALI AT 98-B BUCH VILLAS MULTAN | 15175 | A-1b(03)T | 2018-11-09 | 15151758884003 | 5 | 4.96 | Read Solar (PVT) Limited | Yes | DGL/819/2018 | Buch Villas | Installed | 2019-02-28 | NO | - | 4.96 | Net Meters installed on 28/02/2019 | Billing will start in 04/2019. MCO IS NOT FORWARDED BY SDIV YET TO RO OFFICE. LETTER SENT TO XEN FOR TIMELY BILLING.
31 | MALIK NOOR ASGHAR BUCHA S/O MALIK NOOR MUHAMMAD BUCHA MAIN OFFICE BUILDING BUCH VILLAS BOSAN ROAD MULTAN | 15175 | A-2c(06)T | 2018-11-13 | 28151758887100 | 19 | 26.07 | Orient Energies (Pvt) Ltd. | Yes | DGL/911/2018 | Buch Villas | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 23/01/2019 | Demand notice for CTs and Box was paid by Consumer. Meter will be handed over to Subdivision & M&T soon by Consumer.
32 | Mr. RIZWAN GHAFOOR 1284-R WAPDA TOWN PHASE -II MULTAN | 15175 | A-1b(03)T | 2018-11-12 | 17151753121112 | 10 | 10.07 | HISEL POWER PAKISTAN (Pvt) LIMITED | Yes | DGL/914/2018 | Wapda Town | Installed | 2019-02-26 | - | - | 10.07 | Net Meters Installed on 26/02/2019 | Billing will start in 04/2019. MCO IS NOT FORWARDED BY SDIV YET TO RO OFFICE. LETTER SENT TO XEN FOR TIMELY BILLING.
39 | MUHAMMAD MUNEER S/O GHULAM QADIR KHAN. HOUSE# 1408 BLOCK-S NORTHERN BYPASS ROAD WAPDA TOWN PHASE-II MULTAN | 15175 | A-1b(03)T | 2018-09-01 | 15151753129100 | 5 | 4.96 | Read Solar (PVT) Limited | Yes | DGL/947/2019 | WAPDA TOWN | Installed | 2019-04-15 | - | - | 4.96 | Net Meters Installed on 15/04/2019 | Billing will start in 04/2019
49 | SHAISTA FAROOQ W-O KHAWAJA FAROOQ AHMAD AT 1415-R WAPDA TOWN PHASE-II MULTAN | 15175 | A-1b(03)T | 2019-01-21 | 17151753119905 | 5 | 7.15 | Read Solar (PVT) Limited | Yes | DGL/1141/2019 | Wapda Town | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 21/03/2019 | Under Process for Net Meters
34 | MLK NOOR ASGHAR BUCHA S/O MLK NOOR MUHAMMAD BUCHA THE GRAND COMMERCIAL BUILDING BUCH VILLAS H/S BOSAN ROAD MTN | 15175 | A-2c(06)T | 2018-11-13 | 27151758887001 | 857 | 88.87 | Orient Energies (Pvt) Ltd. | Yes | NIL | Buch Villas | - | - | - | - | - | Applied to NEPRA for extention of DGL license from 25.50 to 114.37 on 12/03/2019 | Enhancement of DGL Sr. 4. The meter is already installed.
[6 empty] | 1490 | 531.98
45 | MUSARAT ULLAH QURESHI S-O ALLAH BACHAYA QURESHI POST OFFICE HARRAND BASTI PANAH ALI JAMPUR RAJANPUR | 15245 | A-1b(03)T | 2018-10-17 | 20152451123102 | 5 | 4.94 | Read Solar (PVT) Limited | Yes | DGL/1084/2019 | HARAND | Not Installed | - | - | - | - | DGL Issued on 07/03/2019 | Under Process for Net Meters
34 | SHAHID SARWAR CONTROL SHED CHAK # 69/12-L BUREWALA | 15331 | B2b(12)T | 2018-11-09 | 27153311095701 | 78 | 50.02 | Tesla Industries (Pvt) Limited. | Yes | DGL/910/2018 | 67/12L (Sultan S.Din) | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 23/01/2019 | CTs, Box and Meters were provided by Consumer and handed over to Subdivision. The meters will be sent to M&T soon by subdivision.
24 | MUHAMMAD SARWAR S/O ABDUL MAJEED PUNJAB DEGREE COLLEGE AZIM ABAD BUREWALA | 15333 | A-2c(06)T | 2018-08-16 | 27153332500302 | 200 | 192 | Preimer Energy (Pvt) Ltd. | Yes | DGL/620/2018 | City-3 | Installed | 2018-10-08 | Yes | 2018-11-06 | 192 | Connection Installed. Billing Started
42 | MUHAMMAD SARWAR S-O MIAN ABDUL MAJEED 441-EB CANAL GARDEN HOUSE #368-369 BUREWALA | 15333 | A-1b(03)T | 2018-12-26 | 05153330482845 | 5 | 6.5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/1060/2019 | CITY-3 | Installed | 2019-04-03 | - | - | 6.5 | Net Meters Installed on 03/04/2019 | Billing will start in 04/2019. LETTER SENT TO XEN FOR TIMELY BILLING.
43 | Dr. OZAIR AHMAD RAFIQ S-O MUHAMMAD RAFIQ MIAN 441-EB CANAL GARDEN HOUSE #370-371 BUREWALA | 15333 | A-1b(03)T | 2018-12-26 | 05153330482858 | 5 | 5.85 | Preimer Energy (Pvt) Ltd. | Yes | DGL/1059/2019 | CITY-3 | Installed | 2019-04-03 | - | - | 5.85 | Net Meters Installed on 03/04/2019 | Billing will start in 04/2019. LETTER SENT TO XEN FOR TIMELY BILLING.
47 | FAISAL SALMAN SHEIKH S-O MUHAMMAD AKRAM SHEIKH. SH DIN MUHAMMAD TRUST HOSPITAL 321-EB BUREWALA | 15335 | A-1a(01) | 2019-01-20 | 11153351601400 | 6 | 8.45 | Sky Electric (PVT) Limited | Yes | DGL/1107/2019 | Sarwar Shah | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 13/03/2019 | Under Process for Net Meters
27 | SAIF ALI S/O CHOUDHARY SARDAR MUHAMMAD CHAK #106/DB YAZMAN, BAHAWALPUR | 15416 | A-1a(01)T | 2018-10-10 | 08154160646004 | 4.5 | 5.2 | Preimer Energy (Pvt) Ltd. | Yes | DGL/818/2018 | Tail Wala | Installed | 2019-03-06 | NO | - | 5.2 | Net Meters Installed on 06/03/2019 | Billing will start in 04/2019. MCO IS NOT FORWARDED BY SDIV YET TO RO OFFICE. LETTER SENT TO XEN FOR TIMELY BILLING.
1 | OFFICE BUILDING TEHSILDAR LODHRAN NEAR MARKET COMMITTEE OFFICE LODHRAN | 15421 | A-1b(03)T | 2016-06-18 | New 15154210167800 Old 03154210167800 | 11 | 3 | M/S Creative Electronics | Yes | DGL/75/2017 | City Lodhran | Installed | 2018-01-06 | Yes | 2018-01-10 | 3 | Connection Installed. Billing Started | -
38 | DR SHER MUHAMMAD AWAN CHAH QASIM WALA LODHRAN | 15421 | A-1a(01) | 2018-12-06 | New16154210217400 Old 04154210217400 | 5 | 7.28 | Sky Electric (PVT) Limited | Yes | DGL/912/2019 | City Lodhran | Installed | 2019-02-19 | NO | - | 7.28 | Net Meters Installed on 19/02/2019 | Billing will start in 04/2019. MCO IS NOT FORWARDED BY SDIV YET TO RO OFFICE. LETTER SENT TO XEN FOR TIMELY BILLING.
17 | AMIR AWAIS GHAURI BX-586/1 SADIQ COLONY BAHAWAL PUR | 15441 | A-2c(06)T | 2018-03-12 | 17154410396400 | 5 | 5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/348/2018 | N.Mahal(Cantt) | Installed | 2018-05-15 | Yes | 2018-06-16 | 5 | Connection Installed. Billing Started | -
51 | FAHAD KHALIL S-O PEERZADA KHALIL AHMED (C-O AHMAD RIZWAN SARFRAZ) CITY SCHOOL CAMPUS BAHAWALPUR | 15441 | A-3(A) (66) | 2019-02-28 | 27154410848302 | 158 | 46.2 | Solis Energy solutions (Pvt), Ltd. | Yes | NIL | Hoot Wala | Not Installed | - | - | - | - | Applied to NEPRA for DGL license on 12/03/2019 | -
48 | DR. SOHAIL MEHMOOD CH. S-O MUHAMMAD SADIQ MUSHTAQ 139-A HASHMI GARDEN BAHAWALPUR | 15441 | A-1b(03)T | 2018-12-21 | 20154413017500 | 7 | 10.24 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/1238/2019 | Hashmi Garden | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 12/04/2019 | NOC issued from XEN OP for self purchase of meter ON 16/04/2019. Under Process for installation of Net Meters.
48 | SAFIA FAROGH W-O FAROGH JALIL QUERSHI, HOUSE #6 A-2, MUHAMMAD HUSSAIN ROAD, MODEL TOWN -A BAHAWALPUR | 15441 | A-1a(01) | 2019-02-28 | 14154410057700 | 5 | 7.5 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | NIL | NLC | Not Installed | - | - | - | - | Applied to NEPRA on 28/03/2019 | -
28 | MEHMOOD AHMAD SHEIKH S-O MUHAMMAD AHMAD SHEIKH NEAR REST HOUSE BAHAWALPUR | 15443 | A-1b(03)T | 2018-09-15 | NEW 04154430970800 OLD 18154430970800 | 6 | 10.24 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/732/2018 | GHANI PUR | Installed | 2019-02-25 | NO | - | 10.24 | Net Meters installed on 25/02/2019. | Billing will start in 04/2019. MCO IS NOT FORWARDED BY SDIV YET TO RO OFFICE. LETTER SENT TO XEN FOR TIMELY BILLING.
25 | AZEEM AKRAM S/O MUHAMMAD AKRAM SUPERIOR COLLEGE VEHARI ROAD HASIL PUR | 15452 | A-1b(03)T | 2018-09-28 | 28154520120216 | 13 | 19.44 | Preimer Energy (Pvt) Ltd. | Yes | DGL/691/2018 | VEHARI ROAD | Installed | 2019-02-21 | Yes | 2019-03-13 | 19.44 | Connection Installed. Billing Started | -
3 | KHALID NAZEER CMISSIONER SAHIWAL | 15512 | A-3(66) | 2016-08-12 | 12155121038000 | 7 | 3 | M/S Creative Electronics | Yes | DGL/74/2017 | Civil Lines | Installed | 2018-05-10 | Yes | 2018-06-20 | 3 | Connection Installed. Billing Started | -
36 | AHMAD RAZA SHIRAZI S-O IMTIAZ HUSSAIN SHIRAZ, SHERAZI DERA MOZA KHAIR SHAH SAHIWAL | 15512 | A-1b(03)T | 2018-11-04 | 19155121582101 | 5 | 4.87 | Sky Electric (PVT) Limited | Yes | DGL/880/2018 | QUTAB SHAHANA | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 18/01/2019 | Net Meters are provided by consumer to subdivision and forwarded to M&T Sahiwal for testing since last month
5 | Asif Iqbal SM Bashir Agencies | 15514 | New A-2c(06)T, Old A-2a(04) | 2016-12-15 | New 28155140275502 and old 03155140275502 | 5 | 4.62 | Royal Energy Sultan Electronics | Yes | DGL/80/2017 | College Road | Installed | 2018-01-18 | Yes | 2018-02-12 | 4.62 | Connection Installed. Billing Started | -
46 | TAHIRA HASSAN NAWAZ W-O RAI HASSAN NAWAZ KHAN MILK CHILLER CHAK # 110-12-L CHICHAWATNI | 15544 | B2b(12)T | 2018-12-21 | 27155442161111 | 38 | 7.28 | Sky Electric (PVT) Limited | Yes | DGL/1099/2019 | Kassowal | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 14/03/2019 | Under Process for Net Meters
50 | M/S ASKARI CNG FILLING STATION NEAR TOLE #10 KLP ROAD SADIQABAD | 15641 | A-2c(06)T | 2019-01-24 | 27156410003201 | 134 | 8.96 | Solar Sigma Pvt Limited. | Yes | DGL/1186/2019 | Manthar | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 10/04/2019 | Under Process for Net Meters
19 | MUSHTAQ AHAMAD LAGHARI S-O MUHAMAMD AKBAR LAGHARI VILLAGE RAHIM ABAD SADIQABAD | 15645 | A-1a(01) | 2018-04-13 | New 28156451202700 and Old 05156451202700 | 12 | 12 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/463/2018 | RAHIM ABAD | Installed | 2018-09-14 | Yes | 2018-10-15 | 12 | Connection Installed. Billing Started | -
40 | RIZWANA NAHEED W-O MIAN NAZEER AHMAD HOUSE# 1438BI TALEERI GARDEN ROAD VILLA LALA ZAR MUZAFFARGARH | 15711 | A-1a(01) | 2018-12-04 | 18157111255900 | 5 | 7.5 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/976/2019 | MUZAFFARGARH | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 30/01/2019 | Under Process for Net Meters
13 | SHABBIR AHMAD S-O MIRAJ DIN EASTREN PRODUCTS-VITAL TEA LTD QAZI WALA HAROON ABAD | 15821 | B2b(12)T | 2017-12-26 | 27158210966702 | 482 | 304 | REON | Yes | DGL/478/2018 | KHATAN | Installed | 2018-11-03 | Yes | 2019-01-03 | 304 | Connection Installed. Billing Started | -
21 | MUHAMMAD HUSSAIN TAHIR S-O MUKHTIAR AHMAD, 73-R BANGLOW ROAD HAROONABAD | 15821 | A-2c(06)T | 2018-01-30 | 27158210754604 | 160 | 30 | M/S Creative Electronics | Yes | DGL/561/2018 | Banglow Road | Installed | 2019-02-06 | Yes | 2019-03-04 | 30 | Connection Installed. Billing Started | -
8 | UNILEVER PAKISTAN LIMITED TEA FACTORY CHAK NO.88-A10R KHANEWAL | 15913 | B3(14)T | 2017-02-08 | 27159132372500 | 503 | 110 | Reon | Yes | DGL/106/2017 | UNILEVER TEA FACTORY | Installed | 2018-01-16 | Yes | 2018-02-03 | 110 | Connection Installed. Billing Started | -
23 | SOBIA AKRAM W/O MUHAMMAD AKRAM CHAK No. 131/10 R JAHANIAN | 15915 | New A-2c(06)T, Old A-2a(04) | 2018-08-31 | New 28159152947315 Old 20159152947315 | 5 | 5.12 | Preimer Energy (Pvt) Ltd. | Yes | DGL/608/2018 | PIR SADIQ SHAH | Installed | 2018-11-01 | Yes | 2018-12-03 | 5.12 | Connection Installed. Billing Started | -
9 | KHAWAJA MUHAMMAD YOUNIS S-O KHAWAJA MUHAMMAD MASOOD FATIMA MODEL SCHOOL MULTAN ROAD K.WALA | 15921 | A-1b(03)T | 2017-03-03 | 28159210647407 | 6 | 5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/76/2017 | Spinning Unit-2 | Installed | 2017-12-21 | Yes | 2018-02-13 | 5 | Connection Installed. Billing Started | -
12 | Kh M YOUNAS M/S MASOOD SPINNING MILLS UNIT NO.02 04-KM MULTAN ROAD KABIR WALA | 15921 | B3(14)T | 2017-03-03 | 30159212533901 | 4999 | 320 | Preimer Energy (Pvt) Ltd. | Yes | DGL/79/2017 | Masood Spinning Unit-2 | Installed | 2018-01-31 | Yes | 2018-02-03 | 320 | Connection Installed. Billing Started | -

## Sheet5
SAIF ALI S/O CHOUDHARY SARDAR MUHAMMAD CHAK #106/DB YAZMAN, BAHAWALPUR | 15416 | A-1a(01)T | 2018-10-10 | 08154160646004 | 4.5 | 5.2 | Preimer Energy (Pvt) Ltd. | Yes | DGL/818/2018 | Tail Wala | Installed | 2019-03-06 | NO | - | 5.2 | Net Meters Installed on 06/03/2019 | Billing will start in 05/2019. MCO IS NOT FORWARDED BY SDIV YET TO RO OFFICE. LETTER SENT TO XEN FOR TIMELY BILLING BUT NOT BILLED IN 04/2019.
OFFICE BUILDING TEHSILDAR LODHRAN NEAR MARKET COMMITTEE OFFICE LODHRAN | 15421 | A-1b(03)T | 2016-06-18 | New 15154210167800 Old 03154210167800 | 11 | 3 | M/S Creative Electronics | Yes | DGL/75/2017 | City Lodhran | Installed | 2018-01-06 | Yes | 2018-01-10 | 3 | Connection Installed. Billing Started | -
DR SHER MUHAMMAD AWAN CHAH QASIM WALA LODHRAN | 15421 | A-1a(01) | 2018-12-06 | New16154210217400 Old 04154210217400 | 5 | 7.28 | Sky Electric (PVT) Limited | Yes | DGL/912/2019 | City Lodhran | Installed | 2019-02-19 | NO | - | 7.28 | Net Meters Installed on 19/02/2019 | Billing will start in 04/2019. MCO IS NOT FORWARDED BY SDIV YET TO RO OFFICE. LETTER SENT TO XEN FOR TIMELY BILLING.
AMIR AWAIS GHAURI BX-586/1 SADIQ COLONY BAHAWAL PUR | 15441 | A-2c(06)T | 2018-03-12 | 17154410396400 | 5 | 5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/348/2018 | N.Mahal(Cantt) | Installed | 2018-05-15 | Yes | 2018-06-16 | 5 | Connection Installed. Billing Started | -
FAHAD KHALIL S-O PEERZADA KHALIL AHMED (C-O AHMAD RIZWAN SARFRAZ) CITY SCHOOL CAMPUS BAHAWALPUR | 15441 | A-3(A) (66) | 2019-02-28 | 27154410848302 | 158 | 46.2 | Solis Energy solutions (Pvt), Ltd. | Yes | NIL | Hoot Wala | Not Installed | - | - | - | - | Applied to NEPRA for DGL license on 12/03/2019 | -
DR. SOHAIL MEHMOOD CH. S-O MUHAMMAD SADIQ MUSHTAQ 139-A HASHMI GARDEN BAHAWALPUR | 15441 | A-1b(03)T | 2018-12-21 | 20154413017500 | 7 | 10.24 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/1238/2019 | Hashmi Garden | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 12/04/2019 | NOC issued from XEN OP for self purchase of meter ON 16/04/2019. Under Process for installation of Net Meters.
SAFIA FAROGH W-O FAROGH JALIL QUERSHI, HOUSE #6 A-2, MUHAMMAD HUSSAIN ROAD, MODEL TOWN -A BAHAWALPUR | 15441 | A-1a(01) | 2019-02-28 | 14154410057700 | 5 | 7.5 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | NIL | NLC | Not Installed | - | - | - | - | Applied to NEPRA on 28/03/2019 | -
MEHMOOD AHMAD SHEIKH S-O MUHAMMAD AHMAD SHEIKH NEAR REST HOUSE BAHAWALPUR | 15443 | A-1b(03)T | 2018-09-15 | NEW 04154430970800 OLD 18154430970800 | 6 | 10.24 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/732/2018 | GHANI PUR | Installed | 2019-02-25 | Yes | 2019-04-12 | 10.24 | Connection Installed. Billing Started. | Net Meters installed on 25/02/2019. Billing Started on 12/04/2019.
AZEEM AKRAM S/O MUHAMMAD AKRAM SUPERIOR COLLEGE VEHARI ROAD HASIL PUR | 15452 | A-1b(03)T | 2018-09-28 | 28154520120216 | 13 | 19.44 | Preimer Energy (Pvt) Ltd. | Yes | DGL/691/2018 | VEHARI ROAD | Installed | 2019-02-21 | Yes | 2019-03-13 | 19.44 | Connection Installed. Billing Started | -

## Sheet1
LIST OF PENDING METERS INSTALLATION ON 14/05/2019
Application No. | Name of Applicant | Sub Division Code | Tariff | Application Date | Reference No. | Sanctioned Load | Required Load for Net Metering | Name of Installer | Applied To NEPRA (Yes or No) | Generation Licence | Feeder | Installation Status (Installed or Uninstalled) | Installation Date | Billing Started (Yes or No) | Billing Start Date | Generation (KW) | Remarks | Current Position (What is Present Status i.e. either with installer or SDO or NEPRA etc.)
20 | FATIMA JAFAR W-O MUHAMMAD JAFAR CHOUDHARY, HOUSE NO. 383-C BUCH VILLAS MULTAN | 15175 | A-1b(03)T | 2018-07-10 | 15151758880903 | 5 | 3.06 | Preimer Energy (Pvt) Ltd. | Yes | DGL/526/2018 | Butch Villas | Not Installed | - | - | - | - | Generation License Issued by NEPRA. DN for bidirectional meters issued to Consumer and paid by Consumer. Demand of Meter sent from Manager (MM) TO SDO. | Under Process for Net Meters
36 | AHMAD RAZA SHIRAZI S-O IMTIAZ HUSSAIN SHIRAZ, SHERAZI DERA MOZA KHAIR SHAH SAHIWAL | 15512 | A-1b(03)T | 2018-11-04 | 19155121582101 | 5 | 4.87 | Sky Electric (PVT) Limited | Yes | DGL/880/2018 | QUTAB SHAHANA | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 18/01/2019 | 1 Net Meter is provided by consumer to subdivision and forwarded to M&T Sahiwal for testing since last month. 2nd meter is provided by Consumer to SDO. Waiting for M&T Checking.
31 | MALIK NOOR ASGHAR BUCHA S/O MALIK NOOR MUHAMMAD BUCHA MAIN OFFICE BUILDING BUCH VILLAS BOSAN ROAD MULTAN | 15175 | A-2c(06)T | 2018-11-13 | 28151758887100 | 19 | 26.07 | Orient Energies (Pvt) Ltd. | Yes | DGL/911/2018 | Buch Villas | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 23/01/2019 | Demand notice for CTs and Box was paid by Consumer. Meter will be handed over to Subdivision & M&T soon by Consumer.
34 | SHAHID SARWAR CONTROL SHED CHAK # 69/12-L BUREWALA | 15331 | B2b(12)T | 2018-11-09 | 27153311095701 | 78 | 50.02 | Tesla Industries (Pvt) Limited. | Yes | DGL/910/2018 | 67/12L (Sultan S.Din) | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 23/01/2019 | CTs, Box and Meters were provided by Consumer and handed over to Subdivision. The meters will be sent soon by subdivision to M&T .
40 | RIZWANA NAHEED W-O MIAN NAZEER AHMAD HOUSE# 1438BI TALEERI GARDEN ROAD VILLA LALA ZAR MUZAFFARGARH | 15711 | A-1a(01) | 2018-12-04 | 18157111255900 | 5 | 7.5 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/976/2019 | MUZAFFARGARH | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 30/01/2019 | Under Process for Net Meters. Meters are to be provided by consumer.
41 | ABDUL SAMMAD S-O MALIK FAZIL MUHAMMAD SHAD, (DISTRIBUTED GENERATOR), AT SADIQABAD #2 MULTAN | 15118 | A-1b(03)T | 2018-10-20 | 12151180980204 | 5 | 3.25 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/1029/2019 | NEW FAROOQ PURA | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 21/02/2019 | Under Process for Net Meters. Meters delivered to sdo on 30/04/2019
44 | MUHAMMAD SALEEM QURESHI S-O MUHAMMAD NASEEB QURESHI HOUSE# 7-8 ABDALI COLONY MULTAN | 15117 | A-1b(03)T | 2018-12-06 | 28151170084802 | 19 | 8 | Sky Electric (PVT) Limited | Yes | DGL/1083/2019 | Hassan Perwana | Not Installed | - | - | - | - | DGL Issued on 07/03/2019 | Under Process for Net Meters. Meter Delivered to SDO.
45 | MUSARAT ULLAH QURESHI S-O ALLAH BACHAYA QURESHI POST OFFICE HARRAND BASTI PANAH ALI JAMPUR RAJANPUR | 15245 | A-1b(03)T | 2018-10-17 | 20152451123102 | 5 | 4.94 | Read Solar (PVT) Limited | Yes | DGL/1084/2019 | HARAND | Not Installed | - | - | - | - | DGL Issued on 07/03/2019 | Under Process for Net Meters
46 | TAHIRA HASSAN NAWAZ W-O RAI HASSAN NAWAZ KHAN MILK CHILLER CHAK # 110-12-L CHICHAWATNI | 15544 | B2b(12)T | 2018-12-21 | 27155442161111 | 38 | 7.28 | Sky Electric (PVT) Limited | Yes | DGL/1099/2019 | Kassowal | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 14/03/2019 | Under Process for Net Meters. DN Paid and meterwill be delivered on Tuesday.
47 | FAISAL SALMAN SHEIKH S-O MUHAMMAD AKRAM SHEIKH. SH DIN MUHAMMAD TRUST HOSPITAL 321-EB BUREWALA | 15335 | A-1a(01) | 2019-01-20 | 11153351601400 | 6 | 8.45 | Sky Electric (PVT) Limited | Yes | DGL/1107/2019 | Sarwar Shah | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 13/03/2019 | Under Process for Net Meters. Meters Delivered to sdo on 08/05/2019.
50 | M/S ASKARI CNG FILLING STATION NEAR TOLE #10 KLP ROAD SADIQABAD | 15641 | A-2c(06)T | 2019-01-24 | 27156410003201 | 134 | 8.96 | Solar Sigma Pvt Limited. | Yes | DGL/1186/2019 | Manthar | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 10/04/2019 | Under Process for Net Meters
51 | FAHAD KHALIL S-O PEERZADA KHALIL AHMED (C-O AHMAD RIZWAN SARFRAZ) CITY SCHOOL CAMPUS BAHAWALPUR | 15441 | A-3(A) (66) | 2019-02-28 | 27154410848302 | 158 | 46.2 | Solis Energy solutions (Pvt), Ltd. | Yes | DGL/1220/2019 | Hoot Wala | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 06/05/2019 | Under Process for Net Meters
48 | DR. SOHAIL MEHMOOD CH. S-O MUHAMMAD SADIQ MUSHTAQ 139-A HASHMI GARDEN BAHAWALPUR | 15441 | A-1b(03)T | 2018-12-21 | 20154413017500 | 7 | 10.24 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/1238/2019 | Hashmi Garden | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 12/04/2019 | NOC issued from XEN OP for self purchase of meter ON 16/04/2019. Under Process for installation of Net Meters.
52 | SAFIA FAROGH W-O FAROGH JALIL QUERSHI, HOUSE #6 A-2, MUHAMMAD HUSSAIN ROAD, MODEL TOWN -A BAHAWALPUR | 15441 | A-1a(01) | 2019-02-28 | 14154410057700 | 5 | 7.5 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/1278/2019 | NLC | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 25/04/2019 | Applied to NEPRA on 28/03/2019. Under Process for Net Meters.
57 | MALIK MUHAMMAD IBRAHEEM S-O WAHID BUX AT SHANGRILLA HOTEL SADAR BAZAR MULTAN CANTT. | 15111 | A-2c(06)T | 2019-01-16 | 27151111824400 | 155 | 30.24 | Read Solar (PVT) Limited | Yes | DGL/1356/2019 | Quaid-e-Azam Road | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 07/05/2019 | Under Process for Net Meters
59 | Ms. RAHEELA BANO W-O KHAWAJA ATIQ UR REHMAN AT HOUSE #729-J SHAH RUKN E ALAM COLONY MULTAN | 15194 | A-1a(01) | 2019-04-11 | 19151941032800 | 5 | 7.36 | Feston Engineering Works Multan | Yes | DGL/1365/2019 | Gulberg Colony | Not Installed | - | - | - | - | Generation License Issued by NEPRA on 07/05/2019 | Under Process for Net Meters

## Sheet4
192
5.12
4.96
10.24
19.44
5
5.2
18.36
7.4
4.87
4.96
10.07
114.37
7.28
6.5
5.85
7.15
428.77