## Net-Metering-Info
NET METERING APPLICATION(S) INFORMATION/STATUS
| COMPANY NAME: MEPCO | [16 empty] | Dated:10-12-2018
Sr. No | Application No. | Name of Applicant | Sub Division Code | Tariff | Application Date | Reference No. | Sanctioned Load | Required Load for Net Metering | Name of Installer | Applied To NEPRA (Yes or No) | Generation Licence | Feeder | Installation Status (Installed or Uninstalled) | Installation Date | Billing Started (Yes or No) | Billing Start Date | Generation (KW) | Remarks | Current Position (What is Present Status i.e. either with installer or SDO or NEPRA etc.)
1 | 1 | OFFICE BUILDING TEHSILDAR LODHRAN NEAR MARKET COMMITTEE OFFICE LODHRAN | 15421 | A-1b(03)T | 2016-06-18 | 03154210167800 | 11 | 3 | M/S Creative Electronics | Yes | DGL/75/2017 | City Lodhran | Installed | 2018-01-06 | Yes | 2018-01-10 | 3 | Connection Installed. Billing Started | -
2 | 2 | XEN CIVIL MEPCO | 15173 | A-1b(03)T | 2016-07-12 | 13151734972100 | 12 | 3 | Reap | Yes | DGL/48/2017 | Wapda Colony | Installed | 2016-07-28 | Yes | 2016-08-23 | 3 | Connection Installed. Billing Started | -
3 | 3 | KHALID NAZEER CMISSIONER SAHIWAL | 15512 | A-1b(03)T | 2016-08-12 | 12155121038000 | 7 | 3 | M/S Creative Electronics | Yes | DGL/74/2017 | Civil Lines | Installed | 2018-05-10 | Yes | 2018-06-20 | 3 | Connection Installed. Billing Started | -
4 | 4 | MALIK NOOR ASGHAR BUCHA S/O MLK NOOR MUHAMMAD BUCHA THE GRAND COMMERCIAL BUILDING BUCH VILLAS H/S BOSAN ROAD MTN | 15175 | A-2c(06)T | 2016-09-12 | 27151758887001 | 857 | 25.5 | Orient Energies (Pvt) Ltd. | Yes | DGL/83/2017 | Buch Villas | Installed | 2018-01-17 | Yes | 2018-03-01 | 25.5 | Connection Installed. Billing Started | -
5 | 5 | Asif Iqbal SM Bashir Agencies | 15514 | A-2a(04) | 2016-12-15 | New 28155140275502 and old 03155140275502 | 5 | 4.62 | Royal Energy Sultan Electronics | Yes | DGL/80/2017 | College Road | Installed | 2018-01-18 | Yes | 2018-02-12 | 4.62 | Connection Installed. Billing Started | -
6 | 6 | MUHAMMAD ARSHAD NADEEM S-O MHAMMAD ASHIQ ST NO 1 MADINA ABAD CLY MTN MULTAN | 15132 | A-1b(03)T | 2017-01-06 | 13151322030405 | 5 | 10 | Solar Tech. | Yes | DGL/117/2017 | Timber Market | Installed | 2017-12-17 | Yes | 2017-12-21 | 10 | Connection Installed. Billing Started | -
7 | 7 | SAJIDA KHALID W/O CH.KHALID LATIF PUNJAB SMALL INDUSTRIES MTN | 15175 | A-1b(03)T | 2017-01-26 | 17151753136101 | 5 | 10 | Pak Friends Enterprises | Yes | DGL/107/2017 | Darbar Peer Akbar Shah | Installed | 2017-12-19 | Yes | 2017-12-20 | 10 | Connection Installed. Billing Started | -
8 | 8 | UNILEVER PAKISTAN LIMITED TEA FACTORY CHAK NO.88-A10R KHANEWAL | 15913 | B3(14)T | 2017-02-08 | 27159132372500 | 503 | 110 | Reon | Yes | DGL/106/2017 | UNILEVER TEA FACTORY | Installed | 2018-01-16 | Yes | 2018-02-03 | 110 | Connection Installed. Billing Started | -
9 | 9 | KHAWAJA MUHAMMAD YOUNIS S-O KHAWAJA MUHAMMAD MASOOD FATIMA MODEL SCHOOL MULTAN ROAD K.WALA | 15921 | A-1b(03)T | 2017-03-03 | 28159210647407 | 6 | 5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/76/2017 | Masood Spinning Unit-2 | Installed | 2017-12-21 | Yes | 2018-02-13 | 5 | Connection Installed. Billing Started | -
10 | 10 | KH MUHAMMAD YOUNIS S-O MUHAMMAD MASOOD 13 B OFFICER CLY MULTAN | 15172 | A-1b(03)T | 2017-03-03 | 18151723474200 | 12 | 32 | Preimer Energy (Pvt) Ltd. | Yes | DGL/78/2017 | Eid Gah Road | Installed | 2017-12-19 | Yes | 2017-12-27 | 32 | Connection Installed. Billing Started | -
11 | 11 | MEHMOOD TEXTILE MILLS LTD MULTAN LOHARI GATE MULTAN CITY | 15113 | A-2c(06)T | 2017-03-03 | 27151130721400 | 200 | 64 | Preimer Energy (Pvt) Ltd. | Yes | DGL/77/2017 | Abdali Road | Installed | 2018-01-29 | Yes | 2018-02-03 | 64 | Connection Installed. Billing Started | -
12 | 12 | Kh M YOUNAS M/S MASOOD SPINNING MILLS UNIT NO.02 04-KM MULTAN ROAD KABIR WALA | 15921 | B3(14)T | 2017-03-03 | 30159212533901 | 4999 | 320 | Preimer Energy (Pvt) Ltd. | Yes | DGL/79/2017 | Masood Spinning Unit-2 | Installed | 2018-01-31 | Yes | 2018-02-03 | 320 | Connection Installed. Billing Started | -
13 | 13 | SHABBIR AHMAD S-O MIRAJ DIN EASTREN PRODUCTS-VITAL TEA LTD QAZI WALA HAROON ABAD | 15821 | B2b (12)T | 2017-12-26 | 27158210966702 | 482 | 304 | REON | Yes | DGL/478/2018 | KHATAN | Installed | 2018-11-03 | NO | - | 304 | Meter Installed on 03/11/2018 | MCO not feeded in billing of 11/2018. Billing will start in 12/2018.
14 | 14 | NAIMAT ULLAH S.O ALLAH BACHAYA QURESHI 259-N WAPDA TOWN-11 MTN | 15175 | A-1b(03)T | 2017-06-01 | 17151753132415 | 5 | 10 | SOLAR MASTER | Yes | DGL/128/2017 | Wapda Town | Installed | 2017-12-19 | YES | 2017-12-20 | 10 | Connection Installed. Billing Started | - | 30
15 | 15 | NASEEM AHMAD/ FAZAL CLOTH MILLS 59/3 ABDALI ROAD MULTAN | 15117 | A-2c(06)T | 2018-02-19 | 27151170144100 | 145 | 88 | Preimer Energy (Pvt) Ltd. | Yes | DGL/349/2018 | Hassan Perwana | Installed | 2018-05-15 | Yes | 2018-06-01 | 88 | Connection Installed. Billing Started | - | 304
16 | 16 | ALLIED ENGINEERING & SERVICES HAMID PUR KANORA SHER SHAH BY PASS MTN | 15138 | B2b (12)T | 2018-03-09 | 27151380994405 | 60 | 23.76 | AYK (Pvt) Ltd. | Yes | DGL/343/20178 | Basti Balail | Installed | 2018-10-18 | NO | - | 23.76 | Connection Installed. Billing will start in 12/2018. | MCO not feeded in 10/2018 & 11/2018 Billing. | 23.76
17 | 17 | AMIR AWAIS GHAURI BX-586/1 SADIQ COLONY BAHAWAL PUR | 15441 | A-2c(06)T | 2018-03-12 | 17154410396400 | 5 | 5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/348/2018 | N.Mahal(Cantt) | Installed | 2018-05-15 | Yes | 2018-06-16 | 5 | Connection Installed. Billing Started | - | 357.76
18 | 18 | HAMEED RAZA S/O AMEER UD DIN AT HOUSE #2 HAMZA STREET BOSAN ROAD MULTAN | 15171 | A-1a(01) | 2018-04-03 | 13151717096201 | 6 | 5.2 | Preimer Energy (Pvt) Ltd. | Yes | DGL/358/2018 | Sabzazar | Installed | 2018-08-29 | Yes | 2018-09-24 | 5.2 | Connection Installed. Billing Started | - | 344.96
19 | 19 | MUSHTAQ AHAMAD LAGHARI S-O MUHAMAMD AKBAR LAGHARI VILLAGE RAHIM ABAD SADIQABAD | 15645 | A-1a(01) | 2018-04-13 | New 28156451202700 and Old 05156451202700 | 12 | 12 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/463/2018 | RAHIM ABAD | Installed | 2018-09-14 | Yes | 2018-10-15 | 12 | Connection Installed. Billing Started | -
20 | 20 | FATIMA JAFAR W-O MUHAMMAD JAFAR CHOUDHARY, HOUSE NO. 383-C BUCH VILLAS MULTAN | 15175 | A-1b(03)T | 2018-07-10 | 15151758880903 | 5 | 3.06 | Preimer Energy (Pvt) Ltd. | Yes | DGL/526/2018 | Butch Villas | Not Installed | - | NO | - | - | DN for bidirectional meters issued to Consumer and paid by Consumer. Demand of Meter sent to Manager (MM) | Under Process for Net Meters
21 | 21 | MUHAMMAD HUSSAIN TAHIR S-O MUKHTIAR AHMAD, 73-R BANGLOW ROAD HAROONABAD | 15821 | A-2c(06)T | 2018-01-30 | 27158210754604 | 160 | 30 | M/S Creative Electronics | Yes | DGL/561/2018 | Banglow Road | Not Installed | - | NO | - | - | Permission granted to consumer on 12/09/2018 for purchase of meter. Meter will be installed after provision by consumer. | Under Process for Net Meters
22 | 22 | ALI SHAH S/O MUREED HUSSAIN SHAH MOHALLAH LAL SHAH MAKHDOOM RASHID MULTAN | 15127 | A-1a(01) | 2017-07-14 | 17151271746812 | 3 | 3.97 | POWER PROJECTS ORGNAIZATION | Yes | DGL/768/2018 | MAKHDOOM RASHID CITY | Not Installed | - | NO | - | - | Applied To NEPRA on 15/08/2018 and License issued the License on 23/11/2018. | Under Process for Net Meters
23 | 23 | SOBIA AKRAM W/O MUHAMMAD AKRAM CHAK No. 131/10 R JAHANIAN | 15915 | A-2a(04) | 2018-08-31 | 20159152947315 | 5 | 5.12 | Preimer Energy (Pvt) Ltd. | Yes | DGL/608/2018 | PIR SADIQ SHAH | Installed | 2018-11-01 | Yes | 2018-12-03 | 5.12 | Connection Installed. Billing Started | Export reading not posted.
24 | 24 | MUHAMMAD SARWAR S/O ABDUL MAJEED PUNJAB DEGREE COLLEGE AZIM ABAD BUREWALA | 15333 | A-2c(06)T | 2018-08-16 | 27153332500302 | 200 | 192 | Preimer Energy (Pvt) Ltd. | Yes | DGL/620/2018 | City-3 | Installed | 2018-10-08 | Yes | 2018-11-06 | 192 | Connection Installed. Billing Started | - | 30
25 | 25 | AZEEM AKRAM S/O MUHAMMAD AKRAM SUPERIOR COLLEGE VEHARI ROAD HASIL PUR | 15452 | A-1b(03)T | 2018-09-28 | 28154520120216 | 13 | 19.44 | Preimer Energy (Pvt) Ltd. | Yes | DGL/691/2018 | VEHARI ROAD | Not Installed | - | NO | - | - | Applied To NEPRA on 01/10/2018 and generation license issued on 24/10/2018 | Under Process for Net Meters | 3.04
26 | 26 | MUHAMMAD JUNAID MASOOD HOUSE #66-M, WAPDA TOWN PHASE II MULTAN | 15175 | A-1b(03)T | 2018-10-07 | 17151753124630 | 8 | 10 | Sky Electric (PVT) Limited | Yes | NIL | Wapda Town | Not Installed | - | NO | - | - | Applied To NEPRA on 19/11/2018
27 | 27 | SAIF ALI S/O CHOUDHARY SARDAR MUHAMMAD CHAK #106/DB YAZMAN, BAHAWALPUR | 15416 | A-1a(01)T | 2018-10-10 | 08154160646004 | 4.5 | 5.2 | Preimer Energy (Pvt) Ltd. | Yes | NIL | Tail Wala | Not Installed | - | NO | - | - | Applied To NEPRA on 20/11/2018 |  | 19.44
28 | 28 | MAHMOOD AHMAD SHEIKH S-O MUHAMMAD AHMAD SHEIKH NEAR REST HOUSE BAHAWALPUR | 15443 | A-1b(03)T | 2018-09-15 | 18154430970800 | 6 | 10.24 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/732/2018 | GHANI PUR | Not Installed | - | NO | - | - | Applied To NEPRA on 22/10/2018 and DGL issued on 19/11/2018 | Under Process for Net Meters
29 | 29 | MUHAMMAD KHALID ALVI S/O MUHAMMAD SHARIF ALVI 43-A GULGASHT COLONY MULTAN | 15171 | A-1a(01)T | 2018-10-01 | 04151715528700 | 5 | 5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/769/2018 | USMANABAD | Not Installed | - | NO | - | - | Applied To NEPRA on 08/11/2018 & DGL issued on 20/11/2018 | Under Process for Net Meters
30 | 30 | SAMINA MUJAHID W/O MUJAHID ALI AT 98-B BUCH VILLAS MULTAN | 15175 | A-1b(03)T | 2018-11-09 | 15151758884003 | 5 | 4.96 | Read Solar (PVT) Limited | Yes | NIL | Buch Villas | Not Installed | - | NO | - | - | Applied To NEPRA on 19/11/2018
31 | 33 | SHAHZIA ZUBAIR W-O ZUBAIR BILAL AT 12-E,OFFICERS COLONY MULTAN | 15172 | A-1b(03)T | 2018-10-29 | 18151723471501 | 5 | 7.5 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | NIL | Shamsabad | Not Installed | - | NO | - | - | Applied To NEPRA on 03/12/2018
32 | 35 | MALIK MUHAMMAD IBRAHEEM S-O WAHID BUX AT H#1341 BM WAHID ABAD COLONY OLD SHUJA ABAD ROAD MULTAN | 15132 | A-1b(03)T | 2018-10-24 | 03151322240300 | 13 | 18.36 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | NIL | Old Shujabad Road | Not Installed | - | NO | - | - | Applied To NEPRA on 06/12/2018
|  |  |  | Total Applied (KW)= |  | 1352.93 | [6 empty] | Total Generation (KW)= |  |  | 1235.2 |  |  |  | 52.48
[7 empty] | 7735.5 | 1352.93

## abstract
Progress of Net Metering (Dated: 10-12-2018)
Description | Detail | Capacity (KW) | Remarks | Formulas
No. of Applications Received | 32 | 1352.93 | - | 1352.93
Genereation licences applied to NEPRA | 32 | 1352.93 | -
Genereation licences issued by NEPRA | 27 | 1306.91 | - | 1306.91
Genereation licences pending at NEPRA | 5 | 46.02 | Applied To NEPRA 19-11-2018, 20-11-2018, 03-12-2018 & 06-12-2018 | 46.02 | 15.24
No. of Connections Installed | 21 | 1235.2 | Billing of 19 Connections Started. 2# Connections billing will start in 12/2018
Applications Under Process | 6 | 71.71 | 2 # Connections DN for bidirectional meters Issued to Consumer. 3 # connections are under process. 01 # connections 30.00 KW, permission granted to consumers on 12/09/2018 for purchase of meters. Meters will be installed after provision of meters by consumers. | 357.76 | 334

## circle wise abstract
MEPCO Circlewise Progress of Net Metering on Roshan Pakistan App (Dated:10-11-2018)
Circles Names | Circles Codes | Total Sanctioned/ Connected Load (KW) | Total required load for Net Metering (KW) | Generation (KW) | Total Applications | Billing Started | Applied to NEPRA | Total connections |  | Remarks
[8 empty] | Installed | Remaining
Multan | 15100 | 1351 | 324.31 | 271.46 | 17 | 9 | 4 | 10 | 7 | 3# Applied To NEPRA For DG License On 19-11-2018 & 03/12/2018 & 06/12/2018. 1# Connection DN Issued To Consumer. 1# connection billing will start in 12/2018. 2# are under process for Net Meters.
Vehari | 15300 | 200 | 192 | 192 | 1 | 1 | 0 | 1 | 0 | Meter installed on 08/10/2018. Billing started in 10/2018.
Bahawalpur | 15400 | 39.5 | 42.88 | 8 | 5 | 2 | 1 | 2 | 3 | 1# connection applied to NEPRA on 20/11/2018. 2# connections are under process for Net Meters.
Sahiwal | 15500 | 12 | 7.62 | 7.62 | 2 | 2 | 0 | 2 | 0 | -
Rahim Yar Khan | 15600 | 12 | 12 | 12 | 1 | 1 | 0 | 1 | 0 | Meter installed on 14/09/2018. Billing started on 15/ 10/2018.
Bahawal Nagar | 15800 | 642 | 334 | 304 | 2 | 0 | 0 | 1 | 1 | Permission granted to consumers on 12/09/2018 for purchase of meter. 2nd Meter will be installed after provision of meters by consumers. 1# connection billing will start in 12/2018.
Khanewal | 15900 | 5513 | 440.12 | 440.12 | 4 | 4 | 0 | 4 | 0 | -
Total |  | 7769.5 | 1352.93 | 1235.2 | 32 | 19 | 5 | 21 | 11 | 2# connections billing will start in 12/2018.

## tariff wise abstract
Progress of Net Metering Tariff wise Abstract (Dated: 10-11-2018)
Sr. No. | Type | Tariff | No. Of Connections | Meters Installed | Under Process
1 | Domestic | A-1a(01) | 5 | 2 | 1# Connection Applied To NEPRA For DG License On 20/11/2018.
|  | A-1b(03)T | 15 | 8 | 2# DN for bidirectional meters issued to Consumer (under Process). 3 connections applied to NEPRA on 19/11/2018 & 03/12/2018 & 06/12/2018. 1# is under process for Net Meter.
2 | Commercial | A-2a(04) | 2 | 2 | Connection Installed. Billing started.
|  | A-2c(06)T | 6 | 5 | Billing of5 connections started. 1# Connection is under process.
3 | Industrial | B2b(12)T | 2 | 2 | Connection Installed. 2# connections Billing will start in 12/2018.
|  | B3(14)T | 2 | 2 | Connection Installed. Billing started.
|  | Total | 32 | 21 | Billing of 19 Connections Started. 3# Connections billing will start in 12/2018

## year wise abstract
NET METERING APPLICATION(S) INFORMATION/STATUS
COMPANY NAME: MEPCO | [7 empty] | Dated: 10-11-2018
Description | 2016 |  | 2017 |  | 2018 |  | TOTAL Connections | TOTAL Load | Pending connections 2018 | Pending Load 2018 | REMARKS
| Connections | Load For Net Metering (KW) | Connections | Load For Net Metering (KW) | Connections | Load For Net Metering (KW) | [7 empty] | 931.2
Number of Connections applied to MEPCO | 5 | 39.12 | 10 | 868 | 17 | 445.81 | 32 | 1352.93 | - | - | 32 applications received
Number of Generation Licenses applied to NEPRA | 0 | 0 | 13 | 600.12 | 19 | 752.81 | 32 | 1352.93 | - | - | 32 applications applied to NEPRA
Number of Generation Licenses issued by NEPRA | 0 | 0 | 13 | 600.12 | 14 | 706.79 | 27 | 1306.91 | 5 | 46.02 | Applied to NEPRA in 10/2018, 11/2018 & 12/2018 |  | 344.96 |  |  | 215.88
Number of Connections Installed | 1 | 3 | 5 | 67 | 15 | 1165.2 | 21 | 1235.2 | 6 | 71.71 | a) 5 connections meter not installed due to non-availability of meters within Manager (MM) MEPCO. b) Permission granted to 1# consumer on 12/09/2018 for purchase of meters. Meters will be installed after provision of meter by consumer. |  | 192 |  | 902.32
Number of Connections Where Billing Started | 1 | 3 | 4 | 62 | 14 | 842.44 | 19 | 907.44 | 2 | 327.76 |  |  | 536.96 |  | 192
710.32
-28.88
[7 empty] | 304 | 200.8
5
19.44
328.44
23.9

## dg licences sheet
NEPRA Generation Licences for MEPCO Net Metering Consumers Till Dated:10-11-2018
Sr.# | Date | Expiry Date | Generation Licence No. And Application No. And Name
1 | 2017-02-02 | 2020-02-01 | Generation Licence No. DGL/48/2017 - Licence Application No. LAN-48 - MEPCO Head Quarters, Khanewal Road, Multan
2 | 2017-03-28 | 2020-03-27 | Generation Licence No. DGL/76/2017 - Licence Application No. LAN-76 - Mr. Khawaja M. Younus, Multan
3 | 2017-04-04 | 2020-04-03 | Generation Licence No. DGL/83/2017 - Licence Application No. LAN-83 Mr. Malik Noor Asghar Bucha, Multan
4 | 2017-04-04 | 2020-04-03 | Generation Licence No. DGL/79/2017 - Licence Application No. LAN-79 - Mr. Khawaja M. Ilyas, Masood Spinning Mills, Kabirwala
5 | 2017-04-04 | 2020-04-03 | Generation Licence No. DGL/77/2017 - Licence Application No. LAN-77 - Mr. Khawaja M. Younus, Mahmood Textile Mills, Multan
6 | 2017-04-04 | 2020-04-03 | Generation Licence No. DGL/80/2017 - Licence Application No. LAN-80 - Mr. Asif Iqbal, Sahiwal
7 | 2017-04-13 | 2020-04-12 | Generation Licence No. DGL/78/2017 - Licence Application No. LAN-78 - Mr. Khawaja Muhammad Younus, Multan
8 | 2017-05-17 | 2020-05-16 | Generation Licence No. DGL/74/2017 - Licence Application No. LAN-74 - Zila Council, Iqbal Road, Sahiwal
9 | 2017-05-22 | 2020-05-21 | Generation Licence No. DGL/75/2017 - Licence Application No. LAN-75 - Office of the Deputy Commissioner, Lodhran
10 | 2017-06-13 | 2020-06-12 | Generation Licence No. DGL/107/2017 - Licence Application No. LAN-107 - Mrs. Sajida Khalid, Multan
11 | 2017-07-10 | 2020-07-09 | Generation Licence No. DGL/106/2017 Licence Application No. LAN-106 Unilever Khanewal Tea Factory, Khanewal
12 | 2017-07-12 | 2020-07-11 | Generation Licence No. DGL/128/2017 Licence Application No. LAN-128 Mr. Naimat Ullah Qureshi, Multan
13 | 2017-07-12 | 2020-07-11 | Generation Licence No. DGL/117/2017 Licence Application No. LAN-117 Mr. Muhammad Arshad Nadeem, Multan
14 | 2018-04-16 | 2025-04-15 | Generation Licence No. DGL/343/2018 Licence Application No. LAN-343 Allied Engineering & Services, Multan
15 | 2018-04-16 | 2025-04-15 | Generation Licence No. DGL/348/2018 Licence Application No. LAN-348 Mr. Amir Owais Ghauri, Bahawalpur
16 | 2018-04-20 | 2025-04-19 | Generation Licence No. DGL/349/2018 Licence Application No. LAN-349 Fazal Cloth Mills Limited, Multan
17 | 2018-04-24 | 2025-04-23 | Generation Licence No. DGL/358/2018 Licence Application No. LAN-358 Mr. Hameed Raza, Multan
18 | 2018-07-06 | 2025-07-05 | Generation Licence No. DGL/463/2018 Licence Application No. LAN-463 Mr. Mushtaq Ahmad Laghari Village Rahimabad Tehsil Sadiqabad
19 | 2018-07-12 | 2025-07-11 | Generation Licence No. DGL/478/2018 - Licence Application No. LAN-478 - Mr. Shabbir Ahmad, Eastern Products (Private) Limited, MEPCO
20 | 2018-08-16 | 2025-08-15 | Generation Licence No. DGL/526/2018 - Licence Application No. LAN-526 - Ms. Fatima Jafar, MEPCO
21 | 2018-09-03 | 2025-09-02 | Generation Licence No. DGL/561/2018 - Licence Application No. LAN-561 -Mr. Muhammad Hussain Tahir, MEPCO
22 | 2018-09-25 | 2025-09-24 | Generation Licence No. DGL/608/2018 - Licence Application No. LAN-608 - Ms. Sobia Akram, MEPCO
23 | 2018-09-25 | 2025-09-24 | Generation Licence No. DGL/620/2018 - Licence Application No. LAN-620 - Mr. Muhammad Sarwar, for 192.0 KW photo voltaic solar based distributed generation facility located at Punjab Degree College, Azim Abad, Burewala
24 | 2018-10-24 | 2025-10-23 | Generation Licence No. DGL/691/2018 - Licence Application No. LAN-691 GL Azeem Akram, for 19.44 KW photo voltaic solar based distributed generation facility located at Superior College, Vehari Road, Hasilpur
25 | 2018-11-19 | 2025-11-18 | Generation Licence No. DGL/732/2018 - Licence Application No. LAN-732 - Mr. Sheikh Mahmood, MEPCO
26 | 2018-11-20 | 2025-11-19 | Generation Licence No. DGL/769/2018 - Licence Application No. LAN-769 - Mr. Muhammad Khalid Alvi, MEPCO
27 | 2018-11-23 | 2025-11-22 | Generation Licence No. DGL/768/2018 - Licence Application No. LAN-768 - Mr. Ali Shah, MEPCO