## Net-Metering-Info
NET METERING APPLICATION(S) INFORMATION/STATUS
COMPANY NAME: MEPCO | [16 empty] | Dated:15-08-2018
Application No. | Name of Applicant | Sub Division Code | Tariff | Application Date | Reference No. | Sanctioned Load | Required Load for Net Metering | Name of Installer | Applied To NEPRA (Yes or No) | Generation Licence | Feeder | Installation Status (Installed or Uninstalled) | Installation Date | Billing Started (Yes or No) | Billing Start Date | Generation (KW) | Remarks | Current Position (What is Present Status i.e. either with installer or SDO or NEPRA etc.)
1 | OFFICE BUILDING TEHSILDAR LODHRAN NEAR MARKET COMMITTEE OFFICE LODHRAN | 15421 | A-1b(03)T | 2016-06-18 | 03154210167800 | 11 | 3 | M/S Creative Electronics | Yes | DGL/75/2017 | City Lodhran | Installed | 2018-01-06 | Yes | 2018-01-10 | 3 | Connection Installed. Billing Started | -
2 | XEN CIVIL MEPCO | 15173 | A-1b(03)T | 2016-07-12 | 13151734972100 | 12 | 3 | Reap | Yes | DGL/48/2017 | Wapda Colony | Installed | 2016-07-28 | Yes | 2016-08-23 | 3 | Connection Installed. Billing Started | -
3 | KHALID NAZEER CMISSIONER SAHIWAL | 15512 | A-1b(03)T | 2016-08-12 | 12155121038000 | 7 | 3 | M/S Creative Electronics | Yes | DGL/74/2017 | Civil Line | Installed | 2018-05-10 | Yes | 2018-06-20 | 3 | Connection Installed. Billing Started | -
4 | MALIK NOOR ASGHAR BUCHA S/O MLK NOOR MUHAMMAD BUCHA THE GRAND COMMERCIAL BUILDING BUCH VILLAS H/S BOSAN ROAD MTN | 15175 | A-2c(06)T | 2016-09-12 | 27151758887001 | 857 | 25.5 | Orient Energies (Pvt) Ltd. | Yes | DGL/83/2017 | Buch Villas | Installed | 2018-01-17 | Yes | 2018-03-01 | 25.5 | Connection Installed. Billing Started | -
5 | Asif Iqbal SM Bashir Agencies | 15514 | A-2a(04) | 2016-12-15 | 03155140275502- old 28155140275502 | 5 | 4.62 | Royal Energy Sultan Electronics | Yes | DGL/80/2017 | College Road | Installed | 2018-01-18 | Yes | 2018-02-12 | 4.62 | Connection Installed. Billing Started | -
6 | MUHAMMAD ARSHAD NADEEM S-O MHAMMAD ASHIQ ST NO 1 MADINA ABAD CLY MTN MULTAN | 15132 | A-1b(03)T | 2017-01-06 | 13151322030405 | 5 | 10 | Solar Tech. | Yes | DGL/117/2017 | Timber Market | Installed | 2017-12-17 | Yes | 2017-12-21 | 10 | Connection Installed. Billing Started | -
7 | SAJIDA KHALID W/O CH.KHALID LATIF PUNJAB SMALL INDUSTRIES MTN | 15175 | A-1b(03)T | 2017-01-26 | 17151753136101 | 5 | 10 | Pak Friends Enterprises | Yes | DGL/107/2017 | Peer Akbar Shah | Installed | 2017-12-19 | Yes | 2017-12-20 | 10 | Connection Installed. Billing Started | -
8 | UNILEVER PAKISTAN LIMITED TEA FACTORY CHAK NO.88-A10R KHANEWAL | 15913 | B3(14)T | 2017-02-08 | 27159132372500 | 503 | 110 | Reon | Yes | DGL/106/2017 | UNILEVER TEA FACTORY | Installed | 2018-01-16 | Yes | 2018-02-03 | 110 | Connection Installed. Billing Started | -
9 | KHAWAJA MUHAMMAD YOUNIS S-O KHAWAJA MUHAMMAD MASOOD FATIMA MODEL SCHOOL MULTAN ROAD K.WALA | 15921 | A-1b(03)T | 2017-03-03 | 28159210647407 | 6 | 5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/76/2017 | Masood Spinning-2 | Installed | 2017-12-21 | Yes | 2018-02-13 | 5 | Connection Installed. Billing Started | -
10 | KH MUHAMMAD YOUNIS S-O MUHAMMAD MASOOD 13 B OFFICER CLY MULTAN | 15172 | A-1b(03)T | 2017-03-03 | 18151723474200 | 12 | 32 | Preimer Energy (Pvt) Ltd. | Yes | DGL/78/2017 | Eid Gah | Installed | 2017-12-19 | Yes | 2017-12-27 | 32 | Connection Installed. Billing Started | -
11 | MEHMOOD TEXTILE MILLS LTD MULTAN LOHARI GATE MULTAN CITY | 15113 | A-2c(06)T | 2017-03-03 | 27151130721400 | 200 | 64 | Preimer Energy (Pvt) Ltd. | Yes | DGL/77/2017 | Abdali Road | Installed | 2018-01-29 | Yes | 2018-02-03 | 64 | Connection Installed. Billing Started | -
12 | Kh M YOUNAS M/S MASOOD SPINNING MILLS UNIT NO.02 04-KM MULTAN ROAD KABIR WALA | 15921 | B3(14)T | 2017-03-03 | 30159212533901 | 4999 | 320 | Preimer Energy (Pvt) Ltd. | Yes | DGL/79/2017 | Masood Spinning-2 | Installed | 2018-01-31 | Yes | 2018-02-03 | 320 | Connection Installed. Billing Started | -
13 | SHABBIR AHMAD S-O MIRAJ DIN EASTREN PRODUCTS-VITAL TEA LTD QAZI WALA HAROON ABAD | 15821 | B2b (12)T | 2017-12-26 | 27158210966702 | 482 | 304 | REON | NO | DGL/478/2018 | KHATAN | Not Installed | - | - | - | - | Applied To NEPRA on 26/06/2018. Generation License Issued on 12/07/2018 | Application Under Process.
14 | NAIMAT ULLAH S.O ALLAH BACHAYA QURESHI 259-N WAPDA TOWN-11 MTN | 15175 | A-1b(03)T | - | 17151753132415 | 5 | 10 | SOLAR MASTER | Yes | DGL/128/2017 | Wapda Town | Installed | 2017-12-19 | YES | 2017-12-20 | 10 | Connection Installed. Billing Started | -
15 | NASEEM AHMAD/ FAZAL CLOTH MILLS 59/3 ABDALI ROAD MULTAN | 15117 | A-2c(06)T | 2018-02-19 | 27151170144100 | 145 | 88 | Preimer Energy (Pvt) Ltd. | Yes | DGL/349/2018 | Hassan Perwana | Installed | 2018-05-15 | Yes | 2018-06-01 | 88 | Connection Installed. Billing Started | -
16 | ALLIED ENGINEERING & SERVICES HAMID PUR KANORA SHER SHAH BY PASS MTN | 15138 | B2b (12)T | 2018-03-09 | 27151380994405 | 60 | 23.76 | AYK (Pvt) Ltd. | Yes | DGL/343/20178 | Basti Balail | Un Installed | - | - | - | - | Demand Notice issued to consumer for bidirectional Meter | NEPRA Issued the licence on 16-04-2018
17 | AMIR AWAIS GHAURI BX-586/1 SADIQ COLONY BAHAWAL PUR | 15441 | A-2c(06)T | 2018-03-12 | 17154410396400 | 5 | 5 | Preimer Energy (Pvt) Ltd. | Yes | DGL/348/2018 | N. Mahal (Cantt) | Installed | 2018-05-15 | Yes | 2018-06-16 | 5 | Connection Installed. Billing Started | -
18 | HAMEED RAZA S/O AMEER UD DIN AT HOUSE #2 HAMZA STREET BOSAN ROAD MULTAN | 15171 | A-1a(01) | 2018-04-03 | 13151717096201 | 2 | 5.2 | Preimer Energy (Pvt) Ltd. | Yes | DGL/358/2018 | Sabzazar | Un Installed | - | - | - | - | Demand Notice issued to consumer for bidirectional Meter | NEPRA Issued the licence on 24-04-2018 | 344.96
19 | MUSHTAQ AHAMAD LAGHARI S-O MUHAMAMD AKBAR LAGHARI VILLAGE RAHIM ABAD SADIQABAD | 15645 | A-1a(01) | 2018-04-13 | 05156451202700 | 12 | 12 | Catkin Engineering Sale and Services (Pvt) Ltd. | Yes | DGL/463/2018 | RAHIM ABAD | Un Installed | - | - | - | - | Applied To NEPRA on 11/06/2018 and DGL Licence Issued on 06-07-2018 | DN For Net Meter Issued.
20 | FATIMA JAFAR W-O MUHAMMAD JAFAR CHOUDHARY, HOUSE NO. 383-C BUCH VILLAS MULTAN | 15175 | A-1b(03)T | 2018-07-10 | 15151758880903 | 5 | 3.06 | Preimer Energy (Pvt) Ltd. | Yes | No | Buch Villas | Un Installed | - | - | - | - | Applied To NEPRA on 19/07/2018.
21 | MUHAMMAD HUSSAIN TAHIR S-O MUKHTIAR AHMAD, 73-4 RBANGLOW ROAD HAROONABAD | 15821 | A-2c(06)T | 2018-01-30 | 27158210754604 | 160 | 30 | M/S Creative Electronics | Yes | No | Banglow Road | Un Installed | - | - | - | - | Applied To NEPRA on 09/08/2018.
22 | ALI SHAH S/O MUREED HUSSAIN SHAH MOHALLAH LAL SHAH MAKHDOOM RASHID MULTAN | 15127 | A-1a(01) | 2017-07-14 | 17151271746804 | 3 | 3 | POWER PROJECTS ORGNAIZATION | Yes | No | MAKHDOOM RASHID CITY | Un Installed | - | - | - | - | Applied To NEPRA on 15/08/2018.
|  |  | Applicant total (KW)= |  |  | 1074.14 | [5 empty] | Generation total (KW)= |  |  | 693.12
[6 empty] | 7501 | 1074.14