## -30.09.18
PRIORITY LIST OF PENDING RIPE CONNECTIONS WHERE 400-630-KVA T/FORMER PROPOSED
IN RESPECT OF MEPCO CIRCLE BAHAWALPUR
Priority No. | Name of Division | Name of S/Division | Application |  | Name of Consumer | Sanc: Load (KW) | Tariff | Capacity of T/Former | D.O.P | SCO/SJO |  | Reason for Non Installation of Connection
|  |  | No. | Date | [5 empty] | No. | Date
1 | M/Town | Satluj | 272/B2G/Misc. | 08.10.13 | Superintendent New Central Jail | 256 | B-2 | 400-KVA | 30.6.14 | 009253 | 10.08.15 | Work completed but progress awaited.
2 | M/Town | Shahdrah | 273A2C | 27.02.18 | Tehseen Ahmed Cheem Hospital | 350 | A-2C | 630-KVA | 27.4.18 | 089908 | 07.06.18 | NOC for purchase of TF has been issued to Consumer, but TF not provided uptill now. Letter has been issued.
3 | City | Yazman | 582/B2 | 13.07.18 | Iqbal Ghulab M/S Ghulab Cotton Factory Yazman | 450 | B-2 | 630-KVA | 13.8.18 | 5400090 74372 | 25.09.18 | Work under progress
4 | City | Yazman | 584/B2 | 29.08.18 | Abdul Sattar Asim M/S M.G Cotton Factory Yazman | 495 | B-2 | 630-KVA | 18.9.18 | 5400090 74385 | 25.09.18 | Documents of Self Purchase Transformer has been sent for verification
No. 4956-57/TR-2 |  |  |  | Dated: 24.10.2018.
Forwarded to :-
| 1- | The Director Commercial MEPCO Multan letter No. 7940/27704-06 dated 10.09.2018 for information please.
| 2- | Addl.CS Director MEPCO Multan w.r to his No. 8931/MC/DCM-39547-48 dated 12.10.1208 for information please.
-Sd-
Superintending Engineer
MEPCO Circle Bahawalpur

## -12.11.18
PRIORITY LIST OF PENDING RIPE CONNECTIONS WHERE 400-630-KVA T/FORMER PROPOSED
IN RESPECT OF MEPCO CIRCLE BAHAWALPUR
Upto 12.11.2018.
Priority No. | Name of Division | Name of S/Division | Application |  | Name of Consumer | Sanc: Load (KW) | Tariff | Capacity of T/Former | D.O.P | SCO/SJO |  | Reason for Non Installation of Connection
|  |  | No. | Date | [5 empty] | No. | Date
1 | M/Town | Satluj | 272/B2G/Misc. | 08.10.13 | Superintendent New Central Jail | 256 | B-2 | 400-KVA | 30.6.14 | 009253 | 10.08.15 | Work completed but progress awaited(Disputed case).
2 | M/Town | Shahdrah | 273A2C | 27.02.18 | Tehseen Ahmed Cheem Hospital | 350 | A-2C | 630-KVA | 27.4.18 | 089908 | 07.06.18 | Requirement of material has been sent to Manager (MM) MEPCO Multan.
3 | City | Yazman | 584/B2 | 29.08.18 | Abdul Sattar Asim M/S M.G Cotton Factory Yazman | 495 | B-2 | 630-KVA | 18.9.18 | 5400090 74385 | 25.09.18 | Pending due to non installation of meter by M&T
No. 5877/TR-2 |  |  |  | Dated: 12.11.2018.
Forwarded to :-
| 1- | The Director Commercial MEPCO Multan letter No. 7940/27704-06 dated 10.09.2018 for information please.
| 2- | Addl.CS Director MEPCO Multan w.r to his No. 9583/MC/DCM dated 30.10.1208 for information please.
-Sd-
Superintending Engineer
MEPCO Circle Bahawalpur

## -19.11.18
PRIORITY LIST OF PENDING RIPE CONNECTIONS WHERE 400-630-KVA T/FORMER PROPOSED
IN RESPECT OF MEPCO CIRCLE BAHAWALPUR
Upto 12.11.2018.
Priority No. | Name of Division | Name of S/Division | Application |  | Name of Consumer | Sanc: Load (KW) | Tariff | Capacity of T/Former | D.O.P | SCO/SJO |  | Reason for Non Installation of Connection
|  |  | No. | Date | [5 empty] | No. | Date
1 | M/Town | Satluj | 272/B2G/Misc. | 08.10.13 | Superintendent New Central Jail | 256 | B-2 | 400-KVA | 30.6.14 | 009253 | 10.08.15 | Work completed but progress awaited(Disputed case).
2 | M/Town | Shahdrah | 273A2C | 27.02.18 | Tehseen Ahmed Cheem Hospital | 350 | A-2C | 630-KVA | 27.4.18 | 089908 | 07.06.18 | Requirement of material has been sent to Manager (MM) MEPCO Multan.
No. ___________/TR-2 |  |  |  | Dated: ____________
Forwarded to :-
| 1- | The Director Commercial MEPCO Multan letter No. 7940/27704-06 dated 10.09.2018 for information please.
| 2- | Addl.CS Director MEPCO Multan w.r to his No. 9583/MC/DCM dated 30.10.1208 for information please.
Superintending Engineer
MEPCO Circle Bahawalpur

## -10.12.18
PRIORITY LIST OF PENDING RIPE CONNECTIONS WHERE 400-630-KVA T/FORMER PROPOSED
IN RESPECT OF MEPCO CIRCLE BAHAWALPUR
Upto 12.11.2018.
Priority No. | Name of Division | Name of S/Division | Application |  | Name of Consumer | Sanc: Load (KW) | Tariff | Capacity of T/Former | D.O.P | SCO/SJO |  | Reason for Non Installation of Connection
|  |  | No. | Date | [5 empty] | No. | Date
1 | M/Town | Shahdrah | 273A2C | 27.02.18 | Tehseen Ahmed Cheem Hospital | 350 | A-2C | 630-KVA | 27.4.18 | 089908 | 07.06.18 | Requirement of material has been sent to Manager (MM) MEPCO Multan.
2 | M/Town | M/Town | 278A2C | 02.11.18 | M/S Aleen Hospital | 351 | A-2C | 630-KVA | 07.12.18 |  |  | NOC for purchase of TF has been issued to Consumer.
No. 7507-08/TR-2 |  |  |  | Dated: 11.12.2018.
Forwarded to :-
| 1- | The Director Commercial MEPCO Multan letter No. 7940/27704-06 dated 10.09.2018 for information please.
| 2- | Addl.CS Director MEPCO Multan w.r to his No. 9583/MC/DCM dated 30.10.1208 for information please.
-Sd-
Superintending Engineer
MEPCO Circle Bahawalpur