## Priority 400 & 630 T.F 30-11-18
PRIORITY LIST OF PENDING RIPE CONNECTIONS WHERE 400-KVA AND 630-KVA SELF PURCHASED TRANSFORMERS IS TO BE INSTALLED IN RESPECT OF MEPCO CIRCLE MULTAN.
Status Ending 30-11-18
Sr. No | Name of Division | Name of S/Divn | Application |  | Name of Consumer | Sanctioned Load (KW) | Tariff | Capacity of Transformer (KVA) | Date of payment | SCO / SJO |  | Reason for non installation of connection
|  |  | No | Date | [5 empty] | No | Date
New Industrial B-2 Connections
1 | S.R.Alam | New Multan | 1286 | 2015-03-17 | Malik Ghulam Muhammad | 158 | B-2 | 400 | 2015-04-23 | 085985 | 2016-01-12 | Connection Pending on consumer Request
2 | City | W/Abad | 1444 | 2017-04-26 | M/S Yousaf feed Mill | 495 | B-2 | 630 | 2017-07-26 | 086701 | 2017-10-23 | Pending with M&T
3 | Mumtazabad | Qasba Maral | 1488 | 2018-01-04 | M/S Faisal Feeds Pvt Ltd | 340 | B-2 | 630 | 2018-01-31 | 086760 | 2018-04-13 | Pending on consumer request
4 | Cantt | Ind: Estate | 15118001213 | 2018-07-03 | Muhammad Shahbaz PVC Pipe Factory | 495 | B-2 | 630 | 2018-08-30 |  |  | Inspection Certificate sent to Lahore for verification
5 | City | W/Abad | 15132001551 | 2018-08-14 | Imtiaz Hussain S/O Muhammad Subhan | 220 | B-2 | 400 | 2018-10-03 |  |  | Self Purchase Documents are awaited
6 | Mumtazabad | Mumtazabad | 15121001760 | 2018-10-15 | Glacries Private Limited C/O Talib Zaki | 495 | B-2 | 630 | 2018-10-18 | 1510011127606 | 2018-11-23 | Work Under Progress
7 | Mumtazabad | Mumtazabad | 15121001813 | 2018-10-19 | M/S Yahar PVT Ltd C/O Ammer Hamza S/O Muhammad Yasin | 400 | B-2 | 630 | 2018-11-06 |  |  | Self Purchase Documents are awaited
Industrial B-2/Extension Connections
1 | Mumtazabad | Mumtazabad | 866 | 2016-12-26 | M/S S.M Food Makers | 139-439 | B-2 | 630 | 2017-01-28 |  |  | Disputed Case
2 | Cantt | Ind: Estate | 949 | 2018-01-22 | M/S NASCO Pvt Ltd | 300-495 | B-2 | 630 | 2018-05-23 |  |  | Self Purchase Documents are awaited
3 | City | W/Abad | 973 | 2018-11-07 | Asghar Ali (Printing Press) | 38-200 | B-2 | 400 | 2018-12-07 |  |  | Self Purchase Documents are awaited
New Government Connections
1 | Musa Pak | Hassanabad | 391 | 2017-01-26 | Regional Office CTD Police | 400 | C-1 | 630 | 2017-03-03 | 012154 | 2018-04-18 | Balance Material D-fuse Fitting & Stay Wire is required
2 | Musa Pak | Bosan Road | 403 | 2017-04-21 | Incharge Citizan Facilitation Center | 220 | A-1B | 400 | 2017-05-26 | 012151 | 2017-10-18 | Material allocated but Pending in S/Div:
Government Extension of Load
1 | S.R.Alam | S.R.Alam | 241 | 2016-10-03 | Regional Director, Allama Iqbal Open University | 69-229 | A-1B | 400 | 2016-11-30 | 197687 | 2017-08-24 | Self Purchased T/Former found faulty & not replaced with Healty
2 | City | G/Town | 416 | 2017-08-24 | Secretary Board of Management | 278-494 | B-2 | 630 | 2017-11-02 |  |  | Self Purchase Documents are awaited
3 | Shujabad | Jalal Pur Pirwala | 425 | 2018-03-09 | Senior Medical Officer THQ Jalal Pur Pirwala | 96-310 | A-1B | 400 | 2018-06-29 |  |  | Self Purchase Documents are awaited
Commercial A-2(C)/Extension Connections
1 | Musa Pak | Wapda Town | 272 | 2018-07-09 | M/S Toyota Motors | 150-234 | A-2C | 400 | 2018-07-18 | 258211 | 2018-12-04 | Work Under Progress
2 | Musa Pak | Wapda Town | 274 | 2018-08-07 | Defence Housing Authority (Office) | 158-319 | A-2C | 400 | 2018-09-27 |  |  | Inspection Certificate sent to Lahore for verification
Tarif (A-3) Connections
1 | S.R.Alam | S.R.Alam | 26 | 2018-10-25 | Shafqat Rasool Aslam S/O Ch. Muhammad Aslam | 158 to 320 | A-3 | 400 | 2018-10-30 | 258210 | 2018-12-04 | Work Under Progress
2 | Musa Pak | Hassanabad | 25 | 2018-09-26 | M/S Mukhtar-e-Sheikh Memorial Welfare Hospital | 485 | A-3 | 630 | 2018-11-13 |  |  | Self Purchase Documents are awaited
3 | Cantt | Ind: Estate | 27 | 2018-11-06 | M/S Roomi Holdings (Pvt) Ltd | 158 to 495 | A-3 | 630 | 2018-11-15 |  |  | Self Purchase Documents are awaited