## abstract 060218
Progress of Net Metering (Dated: 06-02-2018)
Description | Detail | Remarks
No. of Applications Received | 14 | -
No. of Connections Installed | 12 | Billing of 6 Connections is Started & 6 is Under Process
Application Expired | 1 | Cancelled due to Non-Payment of DN.
Applications Under Process | 1 | Case is Incomplete, intimated to Consumer for submission of Load Flow Study.

## Net-Metering-Info 0602
NET METERING APPLICATION(S) INFORMATION/STATUS
COMPANY NAME: MEPCO Dated:06-02-2018
Application No. | Name of Applicant | Sub Division Code | Tariff | Application Date | Reference No. | Sanctioned Load | Required Load for Net Metering | Name of Installer | Applied To NEPRA (Yes or No) | Generation Licence | Feeder | Installation Status (Installed or Uninstalled) | Installation Date | Billing Started (Yes or No) | Billing Start Date | Generation (KW) | Remarks | Current Position (What is Present Status i.e. either with installer or SDO or NEPRA etc.)
1 | OFFICE BUILDING TEHSILDAR LODHRAN NEAR MARKET COMMITTEE OFFICE LODHRAN | 15421 | A-1b(03)T | 2016-06-18 | 03154210167800 | 11 | 3 | M/S Creative Electronics | Yes | Issued | City Lodhran | Installed | 2018-01-06 | Yes | 2018-01-10 | 3 | Connection Installed. Billing Started | -
2 | XEN CIVIL MEPCO | 15173 | A-1b(03)T | 2016-07-12 | 13151734972100 | 12 | 3 | Reap | Yes | Issued | Wapda Colony | Installed | 2016-07-28 | Yes | 2016-08-23 | 3 | Connection Installed. Billing Started | -
3 | Khalid Nazeer Commissioner Sahiwal | 15512 | A-1b(03)T | 2016-08-12 | 12155121038000 | 7 | 3 | M/S Creative Electronics | Yes | Issued | Civil Line | Not Installed |  |  |  |  | Demand Notice Issued to Consumer but he did not pay the DN within stipulated time. | Cancelled due to Non Payment of DN.
4 | MLK NOOR ASGHAR BUCHA S/O MLK NOOR MUHAMMAD BUCHA THE GRAND COMMERCIAL BUILDING BUCH VILLAS H/S BOSAN ROAD MTN | 15175 | A-2c(06)T | 2016-09-12 | 27151758887001 | 857 | 25.5 | Orient Energies (Pvt) Ltd. | Yes | Issued | Buch Villas | Installed | 2018-01-17 | NO | NIL | 25.5 | Connection Installed Billing under Process | In Current Billing Cycle Net Bill will be Issued
5 | Asif Iqbal SM Bashir Agencies | 15514 | A-2a(04) | 2016-12-15 | 03155140275502 | 5 | 4.62 | Royal Energy Sultan Electronics | Yes | Issued | College Road | Installed | 18-01-2017 | NO | NIL | 4.62 | Connection Installed Billing under Process | In Current Billing Cycle Net Bill will be Issued
6 | MUHAMMAD ARSHAD NADEEM S-O MHAMMAD ASHIQ ST NO 1 MADINA ABAD CLY MTN MULTAN | 15132 | A-1b(03)T | 2017-01-06 | 13151322030405 | 5 | 10 | Solar Tech. | Yes | Issued | Timber Market | Installed | 2017-12-17 | Yes | 2017-12-21 | 10 | Connection Installed. Billing Started | -
7 | SAJIDA KHALID W/O CH.KHALID LATIF PUNJAB SMALL INDUSTRIES MTN | 15175 | A-1b(03)T | 2017-01-26 | 17151753136101 | 5 | 10 | Pak Friends Enterprises | Yes | Issued | Peer Akbar Shah | Installed | 2017-12-19 | Yes | 2017-12-20 | 10 | Connection Installed. Billing Started | -
8 | UNILEVER PAKISTAN LIMITED TEA FACTORY CHAK NO.88-A10R KHANEWAL | 15913 | B3(14)T | 2017-02-08 | 27159132372500 | 503 | 110 | Reon | Yes | Issued | UNILEVER TEA FACTORY | Installed | 2018-01-16 | NO | NIL | 110 | Connection Installed Billing under Process | In Current Billing Cycle Net Bill will be Issued
9 | KHAWAJA MUHAMMAD YOUNIS S-O KHAWAJA MUHAMMAD MASOOD FATIMA MODEL SCHOOL MULTAN ROAD K.WALA | 15921 | A-1b(03)T | 2017-03-03 | 28159210647407 | 6 | 5 | Preimer Energy (Pvt) Ltd. | Yes | Issued | Masood Spinning-2 | Installed | 2017-12-21 | NO |  | 5 | Connection Installed Billing under Process | In Current Billing Cycle Net Bill will be Issued
10 | KH MUHAMMAD YOUNIS S-O MUHAMMAD MASOOD 13 B OFFICER CLY MULTAN | 15172 | A-1b(03)T | 2017-03-03 | 18151723474200 | 12 | 32 | Preimer Energy (Pvt) Ltd. | Yes | Issued | Eid Gah | Installed | 2017-12-19 | Yes | 2017-12-27 | 32 | Connection Installed. Billing Started | -
11 | MEHMOOD TEXTILE MILLS LTD MULTAN LOHARI GATE MULTAN CITY | 15113 | A-2c(06)T | 2017-03-03 | 27151130721400 | 200 | 64 | Preimer Energy (Pvt) Ltd. | Yes | Issued | Abdali Road | Installed | 2018-01-29 | NO | - | 64 | Connection Installed Billing under Process | In Current Billing Cycle Net Bill will be Issued
12 | Kh M Younas M/S MASOOD SPINNING MILLS UNIT NO.02 04-KM MULTAN ROAD KABIR WALA | 15921 | B3(14)T | 2017-03-03 | 30159212533901 | 4999 | 320 | Preimer Energy (Pvt) Ltd. | Yes | Issued | Masood Spinning-2 | Installed | 2018-01-31 | NO | - | 320 | Connection Installed Billing under Process | Connection Installed Billing under Process
13 | SHABBIR AHMAD S-O MIRAJ DIN EASTREN PRODUCTS-VITAL TEA LTD QAZI WALA HAROON ABAD | 15821 | B2b (12)T | 2017-12-26 | 27158210966702 | 482 | 300 | REON | NO | No | KHATAN | Not Installed |  |  |  |  | Pending at Installer for provision of technical detail | Pending at Installer for provision of technical detail
14 | NAIMAT ULLAH S.O ALLAH BACHAYA QURESHI 259-N WAPDA TOWN-11 MTN | 15175 | A-1b(03)T | - | 17151753132415 | 5 | 10 | - | Yes | Issued | Wapda Town | Installed | 2017-12-19 | YES | 2017-12-20 | 10 | Connection Installed. Billing Started | -
[12 empty] | Generation total (KW)= |  |  |  | 597.12