## Sheet1
MEPCO ANNUAL PROCUREMENT PLAN FOR GRID STATION & TRANSMISSION LINE MATERIAL F.Y 2016-17 (UNDER RULE 8 AND 9 OF THE PUBLIC PROCUREMENT RULES 2004)
Sr. No. | Name of Procurement | Estimated Cost (PKR in Million) | Procurement Method | Tentative date of Procurement Notice Publication | Tentative date of Award of Contract | Tentative date of completion | Remarks
1 | 132/11.5KV, 31.5/40 MVA Power Transformer | 148.5 | NCB | 10.08.2016 | 01.11.2016 | 01.04.2017 | PMU-52 (Lot-I)
2 | 11KV Switchgear Panels | 410 | NCB | 10.08.2016 | 02.11.2016 | 02.04.2017 | PMU-52 (Lot-II)
3 | Energy Meters for Grid Metering | 25 | NCB | 10.08.2016 | 03.11.2016 | 03.04.2017 | PMU-52 (Lot-III)
4 | 132KV Circuit Breakers | 180 | NCB | 10.08.2016 | 04.11.2016 | 04.04.2017 | PMU-52 (Lot-IV)
5 | 132KV Beam, Column & Earthing Platform | 9 | NCB | 10.08.2016 | 07.11.2016 | 07.04.2017 | PMU-52 (Lot-V)
6 | Relay Panel type RP-3 & RP-4 | 14 | NCB | 10.08.2016 | 08.11.2016 | 08.04.2017 | PMU-52 (Lot-VI)
7 | Control Panels & Station AC/DC Panels | 20.5 | NCB | 10.08.2016 | 10.11.2016 | 10.04.2017 | PMU-52 (Lot-VII)
8 | All: Conductor 600 mm sq | 2.7 | NCB | 10.08.2016 | 11.11.2016 | 11.04.2017 | PMU-52 (Lot-VIII)
9 | SF-6 Gas for Circuit Breakers | 7 | NCB | 10.08.2016 | 14.11.2016 | 14.04.2017 | PMU-52 (Lot-IX)
10 | Termination Kits | 26 | NCB | 10.08.2016 | 15.11.2016 | 15.04.2017 | PMU-52 (Lot-X)
11 | 132KV Tower Extensions | 6 | NCB | 17.08.2016 | 17.11.2016 | 17.04.2017 | PMU-53 (Lot-I)
12 | 220KV Towers & Extensions | 23.5 | NCB | 17.08.2016 | 18.11.2016 | 18.04.2017 | PMU-53 (Lot-II)
13 | LYNX Conductor & Earth-wire | 27.5 | NCB | 17.08.2016 | 21.11.2016 | 21.04.2017 | PMU-53 (Lot-III)
14 | Stay Wire | 0.5 | NCB | 17.08.2016 | 22.11.2016 | 22.04.2017 | PMU-53 (Lot-IV)
15 | Disc Insulators | 48 | NCB | 17.08.2016 | 23.11.2016 | 23.04.2017 | PMU-53 (Lot-V)
16 | Hardware for Rail | 6 | NCB | 17.08.2016 | 24.11.2016 | 24.04.2017 | PMU-53 (Lot-VI)
17 | Hardware for Lynx | 36 | NCB | 17.08.2016 | 25.11.2016 | 25.04.2017 | PMU-53 (Lot-VII)
18 | Hardware for Earth-Wire | 5 | NCB | 17.08.2016 | 28.11.2016 | 28.04.2017 | PMU-53 (Lot-VIII)
19 | Hardware for Dog | 2.5 | NCB | 17.08.2016 | 29.11.2016 | 29.04.2017 | PMU-53 (Lot-IX)
20 | V-Shakle & T-Clamps | 2 | NCB | 17.08.2016 | 30.11.2016 | 30.04.2017 | PMU-53 (Lot-X)
21 | Pulling Grips & Measuring Stick | 1 | NCB | 17.08.2016 | 01.12.2016 | 01.05.2017 | PMU-53 (Lot-XI)
22 | Nut & Bolts | 0.7 | NCB | 17.08.2016 | 02.12.2016 | 02.05.2017 | PMU-53 (Lot-XII)
23 | Grounding Sets for Towers | 8 | NCB | 17.08.2016 | 05.12.2016 | 05.05.2017 | PMU-53 (Lot-XIII)
24 | Cartridge & Mould | 12 | NCB | 24.08.2016 | 22.12.2016 | 22.05.2017 | PMU-54 (Lot-I)
25 | 132KV Bus & Line Isolators | 30 | NCB | 24.08.2016 | 23.12.2016 | 23.05.2017 | PMU-54 (Lot-II)
26 | 132KV Line CTs & 11KV Neutral CTs | 25 | NCB | 24.08.2016 | 26.12.2016 | 26.05.2017 | PMU-54 (Lot-III)
27 | Batteries 110V | 15 | NCB | 24.08.2016 | 27.12.2016 | 27.05.2017 | PMU-54 (Lot-IV)
28 | Grounding Conductor | 16 | NCB | 24.08.2016 | 28.12.2016 | 28.05.2017 | PMU-54 (Lot-V)
29 | Aux. Transformer 200 KVA | 2.5 | NCB | 24.08.2016 | 29.12.2016 | 29.05.2017 | PMU-54 (Lot-VI)
30 | Tension String Assembly & P.G Clamp | 1 | NCB | 24.08.2016 | 30.12.2016 | 30.05.2017 | PMU-54 (Lot-VII)
31 | Protection Relays | 30.5 | NCB | 24.08.2016 | 02.01.2017 | 02.06.2017 | PMU-54 (Lot-VIII)
32 | Control Cables | 39 | NCB | 24.08.2016 | 03.01.2017 | 03.06.2017 | PMU-54 (Lot-IX)
33 | Power Cables | 42 | NCB | 24.08.2016 | 04.01.2017 | 04.06.2017 | PMU-54 (Lot-X)
34 | 11KV PTs | 3.5 | NCB | 31.08.2016 | 06.01.2017 | 06.06.2017 | PMU-55 (Lot-I)
35 | 11KV Incoming Vacuum Interrupters | 13.5 | NCB | 31.08.2016 | 09.01.2017 | 09.06.2017 | PMU-55 (Lot-II)
36 | 11KV Outgoing Vacuum Interrupters | 31.5 | NCB | 31.08.2016 | 10.01.2017 | 10.06.2017 | PMU-55 (Lot-III)
37 | 11KV Incoming Trolleys | 40 | NCB | 31.08.2016 | 11.01.2017 | 11.06.2017 | PMU-55 (Lot-IV)
38 | 11KV Outgoing Trolleys | 60 | NCB | 31.08.2016 | 12.01.2017 | 12.06.2017 | PMU-55 (Lot-V)
39 | 11KV Incoming CTs | 7 | NCB | 31.08.2016 | 13.01.2017 | 13.06.2017 | PMU-55 (Lot-VI)
40 | 11KV Outgoing CTs | 7 | NCB | 31.08.2016 | 16.01.2017 | 16.06.2017 | PMU-55 (Lot-VII)
41 | Capacitor Fuse Link | 0.1 | NCB | 31.08.2016 | 17.01.2017 | 17.06.2017 | PMU-55 (Lot-VIII)
42 | 100KVAR & 200KVAR Capacitor Units | 96 | NCB | 31.08.2016 | 18.01.2017 | 18.06.2017 | PMU-55 (Lot-IX)
43 | 400 KVAR Capacitor Units | 2 | NCB | 31.08.2016 | 19.01.2017 | 19.06.2017 | PMU-55 (Lot-X)
44 | Capacitor Racks | 78 | NCB | 31.08.2016 | 20.01.2017 | 20.06.2017 | PMU-55 (Lot-XI)
45 | Bus Bar Insulators | 0.5 | NCB | 31.08.2016 | 23.01.2017 | 23.06.2017 | PMU-55 (Lot-XII)